## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-011 - LANDSCAPING (Rev A) | [5 empty] | SYM-ITP-011 - LANDSCAPING (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Conformity with Drawings
label | Ref docs: TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
checkpoint | 1.2 - Sample Submission & Approval
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0171
label | Acceptance criteria:
button | • Have all relevant samples been provided to CYP and approved? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
label | CYP D&C JV - Key: H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test results to be provided at least 5 working days prior to bulk deliveries
holdpoint | HOLD POINT
section | 2.0 Pre-Construction Activities
checkpoint | 2.1 - Plant Set-Out
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0752
label | Acceptance criteria:
button | • Have all plants been set out in garden beds prior to planting? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
section | 3.0 Construction Activities
checkpoint | 3.1 - Cultivation of sub-grade
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0751
label | Acceptance criteria:
button | • Has cultivation been undertaken as specified? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.2 - Installation of imported topsoil / subsoil / structural soil
label | Ref docs:
label | • TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 - Section 0751
label | • TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Has topsoil been placed in the manner specified, alongside to the depth specified in detail on drawing set? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.3 - Installation of imported organic / inorganic mulch
label | Ref docs:
label | • TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0753
label | • TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Has mulch been placed in the manner specified, alongside to the depth specified in detail on drawing set? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.4 - Installation of edging
label | Ref docs:
label | • TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0779
label | • TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Has edging been placed in the manner specified, referencing both design standards, drawing details and manufacturers recommendations (where relevant)? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • All City of Melbourne standard / engineering drawings for relevant edging types can be found in Appendix A3: Authority Design Standards
checkpoint | 3.5 - Installation of plants
label | Ref docs:
label | • TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0753
label | • TAS-A-AUD-6007-0426 - LANDSCAPE
label | Acceptance criteria:
button | • Have all plants been placed / installed in the manner specified? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.6 - Installation of turf
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 - Section 0758
label | Acceptance criteria:
button | • Has turf been installed as per method described in section 3.17 ‘turfing’? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot