## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-013 - Retaining walls and wall footings (Rev A) | [5 empty] | SYM-ITP-013 - Retaining walls and wall footings (Rev A)
section | 1.0 General Details
checkpoint | 1.1 - Material classification and source
label | Ref docs:
label | • 503.04
label | • VR 610.07
label | • AS 1379
label | Acceptance criteria:
button | • Is Mix design approved prior to placemen and material properties meet project specification, AS 3600, AS 1379. | Yes,No,N/A
textbox | Concrete Strength |  |  | MPA
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.2 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | Wall/Footing Reference
textbox | Zone
textbox | Stage
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 1.3 - Conformity with Drawings
label | Ref docs: Aconex Documents Register
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
holdpoint | HOLD POINT
checkpoint | 1.4 - Excavation Permit & Penetration Permit
label | Ref docs: SMP VR 602.03
label | Acceptance criteria:
button | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services. | Yes,No,N/A
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | Yes,No,N/A
textbox | Excavation to a total depth of |  |  | mm
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach completed Permit
holdpoint | HOLD POINT
section | 2.0 Wall Footings
checkpoint | 2.1 - Formwork
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | • VR 614.04
label | • VR 613.04
label | • Table 614.041
label | Acceptance criteria:
label | • Formwork has been installed correctly and sufficiently braced. | Yes,No,N/A
label | • Formwork set out has been done as per latest design drawings and specifications | Yes,No,N/A
label | • Were Construction joints/Expansion Joints/Isolation Joints Installed | Yes,No,N/A
label | • Any Backfill/ Underlay Material as per drawings & specifications | Yes,No,N/A
label | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified | Yes,No,N/A
label | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach formwork design and approvals
checkpoint | 2.2 - Reinforcement
label | Ref docs:
label | • AS3600
label | • VR611
label | • VR610
label | Acceptance criteria:
button | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm. | Yes,No,N/A
button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | Yes,No,N/A
button | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars | Yes,No,N/A
button | • Correct concrete cover and chairs on sides, bottom and top Verified | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 2.3 - Pre-pour Inspections
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
button | • Has steel reinforcement been placed correctly with adequate cover? | Yes,No,N/A
button | • Have tie bars and expansion joints been installed at the correct intervals? | Yes,No,N/A
button | • Pour area is free of loose debris, oils, water | Yes,No,N/A
button | • Have any services located within the slab been installed, surveyed and pinned down | Yes,No,N/A
button | • Concrete Testing Lab Representative will be available during concrete pour | Yes,No,N/A
button | • CYP D&C JV informed of concrete pour date and start time | Yes,No,N/A
label | Freq: Prior to start of each Concrete Pour
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 2.4 - Concrete Placement
label | Ref docs:
label | • VR503.07
label | • VR503.05
label | Acceptance criteria:
button | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials. | Yes,No,N/A
button | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects. | Yes,No,N/A
button | • Has a minimum of one of vibrator used at all times while the concreting is in operation | Yes,No,N/A
button | • Ensure monitoring forms/cast in items during the pour | Yes,No,N/A
button | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy | Yes,No,N/A
button | • Concrete Dockets Received, Attach last Docket | Yes,No,N/A
textbox | Pour date
textbox | Total pour Concrete quantity |  |  | M3
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Delivery Doc
label | • Conc pour record
checkpoint | 2.5 - Post Pour
label | Acceptance criteria:
button | • Was Curing agent applies as per project specifications | Yes,No,N/A
button | • Concrete reached design strength to strip formwork | Yes,No,N/A
button | • Any identified defects after striping rectified | Yes,No,N/A
button | • Attach Subcontractor’s QA | Yes,No,N/A
button | • Does Backfill material compl;y with Vicroad specs, Project specs and drawings? | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Concrete Strength Report
checkpoint | 2.6 - Backfilling
label | Ref docs: VR703.29
label | Acceptance criteria:
label | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
label | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
section | 3.0 Retaining Walls
checkpoint | 3.1 - Formwork
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
label | • Formwork has been installed correctly and sufficiently braced. | Yes,No,N/A
button | • Formwork set out has been done as per latest design drawings and specifications | Yes,No,N/A
button | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed | Yes,No,N/A
button | • Any Backfill/ Underlay Material as per drawings & specifications | Yes,No,N/A
button | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified | Yes,No,N/A
button | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 3.2 - Reinforcement
label | Ref docs:
label | • AS3600
label | • VR611
label | Acceptance criteria:
button | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm. | Yes,No,N/A
button | • Steel is free of excess corrosion, loose millings, oil or other contaminants | Yes,No,N/A
button | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars | Yes,No,N/A
button | • Correct concrete cover and chairs on sides, bottom and top Verified | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 3.3 - Pre-pour Inspections
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
button | • Has steel reinforcement been placed correctly with adequate cover? | Yes,No,N/A
button | • Have tie bars and expansion joints been installed at the correct intervals? | Yes,No,N/A
button | • Pour area is free of loose debris, oils, water | Yes,No,N/A
button | • Have any services located within the slab been installed, surveyed and pinned down | Yes,No,N/A
button | • Concrete Testing Lab Representative will be available during concrete pour | Yes,No,N/A
button | • CYP D&C JV informed of concrete pour date and start time | Yes,No,N/A
label | Freq: Prior to start of each Concrete Pour
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SS
label | CYP D&C JV - Key: H
holdpoint | HOLD POINT
checkpoint | 3.4 - Concrete Placement
label | Ref docs:
label | • VR503.07
label | • VR503.05
label | Acceptance criteria:
button | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials. | Yes,No,N/A
button | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects. | Yes,No,N/A
button | • Has a minimum of one of vibrator used at all times while the concreting is in operation | Yes,No,N/A
button | • Ensure monitoring forms/cast in items during the pour | Yes,No,N/A
button | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy | Yes,No,N/A
button | • Concrete Dockets Received, Attach last Docket | Yes,No,N/A
textbox | Pour date
textbox | Total pour Concrete quantity |  |  | M3
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Delivery Doc
label | • Conc pour record
checkpoint | 3.5 - Post Pour
label | Ref docs:
label | • Civil drawings.
label | • Project Specs
label | Acceptance criteria:
button | • Was Curing agent applies as per project specifications | Yes,No,N/A
button | • Concrete reached design strength to strip formwork | Yes,No,N/A
button | • Any identified defects after striping rectified | Yes,No,N/A
button | • Attach Subcontractor’s QA | Yes,No,N/A
button | • Does Backfill material compl;y with Vicroad specs, Project specs and drawings? | Yes,No,N/A
button | • Were as Built completed? Attach report if applicable | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Concrete Test Report
checkpoint | 3.6 - Backfilling
label | Ref docs: VR703.29
label | Acceptance criteria:
label | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
label | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark. | Yes,No,N/A
label | Freq: Each Lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot