## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-018 - Public Lighting (Rev A) | [5 empty] | SYM-ITP-018 - Public Lighting (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs: Lot map
label | Acceptance criteria:
button | • Has the lot been defined and marked up on lot map? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Lot map
holdpoint | WITNESS POINT
checkpoint | 1.2 - Survey set-out
label | Acceptance criteria:
button | • Has the work area been set out as per IFC drawings? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
holdpoint | WITNESS POINT
section | 2.0 Traffic Signals Installation
checkpoint | 2.1 - Public lighting construction
label | Ref docs: IFC Drawings VR 731
label | Acceptance criteria:
button | • Has the public lighting been constructed in accordance with the IFC Drawings? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Subcontractor ITP's
holdpoint | WITNESS POINT
checkpoint | 2.2 - Testing and Commissioning
label | Ref docs: IFC Drawings VR 731
label | Acceptance criteria:
button | • Has the public lighting passed all commissioning and testing? | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Subcontractor ITP's
holdpoint | WITNESS POINT
checkpoint | 2.3 - Powercor Approval
label | Acceptance criteria:
button | • Powercor inspection & approval provided? | Yes,No,N/A
textbox | Date
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Subcontractor ITP's
holdpoint | HOLD POINT
section | 4.0 Conformance check
checkpoint | 4.1 - Test Reports & As-builts
label | Ref docs: Subcontractor ITP
label | Acceptance criteria:
button | • All Test reports and as builts received and reviewed. | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Test reports
label | • As-builts
holdpoint | WITNESS POINT
checkpoint | 4.2 - Product non-conformance
label | Acceptance criteria:
button | • All Product Non-Conformance(s) recorded and closed (if applicable) | Yes,No,N/A
label | Freq: Each lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: W
label | Symal Infrastructure - Resp: SE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Completed NCR form
holdpoint | WITNESS POINT
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot