## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-019 - CLADDING (Rev A) | [5 empty] | SYM-ITP-019 - CLADDING (Rev A)
section | 1.0 Preliminaries
checkpoint | 1.1 - Conformity with Drawings
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC)
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
holdpoint | HOLD POINT
section | 2.0 Pre-Construction Activities
checkpoint | 2.1 - Survey Set-Out
label | Ref docs: TAS-A-AUD-6007-0426 – LANDSCAPE (IFC) & TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 Stone Cladding
label | Acceptance criteria:
button | • Has the structure been surveyed, including any fixing inserts, before commencement? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 2.2 - Installation Considerations
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 (Stone Cladding 3.4)
label | Acceptance criteria:
button | • Is the structure clear of dirt and blemishes? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
section | 3.0 Construction
checkpoint | 3.1 - Fixings
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 (Stone Cladding – 3.5)
label | Acceptance criteria:
button | • Have stone cladding fixings been provided as required, sufficient to support, restrain and resist the structural design loads on each cladding panel, as specified? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.2 - Adhesives
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 (Stone Cladding – 3.5)
label | Acceptance criteria:
button | • Have adhesives been applied where required, as specified? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 3.3 - Installation of cladding
label | Ref docs: TAS-HWW-SDL-ZWD-SPC-AUD-SDU-A0010-00 – Section 0433 (Stone Cladding – 3.7)
label | Acceptance criteria:
button | • Has cladding been installed as described in specification, considering given tolerances? | Yes,No,N/A
label | Freq: Per lot
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot