## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-021 - Precast Concrete Elements (Rev A) | [5 empty] | SYM-ITP-021 - Precast Concrete Elements (Rev A)
section | 1.0 Preliminaries, Pre-delivery
checkpoint | 1.1 - Suppliers QA
label | Ref docs: VR620 Project Specs
label | Acceptance criteria:
button | • Has the pre-pour check been completed? | Yes,No,N/A
button | • Has the ITP been completed supplied? | Yes,No,N/A
button | • Have the concrete test certificates been supplied? | Yes,No,N/A
button | • Has the certificate of compliance been supplied? | Yes,No,N/A
label | Freq: Upon delivery of Element
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Pre Pour Check
label | • Precast element Supplier ITP
label | • Concrete Test Certificates
label | • Certificate of compliance
checkpoint | 1.2 - Transporting
label | Ref docs: Vicroads 620.08
label | Acceptance criteria:
button | • Has the concrete reached its 28-day compressive strength Prior to Transport and not transported before 7 days after casting? | Yes,No,N/A
button | • Any defects (Cracks, chips, honeycomb etc) identified. | Yes,No,N/A
label | Freq: Upon delivery of Element
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SE/PE
checkpoint | 1.3 - Element Detail
label | Acceptance criteria:
textbox | Precast element/s Reference/Type/s
textbox | Zone
textbox | Stage
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Pictures
section | 2.0 Installation of Precast Element
checkpoint | 2.1 - Excavation Permit & Penetration Permit & Bedding
label | Ref docs:
label | • SMP
label | • VR 602.03
label | Acceptance criteria:
button | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services. | Yes,No,N/A
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • 50mm Blinding to be placed as required to allow working surface and protect excavation. | Yes,No,N/A
textbox | Excavation to a total depth of |  |  | mm
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE
holdpoint | HOLD POINT
checkpoint | 2.2 - Installation of precast Element and Backfilling
label | Ref docs:
label | • SMP
label | • IFC Drawings
label | Acceptance criteria:
button | • Has survey set out points identified and existing condition of location checked to ensure suitability of install. | Yes,No,N/A
button | • Has the Precast element been constructed in accordance with the IFC drawings? | Yes,No,N/A
button | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour? | Yes,No,N/A
label | Freq: All stages of Install
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: R
label | Symal Infrastructure - Resp: SS
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot