## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-ITP-024 - Handrails & Balustrades (Rev A) | [5 empty] | SYM-ITP-024 - Handrails & Balustrades (Rev A)
section | 1.0 Handrails & Balustrades
checkpoint | 1.1 - Set Out
label | Ref docs: Civil drawings
label | Acceptance criteria:
button | • Is the work area clearly pegged out for line and level? | Yes,No,N/A
textbox | • Handrail/Balustrade Reference
textbox | • Zone
textbox | • Stage
label | Freq: Prior to the Start of Activity
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: S
label | Symal Infrastructure - Resp: SS
checkpoint | 1.2 - Conformity with Drawings
label | Ref docs: Civil Drawings
label | Acceptance criteria:
button | • Are the drawings, complete & current? | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach Recent IFC Drawings
label | • Attach Shop Drawings
holdpoint | HOLD POINT
checkpoint | 1.3 - Permit &
label | Ref docs: SMP
label | Acceptance criteria:
button | • Relevant permits have been signed and approved. | Yes,No,N/A
button | • Extents and levels correct to relevant drawings | Yes,No,N/A
button | • Are handrails and Balustrades compliant with DDA standards. | Yes,No,N/A
label | Freq: Prior to start of works
label | VERIFY OF ACCEPTANCE BY
label | Symal Infrastructure - Key: H
label | Symal Infrastructure - Resp: SE/PE
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach completed Permit
holdpoint | HOLD POINT
checkpoint | 1.4 - Material compliance
label | Ref docs: QMP
label | Acceptance criteria:
button | • Are handrails and Balustrades compliant with DDA standards. | Yes,No,N/A
checkpoint | 1.5 - Subcontractor ITP
label | Ref docs: QMP
label | Acceptance criteria:
button | • Have the subcontractor ITP’s been completed and attached | Yes,No,N/A
button | • Have handrail and Balustrades been installed as per approved shop drawings? | Yes,No,N/A
button | • All edges smoothed and final finish provided as per project specs? | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach subcontractor ITP
checkpoint | 1.6 - As Built
label | Acceptance criteria:
button | Were survey as-builts completed | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc):
label | • Attach survey Report
checkpoint-no-status | Lot acceptance:
textbox | Works complete (signer SS)
textbox | Date works complete
textbox | Lot conforms (signer PE)
textbox | Date lot closed
textbox | NCR/s no. raised
textbox | Date NCR closed for this lot