## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e5810070-73de-4a2c-9310-5b71f4fe8e21 | checklist | Floor Preparation |  | Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7fbc7582-aba0-411a-9cb4-857dc5d591c3 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
e612fa2f-b46a-4db3-a2fa-32c82254cf63 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
248a95df-4147-4cb0-83f7-f7fffcffe746 | checkpoint | Has screeding been completed to shower at correct height and falls - R4 screed
33522bd6-16d2-450d-9b78-23fb1e7990ea | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
f13c85e5-a85d-4e37-b581-4ef76c61090b | checkpoint | Grinding completed before works (photo required) after works (photo required)
a173534a-b5be-49b7-917f-0e729009c3b4 | checkpoint | Floor levelling completed - hours and bags used to be recorded
aa802266-596e-44f3-abdd-79d5d78acfd7 | checklist | Other Information |  | Other Information
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
13b5f924-e2a6-46f6-8473-d4fb35b949f1 | checkpoint | Variations or extra works added into folder - all works and materials noted
cbad7ea7-8555-4ed2-bcac-bf2f08100e10 | checkpoint | change of details and or instructions
e6ce167b-edbb-4d30-845c-624e3a44688e | checkpoint | Site specific details to be added
c046c11a-3cf5-4f66-9454-3c10f8e517d0 | checkpoint | Material Details - Notes to be added of materials used on site
acb38963-5b5f-4e49-8d3f-f099aebce033 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
70cebabf-ae3f-4d17-967e-87a34f289044 | checkpoint | site has been cleaned in advance of our arrival on site
b2f3357c-b887-49be-baef-b3f3c21cb48b | checkpoint | Walls are plumb and level
2bc2d2cb-a4b3-5a7a-8065-4fb1d905fd96 | note | IMPORTANT
93e23fba-3804-401e-ac15-e3ce8085c030 | checkpoint | Tiling works running to programme - prior trades completed
4e87afdb-97fc-422a-843b-96f5559a0e45 | checkpoint | Has prior trades QA been signed off by main contractor
bc44f23d-9844-4a69-9621-59758f46ddd3 | checkpoint | Gib compound and sanding cleaned up from rooms
21497f0e-c7d7-460e-a699-9af3f3b5b1d6 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor
60b8aaef-b78f-485b-a416-a13e7c016537 | checkpoint | Inductions completed
52055152-0001-4d6b-9558-bdfe076b3bfb | checkpoint | Site Inspection checklist has been completed
32cff7db-6367-4b99-bffb-3e7a81166054 | checkpoint | All tools tagged and tested - (photo's required)
3059e8e3-ec74-41a3-a9d2-3c3e0b509ed8 | checkpoint | Tiler has current site safe - Input number and expiry
daf50c86-4962-4676-8c53-e3d5aad83746 | checkpoint | Tiler has correct PPE
4b4f54ed-39e4-4ed5-ba02-6eed516690d8 | checkpoint | Correct drawings supplied as per onsite
f4210d35-3625-44b8-98d2-ad3840c27dd7 | checklist | QA - Tiling Installation |  | QA - Tiling Installation
cf8178fb-9e68-41a1-abb2-aeb87fd2d694 | section | Tiling bathroom floor and walls
1509f2f1-2484-49f6-bd29-e68d02802bbe | checkpoint | Tiles set out according to latest drawing - always check revisions on site
39e9d75a-b70c-4aac-8a9d-4681b42ee62a | checkpoint | Specified product used with notched trowel or required product
5aa0e61e-d735-4aab-bfd3-a1a50683dc88 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
066ffe9c-121b-45a6-8181-164e61c452fb | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
2faf51ef-839f-4a50-81c3-e8b34c4c8179 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings
2317619f-c53c-464d-bcec-fdfe11757d90 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly (epoxy grout)
29922865-f255-4a0c-b23d-50fb285a7475 | checkpoint | Grout is consistent throughout and no missing grout.
00ac614c-f844-412b-90de-06f9e857e73d | checkpoint | Tiling completed, checked and Supervisor sign off
05860be1-b274-4cb8-aa3a-51390cc3a21f | checkpoint | Silicone is completed to all tile junctions where required
663e1ab6-88e7-463a-a1b5-0bf1b8072656 | checkpoint | Area left clean & tidy
e9df35ad-5113-4c43-a5b5-8ee39a85db31 | checkpoint | Builders clean completed
dc0a04f3-613c-430b-b4b7-37ee7856fc01 | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1b4c238a-60d5-4195-8b89-7443caa6aa18 | checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
4632d231-c712-48b3-83b5-cbe6a5d952cf | checkpoint | Waterproofing coat # 1 applied to floors and walls (take photos)
4b122c7a-1ff5-4501-8318-489d19404bc2 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
72b53687-8c7f-4693-a8df-8aa774195425 | checkpoint | Flood tests, if required, undertaken and photos provided.