## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
76862b13-87f3-4cb8-ab52-da4396fcb3a4 | checklist | Other Information |  | Other Information
ea27ab43-18af-457f-a4d9-48bd347ce866 | section | Other Information
86a35c9c-66a7-4d3d-904f-ebf95114cc55 | checkpoint | Variations or extra works added into folder - all works and materials noted
31bcbac8-2713-430d-8593-0785d524c84a | checkpoint | change of details and or instructions
a857b272-bbc8-422d-9de1-d974b80e066e | checkpoint | Site specific details to be added
681c3dfb-5f0c-4000-80df-0ebca92089bc | checkpoint | Material Details - Notes to be added of materials used on site
7f1fae39-cf0c-43ee-aa7a-fd7f2ba35540 | checkpoint | SSSP/TA forms attached
3a9d1c6f-3d87-48d3-a96c-e14eeb510bad | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9dd22204-647f-4c90-8e6c-1c4e3262f3c1 | checkpoint | site has been cleaned in advance of our arrival on site
cf1f4854-2fc7-4df2-8c19-cf4a0f09ed81 | checkpoint | Walls are plumb and level
c835c5c0-9917-5c7a-b134-7068fb9cd3ba | note | IMPORTANT
d2203a75-afa3-4d4a-a2c6-10656731f420 | checkpoint | Tiling works running to programme - prior trades completed
ce4c52be-b724-478e-87b9-1eb98844b686 | checkpoint | Has prior trades QA been signed off by main contractor
c94dc408-0a6b-4877-b841-e1781d4e9fd6 | checkpoint | Gib compound and sanding cleaned up from rooms
676dbe73-d667-4f0d-b62c-c4ef854b4306 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
b4ce2ed0-5d38-4578-8e2f-441836e1903a | checkpoint | Inductions completed
fa5ebbad-c843-4cb7-a62d-48a310503f47 | checkpoint | Site Inspection checklist has been completed
7998adf7-bfd0-4333-a667-1c81d4436a31 | checkpoint | All tools tagged and tested - (photo's required)
29b96083-79f1-4bb6-8ff6-393b7311798c | checkpoint | Tiler has current site safe - Input number and expiry
5afd6e68-4b80-4c80-bd78-d579188a5afb | checkpoint | Tiler has correct PPE
99096a8a-42d3-4ba0-a916-79e9f9925bb5 | checkpoint | Correct drawings supplied as per onsite
e558e0e3-c081-4262-829f-2ef141638d0a | checklist | QA - Splashback Installation |  | QA - Splashback Installation
d72b9242-50b8-4101-ac60-5e7fabb65ed5 | section | Splashback Installation
223c85b1-e0b8-4ed4-9267-2c0719124700 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
63b1fe22-88bd-4b13-939f-d3526be52f45 | checkpoint | Splashback Tiles set out as per drawings
1f18fc72-59e4-4a42-bf9e-5b26b80d98d6 | checkpoint | Tiles to walls
0f5892c4-afba-4a1f-a326-4d7d7d02b60a | checkpoint | Tiling is completed, checked and supervisor to sign on
390cfdb4-0395-4dfa-bd25-98ddc2b2f76f | checkpoint | silicone nominated is the correct colour and applied evenly and correctly
9b5048ba-e18e-4372-9b75-3e12f6d9bb2e | checkpoint | correct tiles trim is supplied and installed as per drawings
ac7ea699-6921-4c47-b0b7-68f7c960f162 | checkpoint | Area left clean & tidy
1fd04b11-eeb0-4cff-a7e6-b92e4ec624bc | checkpoint | Builders clean completed