## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e41ffa89-cf9b-4220-bfaa-8036386d3915 | checklist | Floor Preparation |  | Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
dd9df747-a200-4624-8bdc-d494d5cecb56 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
68616c49-36a4-406d-beae-41def49900d4 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
2178a68f-dd4f-46a2-87f8-4c4736779010 | checkpoint | Has screeding been completed to shower at correct height and falls - R4 screed
f0ba68c7-13a4-4353-90ab-78533df9ecae | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
074ad3a1-c75d-4a69-9a43-1885af9e4df6 | checkpoint | Grinding completed before works (photo required) after works (photo required)
58b55575-2d72-4b88-b651-05de8742c00b | checkpoint | Floor levelling completed - hours and bags used to be recorded
a7305129-a6fe-4480-85d9-fd2612dbd6a0 | checklist | Other Information |  | Other Information
b524a1a3-f73f-43c5-893b-54aa403df893 | section | Other Information
482f5942-82a4-4597-919e-17bdbdc3f87f | checkpoint | Variations or extra works added into folder - all works and materials noted
3b0ca09d-ba74-4aaa-b947-e59bc642170e | checkpoint | change of details and or instructions
407fe6a6-ae02-4762-a559-b529de0e1f07 | checkpoint | Site specific details to be added
241ae804-f66f-484b-ab93-03eb7e999974 | checkpoint | Material Details - Notes to be added of materials used on site
4da7c1ea-812e-4b88-a56a-8c09b211388f | checkpoint | SSSP/TA forms attached
73d1aa54-4c6d-4593-94a1-5a9eeafb6c04 | checkpoint | Dayworks sheets attached
36432ba5-afc9-4666-9675-66487610c0f5 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7ad4005e-2620-4daa-8a7a-ff0181716462 | checkpoint | site has been cleaned in advance of our arrival on site
906ea5d1-bcef-422e-950f-c7f579916611 | checkpoint | Walls are plumb and level
1a9cc416-4405-5638-89cf-38faa9da5491 | note | IMPORTANT
76835bde-8e75-4be5-b249-a84f70bfcd00 | checkpoint | Tiling works running to programme - prior trades completed
608127cc-eb63-49ff-9b98-da0b56d9d721 | checkpoint | Has prior trades QA been signed off by main contractor
7aa196fb-3de3-4411-a708-69967f6b9225 | checkpoint | Gib compound and sanding cleaned up from rooms
0b590070-3c09-4486-9a75-4afd955baad8 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
4b54f1a6-728c-4077-94e3-103bc4ef2308 | checkpoint | Inductions completed
83daee13-8656-4045-b15b-86c69195f19c | checkpoint | Site Inspection checklist has been completed
604c1f4d-0976-4320-ad42-bdeaf448bbf2 | checkpoint | All tools tagged and tested - (photo's required)
a32ff8ba-a86e-4a09-8eea-4b38eb0d951c | checkpoint | Tiler has current site safe - Input number and expiry
5969484b-39c2-400b-8542-fdbaadfcfed1 | checkpoint | Tiler has correct PPE
e3c51bf8-7f4a-4696-b395-0a3f253e7b6e | checkpoint | Correct drawings supplied as per onsite
9ed1e2dc-0452-490a-ab7c-e662f4a88d7c | checklist | QA - Tiling Installation |  | QA - Tiling Installation
8d4e59e9-12d2-43b9-ab23-d234d6a51a03 | section | Tiling to floor 600x600 tiles to floor in checker board pattern including perimeter and cutting into walls
a71651a6-9353-4ae7-9089-3e18f47fd521 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
68d62153-d7ee-452d-8d28-ddaac29748b0 | checkpoint | Specified product used with notched trowel or required product
b40bf674-eeca-4969-8e3d-6b04dd171496 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
d7414517-31b2-4aa2-a80e-a1be067828db | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
0c2a492d-6fc1-4a20-95a7-e762404de677 | checkpoint | Grout is consistent throughout and no missing grout.
4daebb6a-3ab5-41ec-a71e-bc84642c9dca | checkpoint | Install trim at doorway thresholds
801e5d44-3b78-43a4-954f-7a74b0c27600 | checkpoint | install Latham Strip control joints as per note on page F.05
a037cd8c-5a25-46f4-a5ff-3e619711d3da | checkpoint | Tiling completed, checked and Supervisor sign off
ef9c6253-b0da-432c-98c3-6369406fb09b | checkpoint | Silicone is completed to all tile junctions where required
ae1d0e52-9dfd-475f-ab7c-44d8fd2b9eb3 | checkpoint | Area left clean & tidy
58e9c407-8f09-4b0d-ad5f-f92ef28eb732 | checkpoint | Builders clean completed