## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
86bf112c-b938-448b-a27e-acf1e8df3938 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
53315d92-321d-4c5b-8ab7-6a57cf7d7511 | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
e4a15d0b-9f18-4492-9192-9860d97dd880 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
383424f6-a30e-4108-88e9-a32f1ddc0c5b | checkpoint | site has been cleaned in advance of our arrival on site
24d69bc8-6ea4-4459-9a89-250474a71148 | checkpoint | Walls are plumb and level
79380c51-fccc-550b-848f-9f35aeb05e47 | note | IMPORTANT
4adf0bb0-4593-4c81-8d2a-739bd6d7140c | checkpoint | Tiling works running to programme - prior trades completed
69d380b6-8f29-4788-a9ab-af0343e145f2 | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
596a1616-f968-4918-9598-3438813c27e9 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
5092d91f-218e-4a59-9c59-98ab3034bf5d | checkpoint | Data sheets, of products, are supplied on site with TA's
306ce544-3f53-4747-b680-644e0c07ae41 | checkpoint | Inductions completed & Site Inspection checklist has been completed
c7cf6f96-41cf-4102-ac20-9cd8f34541bd | checkpoint | All tools tagged and tested - (photo's required)
e446c0ff-9570-4cfe-8dcd-a8e3526f7281 | checkpoint | Tiler has current site safe - Input number and expiry
ab72c864-8cd4-4dbc-bd0a-6a3649f66cee | checkpoint | Tiler has correct PPE relevant to project.
33a45280-6b8f-475c-b649-714ee3dd9169 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
4d9adaca-8ec4-428c-9906-4ed11213782b | checklist | QA - Splashback Installation |  | QA - Splashback Installation
fb4ce94f-b600-45af-a516-99eae8c242c7 | section | Splashback Installation
17379c15-6c59-4805-ad40-6b546ee12787 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
5b4701e1-eb22-4114-9b1c-0af0ac3d4769 | checkpoint | Installation of tiles to splashback and as per drawings
7b255b20-5c61-4a5e-8261-ca1719a0efdd | checkpoint | Grouting is consistent, neat and cleaned from surface.
733519ff-9aee-4380-b239-19f9d216b487 | checkpoint | Tiling is completed, checked and supervisor to sign on
34e15adc-88ed-47c5-94d5-a813ffa9d2aa | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
4c42eb1f-cf81-4327-a5d9-2a39c27b458f | checkpoint | Correct tiles trim is supplied and installed as per drawings
4ca1fe08-deed-4235-9cda-a9dba85ee19f | checkpoint | Area left clean & tidy
f37a5d69-8dc0-433d-b826-dc79bf130474 | checkpoint | Builders clean completed
7e8f3bba-7fa7-450d-9f7f-c275bfcc13f6 | checklist | QA-Other Information |  | QA-Other Information
0bbbdb75-245b-4ffb-9df0-d832db033725 | section | Other Information
147dead6-f0af-4e79-bd34-7959ef4cc518 | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
99559178-a0fc-4f9e-b24a-3223e4e99dc2 | checkpoint | change of details and or instructions
61b16d55-de76-475c-9ed3-6f75d1e46fe6 | checkpoint | Site specific details to be added
4a85c402-8409-4ea7-ae39-b90e020bf61c | checkpoint | Material Details - Notes to be added of materials used on site