## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
1d9af602-2b46-40cf-bce0-9ad2b8212590 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ba6f401c-1f20-4fb9-a66f-e8a3b1b3b604 | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
442d5d99-9a4b-4d99-ae02-0d3a6ad234c2 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c9c1fda3-3ead-4164-a4b1-c9212f0f2be1 | checkpoint | site has been cleaned in advance of our arrival on site
4d58325a-7b00-4f15-ae8b-9f21e857c856 | checkpoint | Walls are plumb and level
356241c2-f859-525a-8bbf-2029fa7b902b | note | IMPORTANT
0abd8a74-cb23-4349-bd98-f6a7f6fbbd45 | checkpoint | Tiling works running to programme - prior trades completed
8e892fac-b16b-42ac-9485-4ac5a4617b98 | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
f2ce0406-b431-42d0-9eeb-f2f9d4acdfc4 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
b31c46e0-3c5b-4e64-800a-88328bcf1722 | checkpoint | Data sheets, of products, are supplied on site with TA's
95054938-7910-4d95-9092-3ddbf958e2c7 | checkpoint | Inductions completed & Site Inspection checklist has been completed
7be6ec29-ef82-40e4-972e-b97fb37a29d4 | checkpoint | All tools tagged and tested - (photo's required)
8d53c10b-1dad-46b8-b0fe-4cb0582b049e | checkpoint | Tiler has current site safe - Input number and expiry
b687528c-e4d5-424d-ab0a-e52fb2c60eb1 | checkpoint | Tiler has correct PPE relevant to project.
5481ee92-68d3-4af3-a09b-5716206a3018 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
daa79a94-0a16-48b1-82a9-3d41967ee443 | checklist | QA - Tiling Installation |  | QA - Tiling Installation
2d2ec2cb-4285-4973-a00b-598aca76e087 | section | Tiling to floors and walls
dc28298d-89c0-4803-bbf2-3d85508bc9b1 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
268e7bdd-1034-4400-9d4b-269e45783137 | checkpoint | Specified product used with notched trowel or required product
159da8c5-784a-4f7d-940b-2f42254029ff | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
bc1ae9a5-c06a-4d3f-b19f-5cfb044ddb0b | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
2e6dfcd8-fbe5-47ea-a2c7-dafb0162ba42 | checkpoint | Install TL1 to main shop floor as per drawings
bb25633f-d873-47a7-bbcd-7fb68b7728ed | checkpoint | Install TL3 tiles to floor as per drawings
ec9762d7-bc33-4a28-bbde-9a1797a88fb2 | checkpoint | Install WD3 tiles to changing room floor and shop front entrance floor
ac2c681a-6c0b-4bc7-b5e3-cb3a93b469e3 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
67b4dcd3-c4fd-464f-b614-cfa28c9fd31b | checkpoint | Mitre all tile corners on walls as per detail 3 - A204
e2dd65ab-3b87-4574-a699-4a94a7fee282 | checkpoint | Install TL2 tiles to shopfront walls and cabinet unit
6c037bd5-71a9-48a6-81cc-b1ddefd85f45 | checkpoint | Install TL3 tile to shopfront walls and interior walls as per drawings
23c6f61e-2319-4f16-aefb-b356373f36dc | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
4ca3f26d-2ec9-45a9-a5d1-e8ffbd0dfe70 | checkpoint | Grout is consistent throughout and no missing grout.
ebae81a4-8430-4b1c-a3f3-76e40e038e4e | checkpoint | Tiling completed, checked and Supervisor sign off
646a6f9b-ae8d-40c3-a3a9-98b2ca1d265f | checkpoint | Apply silicone to tile/tile junctions and floor movement joints
88ab1920-5d52-4acf-8fc5-376d57aa2c65 | checkpoint | Apply sealer to all TL3 travertine stone
0d4ca158-7a54-4452-8eff-8c258167d07d | checkpoint | Area left clean & tidy
db576079-9a1b-4b5a-8760-456b0ac16f7b | checkpoint | Builders clean completed
c4f6fe80-3f96-497c-9e3a-7c5a757e8564 | checklist | QA-Other Information |  | QA-Other Information
ff3e6647-e68a-4316-9201-d0f1eb07b25e | section | Other Information
bc5e1e2f-b04a-40af-a6b5-2cd6535def1c | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
d771ed2c-e154-4137-949f-41095989aec1 | checkpoint | change of details and or instructions
71cc6718-9dde-49b1-9ebe-a61dc7538773 | checkpoint | Site specific details to be added
0bb5e4c2-3be7-4d51-ba43-e01a9b7295fc | checkpoint | Material Details - Notes to be added of materials used on site
1fe26a01-4f81-47bb-aeb9-1d121248acd2 | checklist | Wall/Floor Preparation |  | Wall/Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f02e6e16-743a-469c-8e7b-bf9b8ad75402 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
87f1f551-69a1-4069-96a4-3588932d59b9 | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
2cb5289c-187b-42ed-b84e-fbe8f8aa9f9e | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
86f6e157-b84d-4238-b41c-5e347249ea08 | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
a897a2c7-b40c-4587-ad46-947285aff0a8 | checkpoint | Ramping to WD3 to entry