## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
51872c6d-9068-4d42-bc86-4094e7f97f18 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
037c2d18-843e-4114-902d-9f7d19f5a9af | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
78253173-a3b2-4692-b04c-199c24b4d66b | checklist | Floor/Wall Preparation |  | Floor/Wall Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7ae501f6-a2c4-47e5-b59d-33bd714993f8 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
59e4fe2a-28fa-4a8a-b184-0183fdde3d5f | checkpoint | Has screeding been completed to shower at correct height and falls with correct product
0a9b4703-46fb-4da6-8f33-1ee1dff22e41 | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
5421c5eb-9aad-42e5-972d-e7659813f1d0 | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
651d0434-52b3-48e0-975d-60249681d4d3 | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
9f300834-7f48-4a87-9374-a9e2cdfd1a0c | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
57b23b8c-58dd-49d4-80bb-681b8cfe95b2 | checkpoint | site has been cleaned in advance of our arrival on site
e585e236-1361-45a4-b21c-172e62d1bb59 | checkpoint | Walls are plumb and level
ce0c9081-25c1-5049-b7d9-c33b9fea1813 | note | IMPORTANT
0755adc1-b8b8-4f53-8970-41bf8e069807 | checkpoint | Tiling works running to programme - prior trades completed
df986b85-0f99-40aa-99ca-38c9bc9ef1eb | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
e018f13d-fb8d-4b2e-873e-d7b8a40aed6c | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
56f128c4-e215-4857-80d2-536ec3257c30 | checkpoint | Data sheets, of products, are supplied on site with TA's
bf3c204e-994a-413d-bf34-78c227964406 | checkpoint | Inductions completed & Site Inspection checklist has been completed
40ef7b53-18f0-4ded-afe4-c5b48695c808 | checkpoint | All tools tagged and tested - (photo's required)
3a8d3ef0-4d12-459d-880c-edbe10fe8654 | checkpoint | Tiler has current site safe - Input number and expiry
842019f3-d500-4db5-8af7-d1f9c5baf980 | checkpoint | Tiler has correct PPE relevant to project.
9565140d-0d72-4318-85c4-0192caed8e66 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
c6b60197-e780-4ff4-829f-daa12872a7e7 | checklist | QA - Waterproofing to floors and walls |  | QA - Waterproofing to floors and walls
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
81c8408c-ce82-4a89-b08c-2c09f05db77f | checkpoint | Substrate to receive waterproofing has slimline installed to any corners and has been gib stopped
4011e04f-5030-4506-99e2-595fe8edeb0d | checkpoint | Correct waterproofing is supplied as per project specification.
4e9c0e70-0176-4a2a-a90f-5645c480b9c0 | checkpoint | Waterproofing coat # 1 applied to floors, upstand and walls (take photos) - Ardex
78fbc402-8d65-4413-bca4-a18033b13969 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos) - Ardex
3dcc4fe8-1497-4575-8165-35140cb6592a | checkpoint | Flood tests, if required, undertaken and photos provided.
ceecb0b3-a8ab-460e-a8b1-e8daac0aff33 | checklist | QA- Tiling Installation - Floors |  | QA- Tiling Installation - Floors
edfa829e-b09f-4910-9e03-546182d8565d | section | Tiling to floors
e3cc3979-5046-438e-a7e1-5538b3835567 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
e4c723ae-64a0-47b6-bb83-e576f4a5e45a | checkpoint | Specified product used with notched trowel or required product
d426e8ad-c877-44d5-add8-bf3bff11dbd3 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
dd13b14b-f413-4784-b4c0-e54710d4468d | checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
fa618c0a-a6cb-469a-8a0e-05ff54e3cd90 | checkpoint | Fix tiles to floors as per drawings
d8532e86-9641-4dce-b7bc-47679e21fc3d | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
a39ea73b-a24b-4a1d-bfee-350ba901477e | checkpoint | Grout is consistent throughout and no missing grout.
b73fc1ae-41ff-4edf-a6d6-2f6f51e47229 | checkpoint | Tiling completed, checked and Supervisor sign off
caf76f69-e188-4ae7-bb70-7563e4e5fb87 | checkpoint | Silicone is completed to all tile junctions where required
29271832-9c54-4b13-ba8f-6b4c42a66adb | checkpoint | Area left clean & tidy
33a86189-b51a-4149-a735-b29462c78a6a | checkpoint | Builders clean completed
3d3c568b-e673-4934-b4a0-8c6760c5cc71 | checklist | QA- Tiling Installation - Walls |  | QA- Tiling Installation - Walls
71d4f2dc-0361-4fa7-bc76-ba2d94a7898c | section | Tiling to walls
60fddcab-71c8-42f3-afa9-4e455acd983d | checkpoint | Tiles set out according to latest drawing - always check revisions on site
4a4478e5-86e1-4bee-901c-f0b098788386 | checkpoint | Specified product used with notched trowel or required product
a3c21b00-0844-4299-9af9-ec6e5d00a946 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
f86d3718-1069-49e7-8228-49dbe0cca494 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
9684fae5-b037-4277-99ea-f53439a4b283 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
d9593b66-e6b1-4484-a006-60134ff0febe | checkpoint | 600 x 300 volare Enzo Moon Feature Walls
44cf1be6-efce-4609-98a5-5ce2c0a0a34b | checkpoint | 600x300 White Porcelain Main Tile to walls
6163ae20-789e-452a-a77a-8701abf90b7c | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
13adcf01-0327-40bf-a76b-6d2866536e49 | checkpoint | Grout is consistent throughout and no missing grout.
967a8814-6823-4580-a06d-6833bf3209cd | checkpoint | Tiling completed, checked and Supervisor sign off
a4979deb-b85f-4812-935c-17a08583ef9f | checkpoint | Silicone is completed to all tile junctions where required
696ca2a3-b4e8-40a9-8143-306057d46abb | checkpoint | Area left clean & tidy
eae49a68-8c73-494d-86e4-1246ffbcfa1e | checkpoint | Builders clean completed
7e640062-24da-4760-9801-59a5d1beb811 | checklist | QA-Other Information |  | QA-Other Information
aadb4f0b-6bde-44e7-b826-1b558fe922db | section | Other Information
68ba835a-91cd-476b-aba7-10bb07ee187f | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
0144cada-ffd5-43ce-aa31-43b54ad52753 | checkpoint | change of details and or instructions
94bcbeb7-f463-4fd5-b1ea-e28411fdd925 | checkpoint | Site specific details to be added
58d5e21f-fa43-4fe3-b453-5a90ba9a980d | checkpoint | Material Details - Notes to be added of materials used on site