## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f63a4548-6820-4f09-bf9a-2d9261fc3124 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
abc2fe36-dcfd-4267-9516-518a37807fd1 | checkpoint | site has been cleaned in advance of our arrival on site
547c64a9-21fc-4684-b8ec-8e1fea078e43 | checkpoint | Walls are plumb and level
da79590d-d096-554d-a39f-8899aea74203 | note | IMPORTANT
daa6f57b-55a4-44d4-b603-cd33922c626b | checkpoint | Tiling works running to programme - prior trades completed
2c26c207-3e78-44af-bc12-5be24affc39c | checkpoint | Has prior trades QA been signed off by main contractor
5484cd39-30c3-4181-82d7-f2448896039e | checkpoint | Gib compound and sanding cleaned up from rooms
f52d5717-ab3e-4df1-b6cb-dc91a166a0dc | checkpoint | Task Analysis signed onto by tilers and provided to main contractor
a5be51e8-9f93-4f95-81a2-64ca31027667 | checkpoint | Inductions completed
8a242b32-1796-4182-84e6-9eccd8a41b88 | checkpoint | All tools checked for tagged and testing (photos required)
856b631e-85b9-43e5-b435-ddafc2889821 | checkpoint | Site Inspection checklist has been completed
6a023fac-939d-4945-aaee-a72619902995 | checklist | QA - Acoustics and waterproofing |  | QA - Acoustics and waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
28f892e6-6922-4a94-9d8a-dd02a459a7f5 | checkpoint | Floor is primed prior to installation of acoustics
21a055e1-8ec2-40b5-a3fc-65ee946d7a15 | checkpoint | Waterproofing bandage applied to floor perimeter and gaskets to flanges
9af31ea3-3984-4f1c-b929-cf50a578fa17 | checkpoint | Waterproofing applied to floors and walls (take photos)
49959c3c-c89f-415e-82e8-2c731b814fda | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
55c9565f-f144-4049-a977-aa1df1646641 | checkpoint | Flood tests, if required, undertaken and photos provided.
edc7f4c7-f1a2-4bba-bdde-341b5bcd17c0 | checklist | QA - Floor Prep Bathrooms |  | QA - Floor Prep Bathrooms
62ca25ed-4301-4997-b7e9-c194fcd98b79 | section | Floor Preparation
3bad20be-e7ff-4774-94b0-c1ce5dfdcac7 | checkpoint | Is the area clean, and cleared, ready for necesssary preparation
f409a0e4-74cc-4873-be88-557680386fbc | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
a19d441f-8606-4336-bdd7-8a09c573c65c | checkpoint | Has screeding been completed to shower at correct height and falls - R4 screed
15fc5ed7-23c6-4380-9cda-6389f9adc7b0 | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
ae0d76c5-0a1c-4ada-8466-e389d93cc05b | checklist | QA - Tiling Installation |  | QA - Tiling Installation
0c251341-d0b8-483b-837e-5d79812130d2 | section | Tiling bathroom floor and walls
11154cc8-88ef-48f5-8ae3-dee77b5ad604 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
195c450f-7ec5-42c9-ac5a-30f08f7938d9 | checkpoint | Specified product used with notched trowel or required product
a6bd1c16-32de-48da-9ead-77f691277556 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
e5b27591-d198-425a-ae53-b97b31b9ac52 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
ab9dad89-6751-4ee1-8690-820bde829a5a | checkpoint | Wall tiles set out to match floor grout lines or as per drawings
a56256b7-61f3-4fb0-b67b-c78eec129bcd | checkpoint | Grout nominated is the correct colour and applied evenly and correctly (Epoxy or cementitious)
bab83db6-e72e-4e3b-a3f0-9d018b28c400 | checkpoint | Grout is consistent throughout and no missing grout.
42ef0023-236f-417f-96f5-13393bcb0e85 | checkpoint | Tiling completed, checked and Supervisor sign off
7fd0a1fd-9e30-40d9-9f70-ac8c075a451f | checkpoint | Silicone is completed to all tile junctions where required
ccf75643-fb3c-48bd-9e08-e42b3054dd53 | checkpoint | Area left clean & tidy