## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
881fb6c0-593d-4fcb-942a-928adc8eddd2 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
5245c4f4-ab68-47a9-bf8b-451af5088908 | checkpoint | site has been cleaned in advance of our arrival on site
a79180a9-cdda-4566-8f7f-79cf7beb1008 | checkpoint | Walls are plumb and level
66ca631b-e455-536b-9b29-16c4153064eb | note | IMPORTANT
a3c67f4b-3a5a-40c9-885f-644f5f94c970 | checkpoint | Tiling works running to programme - prior trades completed
8dd655de-af56-4876-b6e4-d72b062daf8f | checkpoint | Has prior trades QA been signed off by main contractor
ac993761-afd9-4d92-9c3a-8891f28ac4fd | checkpoint | Gib compound and sanding cleaned up from rooms
357ced1d-c118-4beb-b86f-5d563c9807e1 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor
e4393a1d-3758-4390-bb24-5156f0299d96 | checkpoint | Inductions completed
1f67b2bb-fc34-43ca-a20b-920f4e7e0660 | checkpoint | Site Inspection checklist has been completed
b7312a9a-2658-4351-a90d-377d5a041ee7 | checkpoint | All tools tagged and tested - (photos required)
e966b14f-1ca3-43e8-bef9-4035b3ca92fb | checkpoint | Tiler has current sitesafe - Input number and expiry
25982db1-1624-4d6c-bc08-3280638fbf59 | checkpoint | Tiler has correct PPE
11c264b8-803c-4d50-8996-37200cb0eefe | checkpoint | Correct drawings supplied as per onsite
712b2f3f-cf2b-4af3-996d-8e1ef2083421 | checklist | QA - Tiling Installation Bathroom |  | QA - Tiling Installation Bathroom
1a8538c9-62ce-4e54-b7c5-5be3bd786451 | section | Tiling to Bathroom floor, Wall, Skirting tile
d2619ff7-e294-4679-ad32-4594be5437b6 | checkpoint | floors and walls are primed prior to tiling works
6511501f-2bb7-4531-9ab1-4e31760cf17f | checkpoint | Tiles set out according to latest drawing - always check revisions on site
258b2687-9b12-4a92-be32-6daaebf3da24 | checkpoint | Specified product used with notched trowel or required product
e74afbfa-2951-4796-94a8-930f5c502900 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
0395436b-bedb-4536-b673-ac7dae1fa6d4 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
6ebb52d9-2d0c-4b6b-b633-7ced236c4be5 | checkpoint | Tiling to floors
0098d957-786d-4870-af77-61ee38ad68d8 | checkpoint | Tiling to wall (full height as per markup)
b0c27a66-09a1-4e9f-9e26-93ce83d89a64 | checkpoint | skirting tiles (on remaining non-tiled walls) set out to match floor grout lines or as per drawings
0ea304be-ca3e-4d14-835f-2a576a56b56e | checkpoint | Epoxy Grout nominated is the correct colour and applied evenly and correctly
d98b8163-0bf5-4e95-a5f0-ff1c099515d9 | checkpoint | Grout is consistent throughout and no missing grout.
f9bcf9bb-1930-47ee-98d9-5b8c2dc75393 | checkpoint | silicone is completed to all tile junctions where required
998ff9c7-9493-4112-8695-5869dce4b26c | checkpoint | Correct tile trim supplied and installed where required
f1710e48-7e51-43f7-a2c8-3b1d7ea6b143 | checkpoint | Site is left clean and tidy
d9c2ee1d-fa05-400c-b7e7-205509d91bd7 | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
fe176906-3b82-4d89-948e-d9dbb4d506cd | checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
f3b47cc4-f54b-44c4-8b55-9da018ef5453 | checkpoint | Waterproofing coat # 1 applied to floors and required areas (take photos)
4e7d45fd-bbb7-49c0-9ffc-458654e70816 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
f7be90c3-fc43-4531-879c-a2de234c7ea9 | checkpoint | Flood tests, if required, undertaken and photos provided.