## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
c0cf3a04-9013-4801-9ba3-712860125dfc | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
2c760647-3aa2-4b60-8eb2-0095699416a6 | checkpoint | site has been cleaned in advance of our arrival on site
54e57b6f-f631-42bb-97a9-e7b6faf68138 | checkpoint | Walls are plumb and level
b1b63853-e816-5ede-8460-1f0a25e855f3 | note | IMPORTANT
8ab6d66e-b968-42e3-a30b-d8f8df3fec45 | checkpoint | Tiling works running to programme - prior trades completed
d42d4600-f325-4579-a59c-049649f4e75e | checkpoint | Has prior trades QA been signed off by main contractor
3f375256-04e3-47ba-8391-11b1a8e686ef | checkpoint | Gib compound and sanding cleaned up from rooms
2a3cf813-ef07-4b11-8fcf-8bdac4a0af09 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor
9b1bd9c2-4b35-43cb-b06e-0aa98e1d3c3d | checkpoint | Inductions completed
9f71ae5c-8648-4c22-8a17-4bacd37bc299 | checkpoint | Site Inspection checklist has been completed
0fbab74d-f3d3-4f4b-8ef6-95ddfd4ac89d | checkpoint | All tools tagged and tested - (photo's required)
0811e8ec-be9c-4780-9ffb-1a6a54e898c7 | checkpoint | Dust control tent has been set up and tested
19b46187-5b93-4738-a2af-44ca777e47ec | checklist | QA - Floor Prep Bathrooms |  | QA - Floor Prep Bathrooms
1f6a216a-5ed3-4c31-9bc6-2cf78e139b19 | section | Floor Preparation
18a8255f-ebf5-4a3c-8380-00cf87cbd333 | checkpoint | Is the area clean, and cleared, ready for necesssary preparation
ad6d83cd-e26a-428e-a279-5a56c7201b5c | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
1d993855-fcc6-4d06-b185-0b38101f168d | checkpoint | Has screeding been completed to shower at correct height and falls - R4 screed
b9d004e7-3d01-4422-909b-24bc3069b671 | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
9f1365a8-162d-4c28-8270-e9465df0bf9c | checklist | QA - Floor/wall Prep Bathrooms |  | QA - Floor/wall Prep Bathrooms
6ed63647-4f90-41df-b042-ffb2e9d5c455 | section | Floor/Wall Preparation
c19778e6-8bbc-4016-958b-9ea54b3a7931 | checkpoint | Is the area clean, and cleared, ready for necesssary preparation
0f972714-469f-49bc-a2e2-53137a9a7ee2 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
86e7357b-d594-4da8-9dc9-e50e7212ce0f | checkpoint | Has screeding been completed to shower at correct height and falls - if required
672dc67b-c137-4b91-83a3-0316fb217b5c | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
7b38a8e3-303e-4d59-a4c6-1562c8beca4c | checkpoint | Grinding completed, and signed off by Slava, to areas as per markup
c7f4d002-c57c-448e-8832-e74a56317f35 | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
746874ac-31fe-43a4-ac41-e70cce417c41 | checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
14a539b6-c169-4080-b862-9fde1d53c329 | checkpoint | Waterproofing coat # 1 applied to floors and walls (take photos)
6b617c07-d898-4c90-a827-595d8a76daee | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
98c9351a-cb16-404c-a460-71a1aca50c91 | checkpoint | Flood tests, if required, undertaken and photos provided within conqa
bd90994e-3ca5-4336-939f-0f47ed106967 | checklist | QA Tiling Installation |  | QA Tiling Installation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a6477486-49ee-42bd-82cd-ef145025c9d7 | checkpoint | Floor Tiles set out according to latest drawing - PROCURE drawings required
0ba4014e-e9f1-4988-885f-9047759642c8 | checkpoint | Wall tiles set our according to latest drawing - PROCURE drawings required
d5d6c075-b68c-4712-868d-c679fd0d3fa1 | checkpoint | Specified product used with notched trowel or required product
46ccc35b-5ceb-4459-8845-ab7620f582f3 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
cae5cae3-d9af-4105-adc1-9ccf25280760 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
02fb9968-3f0b-455f-b32d-774c9e038971 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings
61a6670e-3c8d-4511-a083-0805a784d1ea | checkpoint | Tiles to shower niche are tidy including trim installation
aa2eeca5-40e3-4c94-8dcb-e37fc7b6373a | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
a4f92e01-62b0-4818-ab83-021e0b442564 | checkpoint | Grout is consistent throughout and no missing grout.
36269f65-1dee-4310-88da-f14639b7c0b3 | checkpoint | Tiling completed, checked and Supervisor sign off
60aa6cee-e85a-40e5-aa6d-98dfb6043adc | checkpoint | Silicone is completed to all tile junctions where required
7c38857e-628c-469e-bafb-6cc8e03748ff | checkpoint | After grouting, a final clean to remove all grout haze to floors & walls in completed by TAL Tiling
e31a0d12-431a-4a36-9e4e-7cbb7ad32420 | checkpoint | Area left clean & Tidy by TAL Tiling
b5816829-4268-4c9b-b31d-1bf138248d6e | checkpoint | Builders clean completed
21de7bc5-7c7f-41f9-8970-bd2ae8d82789 | checklist | Tile Supply |  | Tile Supply
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1a5f85d5-e854-4a55-9172-7d9c9ec2c18f | checkpoint | Tile photos on arrival to site (before unloading)
110a530c-9192-46a2-9913-26e56aa888bd | checkpoint | Tile photos inside site once loaded into site
ff3fa0ca-70c2-449f-8f40-b170b8310184 | checkpoint | Input numbers of pallets total upon delivery - Grey Matt Impact 300x500
1c062d3e-1d49-415b-8e30-39fe568a4c68 | checkpoint | Input numbers of pallets total upon delivery - Scripter Rebel 300x600
5f6436e9-5b6c-45f6-ae9f-08973f7e811b | checkpoint | Input numbers of pallets total upon delivery - Willow Waters Mosaics
4431e698-b66b-4f6f-a52b-ef69673cfee4 | checkpoint | Imput numbers of pallets total upon delivery - Wooden Grey Hexagon