## Master List Templates
Id | Type | Name | Values | Prompting Name
babd3f93-cbf9-435e-92ef-5b3ea971e164 | checklist | QA - Floor Prep |  | QA - Floor Prep
3619af8f-edc7-4bd1-8a59-ed389d6199e9 | section | Floor Preparation
2ecdf421-b531-4687-b0ad-dadfbac1b1e1 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
54bd46d0-a73a-4fc5-a959-cae704d0f6bc | checkpoint | Uplift carpet tiles
781d95fd-8d83-4faf-9848-89b5e41e1a3f | checkpoint | Floor preparation prior to tiling works completed
772c243e-b7eb-40ef-a6af-cfe7ff004fc0 | checkpoint | Grinding completed before works (photo required) after works (photo required)
04b99b35-b982-4bec-9269-2966cd4acdf0 | checkpoint | Floor levelling completed - hours and bags used to be recorded
41b7787c-22e6-4a86-b507-8d1f5c6111b4 | checklist | QA - Other Information |  | QA - Other Information
5d463afb-a401-4a59-a03a-84086639cdad | section | Other Information
e9d0c639-a1dc-4049-b766-aee560118102 | checkpoint | Variations and other works added into folder
80aadb27-d72a-4c98-ae55-6df420270b26 | checkpoint | Change of details or instructions
4214602c-bd33-47a9-8a77-d602910ecccd | checkpoint | Day works sheet extras
a8b9140e-8f40-4407-a47b-39dbe8a31146 | checkpoint | Snag and defects list
06aa8464-20ec-444d-b7cd-d5230c21d3ed | checkpoint | Materials storage ideas
741853ac-69df-40c6-a1c7-f5193f56f4e5 | checkpoint | Site specific details to be added
84a12dfe-747d-4610-a43c-c0cea6b60d87 | checkpoint | Materials Details - Notes of all materials used on site
11bb8521-aeb8-46e0-8c74-144e1bdae140 | checklist | Ω (DEPRECATED) QA - Other Information (v0) |  | QA - Other Information
5d463afb-a401-4a59-a03a-84086639cdad | section | Other Information
e9d0c639-a1dc-4049-b766-aee560118102 | checkpoint | Variations or extra works added into folder - all works and materials noted
80aadb27-d72a-4c98-ae55-6df420270b26 | checkpoint | change of details and or instructions
741853ac-69df-40c6-a1c7-f5193f56f4e5 | checkpoint | Site specific details to be added
84a12dfe-747d-4610-a43c-c0cea6b60d87 | checkpoint | Material Details - Notes to be added of materials used on site

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
84e58c39-8b2b-4f00-b3f8-a54b848ed5df | checklist | Prestart Inspections |  | Prestart Inspections
a44901e3-a5e2-4146-a0cc-38f851c59431 | section | Prestart
7d9fae32-f5a3-4409-a293-9bb6554156fd | checkpoint | Site has been cleaned in advance of our arrival on site
69cb457d-f22e-451f-a3ad-e591360befd9 | checkpoint | Walls are plumb and level
83005b40-7559-5de8-96f1-ed9c9ee94f78 | note | IMPORTANT
0ec20cb2-04ed-4e39-8bd1-7e352cad0c81 | checkpoint | Tiling works running to programme - prior trades completed
074b22cd-99f9-4343-ad5d-27f647c0b9fd | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
a9989637-6f2a-480a-8740-2111048d53ce | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
6eebad36-ca16-4d1e-988c-13def46108ba | checkpoint | Data sheets, of products, are supplied on site with TA's
81c2ce0e-580e-457c-a4ad-c5994d675e4b | checkpoint | Inductions completed & Site Inspection checklist has been completed
6feebf5c-ffa8-4a2b-bcc6-221312c9adef | checkpoint | All tools tagged and tested - (photo's required)
1ab9e3f1-a220-49f6-a035-aaf342609627 | checkpoint | Tiler has current site safe - Input number and expiry
fbd9b628-58fe-4aea-ac0c-8fdfe6d99315 | checkpoint | Tiler has correct PPE relevant to project.
02f9b2b1-4576-44a6-b8a5-1fab03300be1 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
c0bf24be-3a90-47fc-a7de-f9684bd6075f | checklist | QA - Final |  | Final Sign Off for Invoicing
73e5ef41-dc95-4e49-a8cc-b96d12e21ead | section | Details
c68049a9-d944-4aa8-b7bf-667ce4d7983f | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
928d37de-7ce8-4a2a-a3d6-4ac65330c5ca | checklist | QA - Tiling Installation L28 |  | Tiling Installation
f3e4f5aa-67b0-4dce-aa17-ca335e115eca | section | Tiling to floors and walls
19e537c1-3a88-4493-8cc8-5f03e2d8c573 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
cc28bc18-b733-4af1-a931-4ac4ade0f229 | checkpoint | Specified product used with notched trowel or required product
1879f26f-7c59-4036-80fa-52ea963ad713 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
f1d3c500-bc45-4225-82af-a18fb6103b61 | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
eedeabd2-210b-4a25-8b8d-e83aa6463ebc | checkpoint | Install tiles to floors as per drawings to amenity floors
562bc4ab-f626-400f-ab90-412b3910ee7b | checkpoint | Install tiles to floors as per drawings to floors near staff lounge
15e2bcf0-b32d-4152-aa22-fc04b98a13be | checkpoint | Install skirting tiles to amenity perimeter
d60b81a4-67c5-4e56-b520-782bcf8bbb0e | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
c771eb2a-e651-4fb5-98cc-2ed2169595d9 | checkpoint | Install tiles to walls as per elevations
d954da27-b1e2-4df8-b354-f5e06ec2d055 | checkpoint | Install tiles to walls to wellness room
1e9cffc3-6431-46fa-a4e4-58de8aee4825 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
900419ae-43a9-453e-a417-7e7684caf3fd | checkpoint | Grout is consistent throughout and no missing grout.
e0e0ad38-69b2-44cd-bb9c-7d90d829d648 | checkpoint | Tiling completed, checked and Supervisor sign off
8c556c26-367d-4283-afac-d4333e7227a6 | checkpoint | Silicone is completed to all tile junctions where required
646e3e90-fcd0-4074-9554-fa362a445c9d | checkpoint | Sealer to all stone on L28 and L29
0edfa02e-cc51-49e3-854e-a94ba820c1d4 | checkpoint | Area left clean & tidy
b795afb6-3518-48b2-8ab8-03118f8058fc | checkpoint | Builders clean completed
25e714d7-9e18-425b-bde9-42db76eaec82 | checklist | QA - Tiling Installation L29 |  | Tiling Installation
e1aaca4d-75f2-4b07-afc8-6c5fd44aa917 | section | Tiling to floors and walls
432ff84a-f60a-48d8-b273-056bfa8d6a0e | checkpoint | Tiles set out according to latest drawing - always check revisions on site
9430a01d-f5ce-49e2-aa6b-d46cdce7bdd5 | checkpoint | Specified product used with notched trowel or required product
dbe642d7-ca4f-4e21-b516-d0a9956d0a78 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
354f7f01-ede0-42cd-9697-61d09b698315 | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
71ec6cdb-a328-40cc-982f-4b0fcfed2592 | checkpoint | Install tiles to floors as per drawings to amenity floors
be20ff1d-c008-4c30-9ad0-b1dc58e25159 | checkpoint | Install tiles to floors as per drawings to floors in kitchenette
3f8c9df8-1d6a-4d93-a546-5657958df161 | checkpoint | Install skirting tiles to amenity perimeter
8e914500-c832-4dee-be5c-ff3b308b222b | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
2286f7fd-6d51-4823-852a-28130063e5b9 | checkpoint | Install tiles to walls as per drawings
e28f5ccb-ff24-418a-9bd4-ffb79ba750ed | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
20992363-a294-43af-86aa-870702ab8a4d | checkpoint | Grout is consistent throughout and no missing grout.
d9ccf84b-d58b-4c91-b0c6-3c2043057897 | checkpoint | Tiling completed, checked and Supervisor sign off
d08f2bcc-7b33-4ab5-9cd8-f7563db78d63 | checkpoint | Silicone is completed to all tile junctions where required
d4570b91-480e-453e-8d1d-b6af8c8791e3 | checkpoint | Sealer to all stone on L28 and L29
3a5d79a3-ac71-48ee-886f-2959f8183465 | checkpoint | Area left clean & tidy
3c86baa8-26d1-4176-b605-ae60381056fc | checkpoint | Builders clean completed
c6bf7ea6-bf22-4488-823e-987c25046385 | checkpoint | Change of details and or instructions
4c40ef8e-4f8b-44f9-b51a-d626a5ef0cbc | checkpoint | Site specific details to be added
cc3a8107-74cf-4e33-abb3-349eb51f0b60 | checkpoint | Material Details - Notes to be added of materials used on site
a3c3325e-ca8a-4121-868f-766988c6f89b | checklist | QA - Wall/Floor Preparation |  | Wall/Floor Preparation
ad373651-1d51-46b5-8f8f-857e8fc86757 | section | Details
d4fb065d-b3a8-4e57-98c5-6f6afd34441f | checkpoint | Is the area clean, and cleared, ready for necessary preparation
68e0bf24-baf6-491e-8092-4695c2c94e60 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
235aec78-1e80-490d-b695-f66c87c91649 | checkpoint | Has screeding been completed to shower at correct height and falls with correct product
c8abafc6-411b-4739-81f3-70e84c197805 | checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
5a25e7ba-4865-4feb-b850-d07a193b4c90 | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
726e14a3-0d96-4e54-b05b-81d5aad0abaa | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
fc9a7a87-b81b-43c4-a5d4-d9ab601f473d | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
22b1442c-1d84-4a77-9e57-5e02e4a7d720 | checklist | QA - Waterproofing |  | Waterproofing
af6be854-9c9e-4f8f-b8b8-82912644806d | section | Details
af913a00-8f16-42da-b56a-67e53258e0c0 | checkpoint | Substrate to receive waterproofing has slimline installed to any corners and has been gib stopped
ee15b053-7c77-47d4-b293-f5dc890b3674 | checkpoint | Gaskets have been installed to floor flange and wall plumbing fittings
703726a5-d0f6-4b3d-bf97-db5b185846b3 | checkpoint | Correct waterproofing is supplied as per project specification.
36fefc99-1982-4a27-bea9-3b0930dec69d | checkpoint | Waterproofing coat # 1 applied to floors, upstand and walls (take photos)
ce987949-a685-48a3-b3c7-c343791c488e | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
4d1134ff-cbfb-4861-a652-1b3d09eb171b | checkpoint | Flood tests, if required, undertaken and photos provided.