## Project Structure (digital map)
First Click | Second Click | Checklist Needed:
Facade
Ground Level
Level 1
Level 2
Level 3
Level 4

## Facade Checklists
checklist | FS-01: Aluminium Joinery:
checkpoint | Substrate acceptable
checkpoint | Openings sealed
checkpoint | General install photos
checkpoint | Fixings correct
checkpoint | Windows sealed
checkpoint | Glazing installed
checkpoint | Rainshield angle installed
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received & attached as applicable
checklist | FS-02/3: Precast Concrete Panels:
checkpoint | General install photos
checkpoint | Lifting eye flashings installed and grouted
checkpoint | Joint flashings installed
checkpoint | Expansion tape installed at inaccessible locations
checkpoint | Horizontal joints sealed
checkpoint | Vertical joints sealed
checkpoint | Panel brackets installed
bool | Washers welded where required
bool | Bracket grouted
bool | Intumescent paint applied
checkpoint | Window opening sealed
checkpoint | Panels painted / sealed
checkpoint | Additional flashings installed
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received & attached as applicable
checklist | FS-04: Rooflights - Solatube:
checklist | FS-05: Aluminium Panels:
checkpoint | Nib installed
checkpoint | Framing complete
bool | Correct grade timber used
bool | Set-out correct
bool | Fixings correct
checkpoint | Framing sealed
checkpoint | Waterproofing membrane lapped up nib
checkpoint | RAB installed
checkpoint | Self adhesive membrane installed
bool | Penetrations sealed
checkpoint | Flashing tape installed
checkpoint | Extrusions and underflashings installed
checkpoint | Panels installed
bool | Fixings correct
checkpoint | Panels sealed
checkpoint | Additional flashings installed
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received & attached as applicable
checklist | FS-06: Aluminium Screening:
checklist | FS-07: Aluminium Vertical Louvres:
checklist | FS-08: Soffits - Hermpac Cedar:
checklist | FS-09: Louvrec Louvres:
checklist | FS-10: Brick Veneer:
checklist | FS-11: Concrete Block and Render:
checklist | FS-12: Steel Canopy:
checklist | RS-01: Membrane Roof - Asphaltech IKO Armourplan:
Checkpoint | Framing complete
Checkpoint | Plywood installed
Checkpoint | Membrane installed
Checkpoint | Penetrations through roof installed
Checkpoint | Flashings installed
checkpoint | Roof/gutter testing witnessed by Inhabit
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received & attached as applicable
checklist | MS-01: Balcony Membrane - Asphaltech IKO Permatec:
checkpoint | Substrate acceptable
checkpoint | Membrane installed
checkpoint | Transition waterproofing installed
checkpoint | Flashings installed
checkpoint | Deck tiles installed
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received & attached as applicable
checklist | MS-02: Balcony Membrane - Sikalastic 152:
checklist | BS-01: Glazed Balustrades:

## Fitout Checklists
checklist | Apartment Preline:
checkpoint | IT Bulkheads complete
checkpoint | Steel stud installed
checkpoint | Plumbing first fix complete
checkpoint | Mechanical first fix complete
checkpoint | Sprinkler first fix complete
checkpoint | Passive fire complete
checkpoint | Nogs installed
checkpoint | Insulation installed
checkpoint | GIB installed
checkpoint | Any additional photos, comments and observations
checkpoint | Council / Consultant inspections complete
checkpoint | Trades QA received & attached as applicable

## Add to Conqa 26.06.2023
checklist | RS-01: Membrane Roof - Asphaltech IKO Armourplan:
Checkpoint | Framing complete
Checkpoint | Plywood installed
Checkpoint | Membrane installed
Checkpoint | Penetrations through roof installed
Checkpoint | Flashings installed
checkpoint | Roof/gutter testing witnessed by Inhabit
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received & attached as applicable