## Table 1
[5 empty] | Inspection and Test Plan - Control and Supervision of the Works | [20 empty] | Doc ID: ITP021-1 REV: 0
Client: Melbourne Airport (APAM) | [6 empty] | Contract No: CP1002 | [12 empty] | Prepared By: Giuliano Follacchio
Project: MAPMP 2.0 – DP1 | [14 empty] | Reviewed By: Giuliano Follacchio | [10 empty] | Date: 12/5/23
Construction Process: AGL – Demolition and Isolation | [14 empty] | Approved By: Jordan Nicolaou | [10 empty] | Date: 12/5/23
Specifications: Technical Specification – MAPMP 2.0 – DP1 – Minor Asphalt Works
Structure / Component:
Lot No: |  |  | Lot Details: |  |  | Lot size/Quantity: | [10 empty] | Date:
Item No. |  | Task/Activity Description |  | Inspection/Test | [13 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  |  | Responsibility Project Engineer Principal’s Representative Surveyor Foreman |  | Checked by:
|  |  |  | Frequency |  | Acceptance Criteria |  |  | Reference Documents |  |  | Inspection/ Test Method |  |  | Record of conformity | [8 empty] | Avionics |  |  |  | Principal’ s Rep. |  | FH |  | Date
1 |  | Preliminary Works
Drawing
1.1 |  | Preparation for the Works to be Undertaken |  | Prior to Start |  | Notify the Airport’s Engineering personnel at least two days prior to removing the works area from service and prior to returning the works area to service. |  |  | sets: 60692389- SHT-01_1- 10 60692389- SHT-01_2- |  |  | Verify |  |  | This ITP Signed / Aconex |  |  | HP* |  |  |  | Project Engineer
10
[6 empty] | Ensure the continuity of service of the |  |  | Drawing sets: 60692389- SHT-01_1- 10 60692389- SHT-01_2- 10
AGL facilities is maintained while
undertaking the works.
1.2 |  | AGL Continuity of Service |  | Prior to Start |  | No outages of any facilities shall be | [5 empty] | Verify |  |  | This ITP Signed |  |  | HP* |  |  |  | Project Engineer
permitted unless prior approval has been
received by the Contractor from the
Contract Administrator.
1.3 |  | Check for correct documentation |  | Prior to commencing any activity |  | Ensure that all employees and subcontractors are using the latest and complete set of drawings |  |  | IFC Drawings |  |  | Verify |  |  | This ITP Signed |  |  | HP* |  |  |  | Project Engineer
1.4 |  | Implementation of all measures and controls |  | Prior to commencing any activities |  | All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP. |  |  | PSP, EMP, TMP, JSEA, |  |  | Verify |  |  | Site and Office Inspection |  |  | HP* |  |  |  | Project Engineer / Site Supervisor
[5 empty] | Inspection and Test Plan - Control and Supervision of the Works | [20 empty] | Doc ID: ITP021-1 REV: 0
Client: Melbourne Airport (APAM) | [6 empty] | Contract No: CP1002 | [12 empty] | Prepared By: Giuliano Follacchio
Project: MAPMP 2.0 – DP1 | [14 empty] | Reviewed By: Giuliano Follacchio | [10 empty] | Date: 12/5/23
Construction Process: AGL – Demolition and Isolation | [14 empty] | Approved By: Jordan Nicolaou | [10 empty] | Date: 12/5/23
Specifications: Technical Specification – MAPMP 2.0 – DP1 – Minor Asphalt Works
Structure / Component:
Item No. |  | Task/Activity Description |  | Inspection/Test | [13 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  |  | Responsibility Project Engineer Principal’s Representative Surveyor Foreman |  | Checked by:
|  |  |  | Frequency | Acceptance Criteria |  |  |  | Reference Documents |  |  | Inspection/ Test Method |  |  | Record of conformity | [8 empty] | Avionics |  |  |  | Principal’ s Rep. |  | FH |  | Date
SWMS, WP
2 |  | Demolition and Isolation Works
The Contractor must:
a. investigate and locate both above
ground level features and below ground
2.1 |  | Investigation, Location, Identification, Protection, Modification, Isolation, Extension or Relocation of Existing Features |  | Prior to commencing demolition works | services that may be affected during the performance of the Work under the Contract; b. identify, protect, modify, extend or relocate existing features, services or facilities as necessary for the |  |  |  | IFC Drawings |  |  | Verify |  |  | This ITP signed / Avionics CL001-1, CL001-2, CL001-3 |  |  | IP |  |  |  | Project Engineer/Avion ics
performance of the Work under the
Contract to the satisfaction of the
Principal and other relevant authorities;
2.2 |  | Demolition and/or removal of AGL |  | Each Lot | Prior to any pavement overlay works, all light fittings and shallow bases impacted by the pavement reconstruction works shall be removed. The shallow bases shall be removed by neatly saw cutting a hole in the pavement slightly larger than the outside diameter of the light base. |  |  |  | IFC Drawings |  |  | Verify |  |  | This ITP signed / Avionics CL001-1, CL001-2, CL001-3 |  |  | IP |  |  |  | Project Engineer/Avion ics
[6 empty] | Inspection and Test Plan - Control and Supervision of the Works | [20 empty] | Doc ID: ITP021-1 REV: 0
| Client: Melbourne Airport (APAM) | [6 empty] | Contract No: CP1002 | [12 empty] | Prepared By: Giuliano Follacchio
| Project: MAPMP 2.0 – DP1 | [14 empty] | Reviewed By: Giuliano Follacchio | [10 empty] | Date: 12/5/23
| Construction Process: AGL – Demolition and Isolation | [14 empty] | Approved By: Jordan Nicolaou | [10 empty] | Date: 12/5/23
Specifications: Technical Specification – MAPMP 2.0 – DP1 – Minor Asphalt Works
Structure / Component:
| Item No. |  | Task/Activity Description | Inspection/Test | [14 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  |  | Responsibility Project Engineer Principal’s Representative Surveyor Foreman |  | Checked by:
|  |  |  | Frequency |  | Acceptance Criteria |  |  |  | Reference Documents |  |  | Inspection/ Test Method |  |  | Record of conformity | [8 empty] | Avionics |  |  |  | Principal’ s Rep. |  | FH |  | Date
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point | Work shall not proceed past the HP until released by the Principal’s Representative | [6 empty] | IP |  |  | Inspection point |  |  |  | Formal Inspection to be done and recorded
| HP* |  | Fulton Hogan Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP |  |  | Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point | An inspection which must be witnessed by the Principal’s Representative | [6 empty] | SCP |  |  | Survey conformance point |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point | Written or verbal approval given by the Principal’s Representative
Notes