## Table 1
[8 empty] | Inspection and Test Plan - Control and Supervision of the Works | [20 empty] | Doc ID: ITP021-2 REV: 0
Client: Melbourne Airport (APAM) | [9 empty] | Contract No: CP1002 | [12 empty] | Prepared By: Giuliano Follacchio
Project: MAPMP 2.0 – DP1 | [18 empty] | Reviewed By: Giuliano Follacchio | [9 empty] | Date: 12/5/23
Construction Process: AGL – Reinstallation of Secondary Cable | [18 empty] | Approved By: Jordan Nicolaou | [9 empty] | Date: 12/5/23
Specifications: Technical Specification – MAPMP 2.0 – DP1 – Minor Asphalt Works
Structure / Component:
Lot No: |  |  | Lot Details: |  |  |  | Lot size/Quantity: | [13 empty] | Date:
Item No. |  | Task/Activity Description |  |  | Inspection/Test | [15 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  |  | Responsibility Project Engineer Principal’s Representative Surveyor Foreman |  | Checked by:
[5 empty] | Frequency |  |  |  | Acceptance Criteria |  |  | Reference Documents |  |  | Inspection/ Test Method |  |  | Record of conformity | [8 empty] | Avionics |  |  |  | Principal’ s Rep. |  | FH |  | Date
1 |  | Installation of New Secondary Cable in Existing Shallow Base Canister
Drawing
sets:
1.1 |  | Mark and cut |  |  | Each Lot |  |  |  | Slots marked out and cut from to light base. |  |  | 60692389- SHT-01_1- 10 |  |  | Verify |  |  | This ITP Signed / Avionics |  |  | HP* |  |  |  | Project Engineer/Avionics
[12 empty] | 60692389- | [5 empty] | CL002
SHT-01_2-
10
Drawing
sets:
1.2 |  | Cabling |  |  | Each Lot |  |  |  | Cables ran and connected from existing base via joints/slots/conduits to SIT pit. |  |  | 60692389- SHT-01_1- 10 |  |  | Verify |  |  | This ITP Signed / Avionics |  |  | IP |  |  |  | Project Engineer/Avionics
[12 empty] | 60692389- | [5 empty] | CP002
SHT-01_2-
10
1.3 |  | Sealing |  |  | Each Lot |  |  |  | Once cables installed, backing rod placed and expansion joints sealed with approved product. |  |  | Drawing sets: 60692389- SHT-01_1- 10 |  |  | Verify |  |  | This ITP Signed / CL002 |  |  | IP |  |  |  | Project Engineer/Avionics
[9 empty] | Inspection and Test Plan - Control and Supervision of the Works | [20 empty] | Doc ID: ITP021-2 REV: 0
| Client: Melbourne Airport (APAM) | [9 empty] | Contract No: CP1002 | [12 empty] | Prepared By: Giuliano Follacchio
| Project: MAPMP 2.0 – DP1 | [18 empty] | Reviewed By: Giuliano Follacchio | [9 empty] | Date: 12/5/23
| Construction Process: AGL – Reinstallation of Secondary Cable | [18 empty] | Approved By: Jordan Nicolaou | [9 empty] | Date: 12/5/23
Specifications: Technical Specification – MAPMP 2.0 – DP1 – Minor Asphalt Works
Structure / Component:
| Item No. |  | Task/Activity Description |  |  | Inspection/Test | [15 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  |  | Responsibility Project Engineer Principal’s Representative Surveyor Foreman |  | Checked by:
[6 empty] | Frequency |  |  | Acceptance Criteria |  |  |  | Reference Documents |  |  | Inspection/ Test Method |  |  | Record of conformity | [8 empty] | Avionics |  |  |  | Principal’ s Rep. |  | FH |  | Date
60692389- SHT-01_2- 10
Drawing
sets:
| 1.6 |  | Finishing, Testing, Demobilisation |  |  | Each Lot |  |  | Gasket positioned on light top, light plugged and positioned to current orientation. Light tested and area |  |  |  | 60692389- SHT-01_1- 10 |  |  | Verify |  |  | This ITP Signed / Avionics |  |  | IP |  |  |  | Project Engineer/Avionics
[9 empty] | cleaned before demobilisation. |  |  |  | 60692389- | [5 empty] | CL002
SHT-01_2-
10
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point | Work shall not proceed past the HP until released by the Principal’s Representative | [9 empty] | IP |  |  | Inspection point |  |  |  |  | Formal Inspection to be done and recorded
| HP* |  | Fulton Hogan Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [9 empty] | TP |  |  | Test Point |  |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point | An inspection which must be witnessed by the Principal’s Representative | [9 empty] | SCP |  |  | Survey conformance point |  |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point | Written or verbal approval given by the Principal’s Representative
[8 empty] | Inspection and Test Plan - Control and Supervision of the Works | [20 empty] | Doc ID: ITP021-2 REV: 0
Client: Melbourne Airport (APAM) | [9 empty] | Contract No: CP1002 | [12 empty] | Prepared By: Giuliano Follacchio
Project: MAPMP 2.0 – DP1 | [18 empty] | Reviewed By: Giuliano Follacchio | [9 empty] | Date: 12/5/23
Construction Process: AGL – Reinstallation of Secondary Cable | [18 empty] | Approved By: Jordan Nicolaou | [9 empty] | Date: 12/5/23
Specifications: Technical Specification – MAPMP 2.0 – DP1 – Minor Asphalt Works
Structure / Component:
Notes