## Table 1
[5 empty] | Inspection and Test Plan - Control and Supervision of the Works | [20 empty] | Doc ID: ITP 021-4A REV: 0
Client: Melbourne Airport | [6 empty] | Contract No: CP1002 | [12 empty] | Prepared By: Giuliano Follacchio
Project: MAPMP 2.0 – DP1 | [15 empty] | Reviewed By: Giuliano Follacchio | [9 empty] | Date: 17/5/23
Construction Process: AGL – New Foundation Works – Removal | [15 empty] | Approved By: Jordan Nicolaou | [9 empty] | Date: 17/5/23
Specifications: Technical Specification – MAPMP 2.0 – DP1 – Minor Asphalt Works
Structure / Component:
Lot No: |  |  | Lot Details: |  |  | Lot size/Quantity: | [11 empty] | Date:
Item No. |  | Task/Activity Description |  | Inspection/Test | [13 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  |  | Responsibility Project Engineer Principal’s Representative Surveyor Foreman |  | Checked by:
|  |  |  | Frequency |  | Acceptance Criteria |  |  | Reference Documents |  |  | Inspection/ Test Method |  |  | Record of conformity | [8 empty] | Avionics |  |  |  | Principal’ s Rep. |  | FH |  | Date
1 |  | Removals
Drawing
sets:
60692389-
1.1 |  | Preparation for the works to be undertaken |  | Prior to Start |  | Ensure survey set out is undergone, excavation permit obtained and (if required) services in work(s) area isolated. Dilapidation survey. |  |  | SHT-01_1- 10 60692389- SHT-01_2- 10 Specification |  |  | Verify |  |  | This ITP Signed / Avionics CL004A |  |  | HP* |  |  |  | Project Engineer/Avionics
: 60692389-
PS-01-AV-
1
Drawing
sets:
1.2 |  | Core and inspect |  | Each Lot |  | Light base cored into pavement and slot from base cut to pavement edge/expansion joint. Based removed and cleaned. Inspection to determine works method. |  |  | 60692389- SHT-01_1- 10 60692389- SHT-01_2- 10 |  |  | Verify |  |  | This ITP Signed / Avionics CL004A |  |  | IP |  |  |  | Project Engineer/Avionics
Specification
: 60692389-
[5 empty] | Inspection and Test Plan - Control and Supervision of the Works | [20 empty] | Doc ID: ITP 021-4A REV: 0
Client: Melbourne Airport | [6 empty] | Contract No: CP1002 | [12 empty] | Prepared By: Giuliano Follacchio
Project: MAPMP 2.0 – DP1 | [15 empty] | Reviewed By: Giuliano Follacchio | [9 empty] | Date: 17/5/23
Construction Process: AGL – New Foundation Works – Removal | [15 empty] | Approved By: Jordan Nicolaou | [9 empty] | Date: 17/5/23
Specifications: Technical Specification – MAPMP 2.0 – DP1 – Minor Asphalt Works
Structure / Component:
Item No. |  | Task/Activity Description |  | Inspection/Test | [13 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  |  | Responsibility Project Engineer Principal’s Representative Surveyor Foreman |  | Checked by:
|  |  |  | Frequency | Acceptance Criteria |  |  |  | Reference Documents |  |  | Inspection/ Test Method |  |  | Record of conformity | [8 empty] | Avionics |  |  |  | Principal’ s Rep. |  | FH |  | Date
PS-01-AV- 0001
[5 empty] | Continue core to depth of basecourse. |  |  |  | Drawing sets: 60692389- SHT-01_1- 10 Specification : 60692389- PS-01-AV- 0001
Reconnect conduits.
1.3 |  | ‘Method 2’ installation (SP1 only) |  | Each Lot | Concrete poured to correct level and cover. Spacers positioned and conduits/cabled | [6 empty] | Verify |  |  | This ITP Signed / Avionics |  |  | IP |  |  |  | Project Engineer/Avionics
[5 empty] | cleaned. | [9 empty] | CL004A
Mesh laid and rapid-set concrete
poured.
Drawing
sets:
60692389-
SHT-01_1-
1.4 |  | Finishing and demobilisation |  | Each Lot | Pavement area cleaned and equipment packed away. Work crews demobilised and FOD walk undertaken. |  |  |  | 10 60692389- SHT-01_2- 10 |  |  | Verify |  |  | This ITP Signed / Avionics CL004A |  |  | IP |  |  |  | Project Engineer/Avionics
Specification
: 60692389-
PS-01-AV-
1
[6 empty] | Inspection and Test Plan - Control and Supervision of the Works | [20 empty] | Doc ID: ITP 021-4A REV: 0
| Client: Melbourne Airport | [6 empty] | Contract No: CP1002 | [12 empty] | Prepared By: Giuliano Follacchio
| Project: MAPMP 2.0 – DP1 | [15 empty] | Reviewed By: Giuliano Follacchio | [9 empty] | Date: 17/5/23
| Construction Process: AGL – New Foundation Works – Removal | [15 empty] | Approved By: Jordan Nicolaou | [9 empty] | Date: 17/5/23
Specifications: Technical Specification – MAPMP 2.0 – DP1 – Minor Asphalt Works
Structure / Component:
| Item No. |  | Task/Activity Description | Inspection/Test | [14 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  |  | Responsibility Project Engineer Principal’s Representative Surveyor Foreman |  | Checked by:
|  |  |  | Frequency |  | Acceptance Criteria |  |  |  | Reference Documents |  |  | Inspection/ Test Method |  |  | Record of conformity | [8 empty] | Avionics |  |  |  | Principal’ s Rep. |  | FH |  | Date
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point | Work shall not proceed past the HP until released by the Principal’s Representative | [6 empty] | IP |  |  | Inspection point |  |  |  |  | Formal Inspection to be done and recorded
| HP* |  | Fulton Hogan Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP |  |  | Test Point |  |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point | An inspection which must be witnessed by the Principal’s Representative | [6 empty] | SCP |  |  | Survey conformance point |  |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point | Written or verbal approval given by the Principal’s Representative
Notes