## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP021-1 – Demolition and Isolation | itp |  |  |  |  | ITP021-1 – Demolition and Isolation
section | 1. Preliminary Works
checkpoint | 1.1 - Preparation for the Works to be Undertaken
label | Frequency - Prior to Start
label | Acceptance Criteria - Notify the Airport’s Engineering personnel at least two days prior to removing the works area from service and prior to returning the works area to service.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Aconex
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.2 - AGL Continuity of Service
label | Frequency - Prior to Start
label | Acceptance Criteria - Ensure the continuity of service of the AGL facilities is maintained while undertaking the works.
label | • No outages of any facilities shall be permitted unless prior approval has been received by the Contractor from the Contract Administrator.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.3 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | Reference Documents - IFC Drawings
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.4 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activities
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/ Test Method - Verify
label | Record of conformity - Site and Office Inspection
label | HP*
label | Responsibility - Project Engineer / Site Supervisor
section | 2. Demolition and Isolation Works
checkpoint | 2.1 - Investigation, Location, Identification, Protection, Modification, Isolation, Extension or Relocation of Existing Features
label | Frequency - Prior to commencing demolition works
label | Acceptance Criteria - The Contractor must:
label | a. investigate and locate both above ground level features and below ground services that may be affected during the performance of the Work under the Contract;
label | b. identify, protect, modify, extend or relocate existing features, services or facilities as necessary for the performance of the Work under the Contract to the satisfaction of the Principal and other relevant authorities;
label | Reference Documents - IFC Drawings
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP signed / Avionics CL001-1, CL001-2, CL001-3
label | IP
label | Responsibility - Project Engineer/Avion ics
checkpoint | 2.2 - Demolition and/or removal of AGL
label | Frequency - Each Lot
label | Acceptance Criteria - Prior to any pavement overlay works, all light fittings and shallow bases impacted by the pavement reconstruction works shall be removed. The shallow bases shall be removed by neatly saw cutting a hole in the pavement slightly larger than the outside diameter of the light base.
label | Reference Documents - IFC Drawings
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP signed / Avionics CL001-1, CL001-2, CL001-3
label | IP
label | Responsibility - Project Engineer/Avion ics
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checklist | ITP021-2 – Reinstallation of Secondary Cable | itp |  |  |  |  | ITP021-2 – Reinstallation of Secondary Cable
section | 1. Installation of New Secondary Cable in Existing Shallow Base Canister
checkpoint | 1.1 - Mark and cut
label | Frequency - Each Lot
label | Acceptance Criteria - Slots marked out and cut from to light base.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL002
label | HP*
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.2 - Cabling
label | Frequency - Each Lot
label | Acceptance Criteria - Cables ran and connected from existing base via joints/slots/conduits to SIT pit.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CP002
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.3 - Sealing
label | Frequency - Each Lot
label | Acceptance Criteria - Once cables installed, backing rod placed and expansion joints sealed with approved product.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / CL002
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.6 - Finishing, Testing, Demobilisation
label | Frequency - Each Lot
label | Acceptance Criteria - Gasket positioned on light top, light plugged and positioned to current orientation. Light tested and area cleaned before demobilisation.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL002
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checklist | ITP021-3 – Reinstallation of Shallow Base Canister | itp |  |  |  |  | ITP021-3 – Reinstallation of Shallow Base Canister
section | 1. Installation of Shallow Base Canister
checkpoint | 1.1 - Preparation for the Works to be Undertaken
label | Frequency - Prior to Start
label | Acceptance Criteria - Ensure survey set out is undergone, excavation permit obtained and (if required) services in work(s) area isolated. Lights, slot cuts, and aiming points marked out.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL003
label | HP*
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.2 - Core and Cut
label | Frequency - Each Lot
label | Acceptance Criteria - Light base cored into pavement and slot from base cut to pavement edge/expansion joint
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL003
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.3 - Base positioning
label | Frequency - Each Lot
label | Acceptance Criteria - Light base positioned and epoxy poured to secure. Installation of jig.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1- 10
label | • 60692389- SHT-01_2- 10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL003
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.4 - Cabling
label | Frequency - Each Lot
label | Acceptance Criteria - Cables ran and connected from new base via joints/slots/conduits to SIT pit.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL003
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.5 - Sealing
label | Frequency - Each Lot
label | Acceptance Criteria - Once cables installed, backing rod placed and expansion joints sealed with approved product.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL003
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.6 - Finishing, Testing, Demobilisation
label | Frequency - Each Lot
label | Acceptance Criteria - Gasket positioned on light top, light plugged and positioned to current orientation. Light tested and area cleaned before demobilisation.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL003
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checklist | ITP021-4A – New Foundation Works – Removal | itp |  |  |  |  | ITP021-4A – New Foundation Works – Removal
section | 1. Removals
checkpoint | 1.1 - Preparation for the works to be undertaken
label | Frequency - Prior to Start
label | Acceptance Criteria - Ensure survey set out is undergone, excavation permit obtained and (if required) services in work(s) area isolated. Dilapidation survey.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1- 10
label | • 60692389- SHT-01_2- 10
label | • Specification: 60692389-PS-01-AV-0001
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL004A
label | HP*
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.2 - Core and inspect
label | Frequency - Each Lot
label | Acceptance Criteria - Light base cored into pavement and slot from base cut to pavement edge/expansion joint. Based removed and cleaned. Inspection to determine works method.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | • Specification: 60692389-PS-01-AV-0001
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL004A
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.3 - ‘Method 2’ installation (SP1 only)
label | Frequency - Each Lot
label | Acceptance Criteria - Continue core to depth of basecourse.
label | • Reconnect conduits.
label | • Concrete poured to correct level and cover.
label | • Spacers positioned and conduits/cabled cleaned.
label | • Mesh laid and rapid-set concrete poured.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1- 10
label | • Specification: 60692389- PS-01-AV- 0001
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL004A
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.4 - Finishing and demobilisation
label | Frequency - Each Lot
label | Acceptance Criteria - Pavement area cleaned and equipment packed away. Work crews demobilised and FOD walk undertaken.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | • Specification: 60692389-PS-01-AV-0001
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL004A
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checklist | ITP021-4B – New Foundation Works – Installation | itp |  |  |  |  | ITP021-4B – New Foundation Works – Installation
section | 1. Re-installs
checkpoint | 1.1 - Preparation for the works to be undertaken
label | Frequency - Prior to Start
label | Acceptance Criteria - Resurvey light position and aiming points.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | • Specification: 60692389-PS-01-AV-0001
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL004B
label | HP*
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.2 - Core and inspect
label | Frequency - Each Lot
label | Acceptance Criteria - Core to depth of new foundation.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | • Specification: 60692389-PS-01-AV-0001
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL004B
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.3 - Installation of new can
label | Frequency - Each Lot
label | Acceptance Criteria - New can mounted on positioning jig. Jig/can positioned, levelled, aligned. Spacers positioned and conduits checked for clearance. Epoxy poured.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | • Specification: 60692389-PS-01-AV-0001
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL004B
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.4 - Reinstallation of light
label | Frequency - Each Lot
label | Acceptance Criteria - Foundation hole cleaned and existing light to be positioned, identified.
label | • Light plugged back in and positioned. New bolts installed with required torque.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | • Specification: 60692389-PS-01-AV-0001
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL004B
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | 1.5 - Finishing, demobilisation and testing
label | Frequency - Each Lot
label | Acceptance Criteria - Pavement area cleaned and equipment packed away. Work crews demobilised and FOD walk undertaken. Light tested once circuit re-energised.
label | Reference Documents - Drawing sets:
label | • 60692389- SHT-01_1-10
label | • 60692389- SHT-01_2-10
label | • Specification: 60692389-PS-01-AV-0001
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP Signed / Avionics CL004B
label | IP
label | Responsibility - Project Engineer/Avionics
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP