## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Project Completion Checklist
section | Details
checkpoint-no-status | Details
date | Date
textbox | Person Completing
section | Have the below been completed?
checkpoint | All Variations Submitted
checkpoint | Electrical Testing Complete
checkpoint | Data Testing Complete
checkpoint | All DB schedules Laminated and displayed on board
checkpoint | ITPs in CONQA
checkpoint | CCEW form completed and emailed to meterccew@customerservice.nsw.gov.au
checkpoint | As-builts complete and sent to office staff
checkpoint | O&M Sent to builder including As-builts
checkpoint | All tools / equipment removed from site and brought back to the stores
checkpoint | Over ordered materials identified and returned to wholesaler
checkpoint | Project Fully Claimed
checkpoint | First 50% Retention/BG Release Requested
checkpoint | DLP Works reminder set in Outlook Calender
checkpoint | Second 50% Retention/BG Release Requested
checkpoint | End of job review/meeting with office team and Foreman
section | Completion Signoff
checkpoint | Completion Signoff
date | Date
textbox | Project Manager
textbox | Project Co-Ordinator
holdpoint | Add Signatures
checklist | Tender Handover Meeting
section | Meeting Details
checkpoint-no-status | Meeting Details
date | Date
textbox | Start Time
textbox | Attendees
section | Project Details
checkpoint-no-status | Project Details
textbox | Project Name
textbox | Project Number
textbox | Project Location
textbox | Client
textbox | Client Contact
textbox | Client Contact Details (Phone & Email)
textbox | Ergo Estimator
textbox | Ergo Project Manager
textbox | Ergo Foreman
textbox | Project Start Date
textbox | Contract Value
textbox | Estimated Profit
textbox | Type of Project & Scope off Works
textbox | PC Date
textbox | Program Weeks
textbox | Estimated Workforce
checkpoint | Contract Received
checkpoint | Insurences sent to Client
section | Procurement
checkpoint | Procurement
textbox | Suppliers
textbox | Subcontractors
textbox | Long Lead Time Items
section | Job Folder
checkpoint | Setup Job Folder in Sharepoint
checkpoint | Quotation in Job Folder
checkpoint | Add Drawings, Specification & any other project related information into Job Folder
section | Health & Safety
checkpoint | SWMS Complete
checkpoint | Upload/Provide SWMS to Builder
checkpoint | Prepare Hardcopy of SWMS for site
checkpoint | Project Management Plan (If Required)
checkpoint | Site Specific PPE supplies to be discussed [LVR kits, First Aid, Respirators, HV Kit]
section | Quality Assurance
checkpoint | CONQA Checklists to be set up
checkpoint | Foreman to be given access to CONQA
section | Foreman Expectations
checkpoint-no-status | Foreman Expectations
textbox | Expectations of the Foreman for the Project Duration
section | Notes
checkpoint-no-status | Project & Estimate Specifics / Issues / Potential Risk or Reward
textbox | Project & Estimate Specifics/Issues/Potential Risk or Reward
section | Meeting Signoff
checkpoint | Meeting Signoff
textbox | Finish Time
textbox | Project Manager
textbox | Foreman
textbox | Project Co-Ordinator
holdpoint | Add Signatures