## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-186-STR-SSB-Bridge expansion joints and waterproofing
ITP Description: |  | SSB-Bridge expansion joints and waterproofing
Discipline (e.g. CIV/STR/RAIL: |  | 186-STR
Revision Number: |  | 0
Revision Date: |  | 2024-07-24
ITP created by: |  | Isaac El Zayat
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for SSB Project
Inspection & Test Plan - Bridge Expansion Joints
[9 empty] | Revision: | 0
[9 empty] | Date: | 2024-07-24
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 660 January 2018 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | AC-AR Installation Guide | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.2 | Expansion Joint Components | IFC Drawings VR 660.03 | The Contractor shall supply all expansion joint components including joints, seals, inserts, anchorages, cover plates, waterproofing membrane, drainage system, bedding mortar, nosing, edging and all adhesives and sealants required for the installation of the joint system in conformity with the supplier’s recommendations. Attach Delivery dockets/Proof of purchase | Document Review/ Inspection | Where applicable, for each element | IP | PE/SPE | This ITP
3 | Preliminaries-Procedures
3.2 | Expansion Joint Design | IFC Drawings VR 660.03 | The expansion joint system shall match the drawings. Where applicable, the joint sealant shall match the Drawings and installation manual [free text box] : Enter: Specify the Joint type: AC-AR-125D for road P2-100D for SUP and Footpath | Document Review | Where applicable, once, within 4 weeks of acceptance of tender | WP | SE/PE | This ITP
4 | Pre-construction Activities
4.1 | Expansion Joint Installation Temperature | VR 660.04 | The bridge temperature shall be measured at the time of installation and where it differs by more than ±5°C from 20°C , shall be adjusted by the calculated values provided by the designers. For installation tempratures outside 20±5°C, the gap shall be adjusted by ±3mm per ±50°C Installation Temperature = [free text] | Measure | At the time of installation | IP | SE/PE | ConQA Hold Point Release
4.2 | Post-pour Inspection of Expansion Joint Bearing Surface | VR 660.04 | The faces of the concrete under the full length of the expansion joint shall be inspected for the presence of voids and other imperfections. | Visual | Prior to joint sealant (where applicable) | IP | SE/PE | ConQA Hold Point Release
5 | Construction Activities
5.1 | Expansion Joint Placement- Anchor Bolts | IFC Drawings AC-AR Installation Manual | After concrete strength is in excess of 30MPa, the anchor bolts can be tightenedvia the snug tight plus part turn method or with a claibrated torque wrench. As per installation manual: Part turn method: Snug tight + half turn Calibrated torque wrench: 400Nm | Measure Visual | AC-AR 125D (Road section) joints | IP | SE/PE/SPE | This ITP
5.2 | Expansion Joint Placement-Coverplate | IFC Drawing | Aluminium checker plate is installed with M12 Cuntersunk bolts as specified in the drawings | Inspection | P2-100D (SUP and Fottpath) Joints | IP | SE/PE | This ITP
5.3 | Expansion Joint Placement | IFC Drawings AC-AR Installation Manual VR 660.04 | Check compliance with the Drawings, installation manual and tolerances: Joint gap = ±3mm (38mm is specified on the drawings) Deviation from plan alignment = 5mm max. Deviation of top surfaces (step) = 0mm to -2mm when measured perpendicular with a 2.5m straight edge | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.4 | Compression Seals, Inserts and Membranes | VR 660.04 | Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint, inclusive of footpaths and barriers. Completed joints shall be watertight. | Visual | Where applicable, each element | IP | SE/PE/SPE | This ITP
5.5 | Final Inspection of installed system including all accessories | IFC Drawings | No visual damage to the installed system | Inspection | Once per Lot | IP | SE/PE | This ITP
6 | Post-construction Activities
5.1 | Trafficking of Joints During Construction | VR 660.04 | Joints, seals, inserts and membranes shall be protected from damage due to construction activities and the passage of site vehicles. | Visual | Where applicable, each element | IP | SE/PE/SPE | This ITP
5.2 | As-built Survey | IFC Drawings VR 660.04 | Provide record of dimensional measurements to demonstrate expansion joints comply with tolerances as per 5.3 above. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.3 | Subcontractor Product warranties obtained | Work Method Statement IFC Drawings | Product warranties obtained and are compliant with what is specificed in IFC Drawings | Inspection Document Review | Once per Lot | HP* | SPE/PE | Copies of product warranties
5.4 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /