## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-186-STR-SSB-Bridge Expansion Joint | itp |  |  |  |  | ITP-186-STR-SSB-Bridge Expansion Joint Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-186-STR-SSB-Bridge expansion joints and waterproofing
label | ITP Description: SSB-Bridge expansion joints and waterproofing
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 186-STR
label | Revision Number: 0
label | Revision Date: 24/07/2024
label | ITP created by: Isaac El Zayat
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 660 January 2018
label | 1.2 Non Dependent
label | Reference: AC-AR Installation Guide
section | Preliminaries-Materials
checkpoint | 2.2 Expansion Joint Components
label | REFERENCE: IFC Drawings, VR 660.03
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall supply all expansion joint components including joints, seals, inserts, anchorages, cover plates, waterproofing membrane, drainage system, bedding mortar, nosing, edging and all adhesives and sealants required for the installation of the joint system in conformity with the supplier’s recommendations.
label | ○ Attach Delivery dockets/Proof of purchase
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review/Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, for each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Preliminaries-Procedures
checkpoint | 3.2 Expansion Joint Design
label | REFERENCE: IFC Drawings, VR 660.03
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The expansion joint system shall match the drawings.
label | ○ Where applicable, the joint sealant shall match the Drawings and installation manual
textbox | Enter: Specify the Joint type:
label | ○ AC-AR-125D for road
label | ○ P2-100D for SUP and Footpath
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, once, within 4 weeks of acceptance of tender
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Pre-construction Activities
checkpoint | 4.1 Expansion Joint Installation Temperature
label | REFERENCE: VR 660.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The bridge temperature shall be measured at the time of installation and where it differs by more than ±5°C from 20°C , shall be adjusted by the calculated values provided by the designers.
label | ○ For installation tempratures outside 20±5°C, the gap shall be adjusted by ±3mm per ±50°C
label | ○ Installation Temperature = [free text]
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: At the time of installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 4.2 Post-pour Inspection of Expansion Joint Bearing Surface
label | REFERENCE: VR 660.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The faces of the concrete under the full length of the expansion joint shall be inspected for the presence of voids and other imperfections.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to joint sealant (where applicable)
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Expansion Joint Placement- Anchor Bolts
label | REFERENCE: IFC Drawings, AC-AR Installation Manual
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: After concrete strength is in excess of 30MPa, the anchor bolts can be tightenedvia the snug tight plus part turn method or with a claibrated torque wrench.
label | As per installation manual:
label | ○ Part turn method: Snug tight + half turn
label | ○ Calibrated torque wrench: 400Nm
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: AC-AR 125D (Road section) joints
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Expansion Joint Placement-Coverplate
label | REFERENCE: IFC Drawing
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Aluminium checker plate is installed with M12 Cuntersunk bolts as specified in the drawings
label | – – – – – – – – – – – – – – – – –
label | METHOD: Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: P2-100D (SUP and Fottpath) Joints
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Expansion Joint Placement
label | REFERENCE: IFC Drawings, AC-AR Installation Manual, VR 660.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Check compliance with the Drawings, installation manual and tolerances:
label | ○ Joint gap = ±3mm (38mm is specified on the drawings)
label | ○ Deviation from plan alignment = 5mm max.
label | ○ Deviation of top surfaces (step) = 0mm to -2mm when measured perpendicular with a 2.5m straight edge
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Compression Seals, Inserts and Membranes
label | REFERENCE: VR 660.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint, inclusive of footpaths and barriers.
label | ○ Completed joints shall be watertight.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Final Inspection of installed system including all accessories
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: No visual damage to the installed system
label | – – – – – – – – – – – – – – – – –
label | METHOD: Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Trafficking of Joints During Construction
label | REFERENCE: VR 660.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Joints, seals, inserts and membranes shall be protected from damage due to construction activities and the passage of site vehicles.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.2 As-built Survey
label | REFERENCE: IFC Drawings, VR 660.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate expansion joints comply with tolerances as per 5.3 above.
label | ○ Attach: Survey As-builts / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 Subcontractor Product warranties obtained
label | REFERENCE: Work Method Statement, IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Product warranties obtained and are compliant with what is specificed in IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | METHOD: Inspection, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SPE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Copies of product warranties
date | Date Completed:
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP