## QA Folder Structure
QA Folder Structure |  |  | Checklists
Manufacturing / Off-site QA
Site QA
SKP-GAB-003
| Shop Drawing - SKP-GAB-003 | D16 | ONSITE - Installation of Facade System
|  | D19 | ONSITE - Installation of Facade System
|  | D36 | ONSITE - Installation of Facade System
|  | DGF21 | ONSITE - Installation of Facade System
SKP-GAB-004
| Shop Drawing - SKP-GAB-004 | E01 | ONSITE - Installation of Facade System
|  | E12 | ONSITE - Installation of Facade System
|  | EGF04 | ONSITE - Installation of Facade System
|  | F02 | ONSITE - Installation of Facade System
SKP-GAB-005
| Shop Drawing - SKP-GAB-005 | F02 | ONSITE - Installation of Facade System
|  | F07 | ONSITE - Installation of Facade System
|  | G10 | ONSITE - Installation of Facade System
|  | H06 | ONSITE - Installation of Facade System
|  | J06 | ONSITE - Installation of Facade System
|  | J17 | ONSITE - Installation of Facade System
SKP-GAB-006
| Shop Drawing - SKP-GAB-006 | L05 | ONSITE - Installation of Facade System
|  | L07 | ONSITE - Installation of Facade System
|  | L28 | ONSITE - Installation of Facade System
|  | L32 | ONSITE - Installation of Facade System
SKP-GAB-007
| Shop Drawing - SKP-GAB-007 | P09 | ONSITE - Installation of Facade System
|  | P10 | ONSITE - Installation of Facade System
|  | R03 | ONSITE - Installation of Facade System
|  | R08 | ONSITE - Installation of Facade System
|  | S05 | ONSITE - Installation of Facade System
SKP-GAB-008
| Shop Drawing - SKP-GAB-007 | T05 | ONSITE - Installation of Facade System
|  | U08 | ONSITE - Installation of Facade System
|  | U15 | ONSITE - Installation of Facade System

## ITPs Checklists
type | name | values
checklist | OFFSITE - Fabrication of ALPOLIC NC Checklist
section | Pre-fabrication
checkpoint | Ensure CNC machine operator daily checklist has been undertaken
checkpoint | Nest summary and site drawings provided by programmer, file number printed on paperwork corresponds with file programmed in CNC
checkpoint | Check currency of Drawings and Approved
checkpoint | Check Alpolic NC 4mm pre-finished sheet is selected.
label | Insert photo of inkjet writing on back of sheet showing product, colour and batch number
checkpoint | Colour and sheet size corresponds with fabrication drawings and nesting.
checkpoint | Sheets are not bent, scratched or damaged before placing on CNC table
checkpoint | No metal filings located on CNC table or sheets prior to placing sheet on bed. Compressed air used to remove any debris
section | Machining
checkpoint | Fluid levels, suction pressures and functions are optimum. Correct tooling is selected and utilized
checkpoint | Ensure route depth thickness is maintained
checkpoint | Panel numbers engraved into back of panel correspond with file numbers and fabrication drawings
checkpoint | Corresponding bracket sizes are written on back of panel as per fabrication drawings
checkpoint | Panels are checked off as machined once machining has terminated
checkpoint | Panels stacked neatly on edge on A frame back to back - face to face.
section | Fabrication
checkpoint | Correct tooling used to fold edges of panels. Panel returns folded neatly and square
checkpoint | Panel cleaned of any excess cutting lubricant or foreign debris. Back of panel is clean. Back of panel be adraided via palm sander with 40 girt sand paper at stiffener locations as per Dowsil recomendations. Locations to be cleaned with clean cloth and isopropanol prior to stiffener application.
checkpoint | Correct sized mill finished aluminum 6063 -T5 'Z' brackets run full length of folds and finish no more than 30mm from edge of panel. Correctly positioned perimeter Z bracket
checkpoint | Dowsil 896 Structural Silicon used to adhere stiffeners to back of panel. Dowsil 896 to be applied continuously to both sides of stiffeners 3mm thick x 12mm wide.
label | Insert images of Dowsil 896 been applied to stifferned as per above detail. ALSO INSERT IMAGE OF DOWSIL 896 BOX / CARTON SHOWING BATCH NUMBER OF PRODUCT.
checkpoint | Z' brackets fixed to folded returns via 4 alumanium rivets at no greater than 300mm centers. Correctly fixed perimeter Z bracket
checkpoint | Correct Mill finished aluminum stiffeners selected 40x20x3 RHS 6060-T5 RHS 6060-T5 where required
checkpoint | Stiffeners cut to length to fit neatly between 'Z' brackets. Neat fitting stiffener in correct position fixed to perimeter 'Z' brackets via 40x3 EA and 4 aluminium rivets
label | Insert photo of completed panel showing stiffener spacings (use tape measure) and general arrangement.
section | Packing
checkpoint | Panels stacked neatly back to back - face to face with protective foam placed between panel faces for transport
checkpoint | Ensure panel numbers are marked off as complete
checkpoint | Panels are secured and wrapped ready for transport
checkpoint | Remove rubbish from work area. Clean workshop for next shift
checklist | ONSITE - Installation of Facade System
section | Pre-constructions and Removal of existing ACP and top hat framing.
checkpoint | Existing condition of surrounding surfaces and finished is documented and photo evidence is obtained and emailed through to Skypanel Management
checkpoint | Removal of sealant in a safe manner, place into bin/bags for disposal and tidy work area.
checkpoint | Removal of composite panels in a safe manner from facade, move to lay down area and secure ensuring work area kept tidy
checkpoint | Removed composite panels stacked neatly and securely strapped within the shipping container in manner suitable for transport
section | Assessment of Structure and Aluminium Framing Installation
checkpoint | Visually check existing structure for condition. Identify any visible cracked welds, missing fixtures and connections and take photo graphic evidence
checkpoint | Identify existing structure. Capture images with tape measure showing type, size, spans, centers and connections at selected locations
label | Insert Photos showing exisitng structure showing member sizing, spans, centers & connections at selected locations and general structure at location.
checkpoint | Install wall wrap ensuring material is lapped and sealed to all adjacent structures
checkpoint | Refer to design documents to ensure tophat span design sizes are not going to be exceeded for the project. 30mm Tophat max span 1000mm at 600 & 750mm spacing
checkpoint | Ensure mill finished aluminium extrusion are utilized as per Jabin Tophat Design
checkpoint | Check fixings types of aluminium subframe into structure: Fixings to be B8 Tek screws.
checkpoint | Ensure aluminium frames setout reflects shop drawing setout are installed plumb, level and are packed to suit existing build out as required with aluminium packers
checkpoint | Prior to commencement of cladding installation: Ensure other services are complete: Ensure all framing requirements are met
label | Insert Photos showing completed aluminum framing with components identified showing spans, tophat sizes, fixings at selected locations
section | Installation of 50mm Volcore Panel
checkpoint | Ensure cladding material is correct by referencing shop drawings - Volcore 50mm Flat panel
checkpoint | Ensure male & female edges of panels are uniform & free from damage
checkpoint | Ensure Volcore is fixed to structure as per Jabin engineering comments
checkpoint | Ensure panels are installed flush and mating correctly
checkpoint | Ensure panel joint consistancy is maintianed
checkpoint | Ensure there are no large gaps between the Volcore panel and the existing/surrounding structure
label | Insert Photos of installed panel, panel widths, junctions, screws and fixing centers at selected locations
section | Installation of 4mm Alpolic NC
checkpoint | Ensure cladding material and colour is correct by referencing shop drawings - Alpolic NC
checkpoint | Ensure appropriate stiffeners are located in back of panel as per Jabin Design documents & Skypanel Shop drawings
checkpoint | Ensure specific stiffener details are achieved as noted in corner situations i.e. High wind corner stiffener support connection
checkpoint | Ensure 3mm aluminum mill finished angles are installed with strucutural silicone to the back of panels to support all corner folds as per Jabin documents
checkpoint | Ensure rivet fixing of Z bracket to panel return edges spaced no more than 300mm apart
checkpoint | Ensure panels are defect free with no scratches and dents
checkpoint | Install cladding panels by mechanically fixing through 'Z' brackets to tophat support framing with 10g B8 screws at nominated fixing centers.
checkpoint | Ensure all panels of the same colour are installed in the same direction as indicated on the protective film
checkpoint | Ensure panel joint consistancy is maintianed
checkpoint | Ensure panels are installed plumb, square and true, and within Skypanel tolerances
checkpoint | Ensure panels are installed in correct positions by checking engraving on back of sheet corresponds with position on shop drawings
label | Insert Photos of installed panel, panel widths, junctions, screws and fixing centers at selected locations
section | Caulking of panels
checkpoint | Ensure backing rod is applied correctly
checkpoint | Ensure Black Dowsil 791 sealant is installed correctly and consistently.
checkpoint | Ensure all penetrations are caulked
checkpoint | Ensure plastic film is removed and caulking and glue residues are properly cleaned from cladding surface
label | Insert photos of sealed panels at selected locations
holdpoint | Hold Point - Approval of caulking required by Superintendent before demobilising from area
checklist-flat | Drawing Upload & Access
checkpoint | Ensure safest access method is selected and utilized, ensuring scaffold is signed off as complete and EWP/plant daily pre starts are undertaken and documented
checkpoint | Check dimensions nominated on shop drawings match the dimensions onsite with regard to existing cladding to be removed and replaced