## Checklist Templates
Id | Type | Name | Values | Prompting Name
8c87b397-48f2-4ba6-8612-7df334d34aee | checklist | Drawing Upload & Access |  | Drawing Upload & Access
faf254a0-3700-4b63-ad5c-17c77f90c148 | checkpoint | Ensure safest access method is selected and utilized, ensuring scaffold is signed off as complete and EWP/plant daily pre starts are undertaken and documented
6078a153-a557-4e62-904b-ab3cdf864d45 | checkpoint | Check dimensions nominated on shop drawings match the dimensions onsite with regard to existing cladding to be removed and replaced
a8f3a2c8-623e-4279-9602-06cc635e40af | checklist | OFFSITE - Fabrication of ALPOLIC NC Checklist |  | OFFSITE - Fabrication of ALPOLIC NC Checklist
b9a1cfcf-256c-476b-aed2-df9c9f765b60 | section | Pre-fabrication
f9129336-0fea-4bb1-9373-8379e94d7e72 | checkpoint | Ensure CNC machine operator daily checklist has been undertaken
95872718-7a71-485e-94dc-65ba61aab4c1 | checkpoint | Nest summary and site drawings provided by programmer, file number printed on paperwork corresponds with file programmed in CNC
8eea4468-cdfc-4539-abc6-69141fe5cd8f | checkpoint | Check currency of Drawings and Approved
06ce7ca5-4f8e-4923-b0c7-6542f84bb904 | checkpoint | Check Alpolic NC 4mm pre-finished sheet is selected.
c6790999-3265-5334-b644-4b4706fb65b9 | note | Insert photo of inkjet writing on back of sheet showing product, colour and batch number
8e9eeff9-6961-4f0c-8040-23e58c22f3af | checkpoint | Colour and sheet size corresponds with fabrication drawings and nesting.
99bf13ae-d9b0-413e-a55d-6b2c1ab2c823 | checkpoint | Sheets are not bent, scratched or damaged before placing on CNC table
fc763a8a-7588-4236-ba54-db22f4ef2c1c | checkpoint | No metal filings located on CNC table or sheets prior to placing sheet on bed. Compressed air used to remove any debris
d77ded55-66cc-4872-8aa4-9a31ba85c1a7 | section | Machining
ad2ca213-eb65-4364-9c88-cac53ffd803f | checkpoint | Fluid levels, suction pressures and functions are optimum. Correct tooling is selected and utilized
ae60f3db-b7a4-4309-bdc7-765a4ef359d3 | checkpoint | Ensure route depth thickness is maintained
bcc4465b-c3ea-4dd3-bfe5-b232137d1250 | checkpoint | Panel numbers engraved into back of panel correspond with file numbers and fabrication drawings
8adaf0f0-d08a-4fbf-b152-655a2e789925 | checkpoint | Corresponding bracket sizes are written on back of panel as per fabrication drawings
0b772b61-8f77-41ba-829d-5fd15c4d7fba | checkpoint | Panels are checked off as machined once machining has terminated
ebc8b6a7-3c4b-4cf3-a788-1424792c66b4 | checkpoint | Panels stacked neatly on edge on A frame back to back - face to face.
e214f025-1709-4714-8895-f746c7218ed0 | section | Fabrication
f3749502-8615-4986-a51a-5ca569178b6d | checkpoint | Correct tooling used to fold edges of panels. Panel returns folded neatly and square
7eb221c9-a93c-4723-8c6c-a2f503fd5f76 | checkpoint | Panel cleaned of any excess cutting lubricant or foreign debris. Back of panel is clean. Back of panel be adraided via palm sander with 40 grit sandpaper at stiffener locations as per Dowsil recomendations. Locations to be cleaned with clean cloth and isopropanol prior to stiffener application.
520229b2-a98e-4783-97c4-1fe4b0e9482e | checkpoint | Correct sized mill finished aluminum 6063 -T5 'Z' brackets run full length of folds and finish no more than 30mm from edge of panel. Correctly positioned perimeter Z bracket
4d2fe2dc-962c-46c9-8ca5-3b5a25b8f484 | checkpoint | Dowsil 896 Structural Silicon used to adhere stiffeners to back of panel. Dowsil 896 to be applied continuously to both sides of stiffeners 3mm thick x 12mm wide.
0caec881-0928-5efb-981a-6f493dec3127 | note | Insert images of Dowsil 896 been applied to stifferned as per above detail. ALSO INSERT IMAGE OF DOWSIL 896 BOX / CARTON SHOWING BATCH NUMBER OF PRODUCT.
7f3b2952-fb7e-40d7-a177-7601059778e6 | checkpoint | Z' brackets fixed to folded returns via 4 alumanium rivets at no greater than 300mm centers. Correctly fixed perimeter Z bracket
df4ff5a5-abce-435c-92b2-437fcb6063fd | checkpoint | Correct Mill finished aluminum stiffeners selected 40x20x3 RHS 6060-T5 RHS 6060-T5 where required
9b6641af-9629-4b3b-867f-04154e14b790 | checkpoint | Stiffeners cut to length to fit neatly between 'Z' brackets. Neat fitting stiffener in correct position fixed to perimeter 'Z' brackets via 40x3 EA and 4 aluminium rivets
60fb5d74-1679-5f74-b5d0-f0c7dfce2f3f | note | Insert photo of completed panel showing stiffener spacings (use tape measure) and general arrangement.
428087dc-cfc8-4944-8a59-3017ef6d8df3 | section | Packing
84b5f51e-ae2b-47a5-a4c0-01b1d96a3a8c | checkpoint | Panels stacked neatly back to back - face to face with protective foam placed between panel faces for transport
77e8ad49-328d-4e60-b131-7014379a91fd | checkpoint | Ensure panel numbers are marked off as complete
3804e7d7-7097-4491-8551-6c74bc2e40d5 | checkpoint | Panels are secured and wrapped ready for transport
3a458c89-8e0c-4246-b506-8a4f506b2145 | checkpoint | Remove rubbish from work area. Clean workshop for next shift
81e7d413-aae7-4572-a116-824efcd35755 | checklist | ONSITE - Installation of Facade System |  | ONSITE - Installation of Facade System
daa67b8f-c727-4a25-9d97-9797c699b992 | section | Pre-constructions and Removal of existing ACP and top hat framing.
e48f118b-c88b-4f5e-a491-487bd51c668d | checkpoint | Existing condition of surrounding surfaces and finished is documented and photo evidence is obtained and emailed through to Skypanel Management
34333509-4742-4ee0-b90c-452fdb63b509 | checkpoint | Removal of sealant in a safe manner, place into bin/bags for disposal and tidy work area.
f70a600a-e2f9-477b-ad4d-597903340718 | checkpoint | Removal of composite panels in a safe manner from facade, move to lay down area and secure ensuring work area kept tidy
c41cccc9-3f06-4212-a554-cb38a42cbd04 | checkpoint | Removed composite panels stacked neatly and securely strapped within the shipping container in manner suitable for transport
8770dc59-b1fc-4b68-b7fc-25a34584b5bb | section | Assessment of Structure and Aluminium Framing Installation
bce7cc78-3d9d-467b-8965-0d6588a20c60 | checkpoint | Visually check existing structure for condition. Identify any visible cracked welds, missing fixtures and connections and take photo graphic evidence
b57475d0-176b-4e10-b01b-9de85ffc304d | checkpoint | Identify existing structure. Capture images with tape measure showing type, size, spans, centers and connections at selected locations
3fc44d66-e15f-5db5-8eda-c758bc6a0c5d | note | Insert Photos showing existing structure showing member sizing, spans, centers & connections at selected locations and general structure at location.
75651f13-0d7b-42c1-80e1-c24f16d01593 | checkpoint | Install wall wrap ensuring material is lapped and sealed to all adjacent structures
8a4881cf-5fb2-474c-96ff-ca50cf155874 | checkpoint | Refer to design documents to ensure tophat span design sizes are not going to be exceeded for the project. 30mm Tophat max span 1000mm at 600 & 750mm spacing
b5d68c20-d678-4947-ac71-e3eb16623616 | checkpoint | Ensure mill finished aluminium extrusion are utilized as per Jabin Tophat Design
7369b8da-e61d-4583-8587-f0d16fab5e4c | checkpoint | Check fixings types of aluminium subframe into structure: Fixings to be B8 Tek screws.
11513048-34d2-4591-8d48-b6a875e3ec95 | checkpoint | Ensure aluminium frames setout reflects shop drawing setout are installed plumb, level and are packed to suit existing build out as required with aluminium packers
45e2e52e-7623-470c-8a2c-bbfd310db052 | checkpoint | Prior to commencement of cladding installation: Ensure other services are complete: Ensure all framing requirements are met
1bcc2c64-de81-5599-9194-166a45717fa7 | note | Insert Photos showing completed aluminum framing with components identified showing spans, tophat sizes, fixings at selected locations
3ee80cd9-30c7-4993-a579-dadc90ab92a4 | section | Installation of 50mm Volcore Panel
303edba8-7695-4bf7-99a2-80d4e057f67b | checkpoint | Ensure cladding material is correct by referencing shop drawings - Volcore 50mm Flat panel
9dc9f01a-e4e4-4ff1-9a72-b4a565c5cba2 | checkpoint | Ensure male & female edges of panels are uniform & free from damage
aa23ef8b-f68c-489a-a189-02b8d1b97800 | checkpoint | Ensure Volcore is fixed to structure as per Jabin engineering comments
e3da4bfe-c23d-4a3c-a888-96bf3a2f24ee | checkpoint | Ensure panels are installed flush and mating correctly
584f6544-a530-472d-9dd6-dad2fd9b17c4 | checkpoint | Ensure panel joint consistency is maintained
015dd7fa-261e-499b-8bc1-804b9e6a2d31 | checkpoint | Ensure there are no large gaps between the Volcore panel and the existing/surrounding structure
ae8fd73e-70b7-5c9d-87f4-dbb595e35fc4 | note | Insert Photos of installed panel, panel widths, junctions, 12ga bi metal screws and fixing centers at selected locations
a0ea8cc9-0111-4a7f-8a5c-2a73d22b2889 | section | Installation of 3mm Mondoclad Cladding
bbb24568-b6c7-492d-903f-b0329d33b034 | checkpoint | Ensure cladding material and colour is correct by referencing shop drawings - Alpolic NC
93bae950-8f22-4794-8920-9dac671b7633 | checkpoint | Ensure appropriate stiffeners are located in back of panel as per Jabin Design documents & Skypanel Shop drawings
0ff6243c-54ce-43fe-a903-0f7547aff0df | checkpoint | Ensure specific stiffener details are achieved as noted in corner situations i.e. High wind corner stiffener support connection
932efbe6-b9ae-4f3c-ac4c-bc47ef08cbe8 | checkpoint | Ensure 3mm aluminum mill finished angles are installed with structural silicone to the back of panels to support all corner folds as per Jabin documents
48b580c3-b330-42a0-ab5c-948fed4c4807 | checkpoint | Ensure rivet fixing of Z bracket to panel return edges spaced no more than 300mm apart
0333cbd8-fa71-46ae-ac70-c4783d0997f1 | checkpoint | Ensure panels are defect free with no scratches and dents
84808edd-f5a1-46c8-9867-8440fe27f01c | checkpoint | Install cladding panels by mechanically fixing through 'Z' brackets to tophat support framing with 10g B8 screws at nominated fixing centers.
0a04e235-542d-4c55-9b12-8c5a5889b6c3 | checkpoint | Ensure all panels of the same colour are installed in the same direction as indicated on the protective film
16893132-c236-4f5b-b4d8-f53a6476a7b2 | checkpoint | Ensure panel joint consistency is maintained
61fb9221-9820-46f3-9017-e4910741199d | checkpoint | Ensure panels are installed plumb, square and true, and within Skypanel tolerances
eae5b3b9-e08d-456a-b600-ea7e3b52e61c | checkpoint | Ensure panels are installed in correct positions by checking engraving on back of sheet corresponds with position on shop drawings
563f5f82-dfa2-5c72-8292-d2ccdd09f453 | note | Insert Photos of installed panel, panel widths, junctions, screws and fixing centers at selected locations
b2e10d6e-62ef-4401-96fe-a6fb91465bcd | section | Caulking of panels
0319b69d-e8bf-4962-8cfe-145edf9e05df | checkpoint | Ensure backing rod is applied correctly
26dbe950-15b7-4bc2-9512-aef52bd3963a | checkpoint | Ensure Black Dowsil 791 sealant is installed correctly and consistently.
23aa13ef-e724-44e4-bbca-33486a98a6b0 | checkpoint | Ensure all penetrations are caulked
e9a1a3ff-c9db-4c0d-b2e5-57669fa35249 | checkpoint | Ensure plastic film is removed and caulking and glue residues are properly cleaned from cladding surface
53538620-2b4b-53db-86bb-8542408c2884 | note | Insert photos of sealed panels at selected locations
0cf48893-2cc7-4878-a95b-98519886a0e4 | signoff | Hold Point - Approval of caulking required by Superintendent before demobilising from area