## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
81e7d413-aae7-4572-a116-824efcd35755 | checklist | ONSITE - Installation of Facade System |  | ONSITE - Installation of Facade System
daa67b8f-c727-4a25-9d97-9797c699b992 | section | Pre-constructions and Removal of existing ACP and top hat framing.
e48f118b-c88b-4f5e-a491-487bd51c668d | checkpoint | Existing condition of surrounding surfaces and finished is documented and photo evidence is obtained and emailed through to Skypanel Management
34333509-4742-4ee0-b90c-452fdb63b509 | checkpoint | Removal of sealant in a safe manner, place into bin/bags for disposal and tidy work area.
f70a600a-e2f9-477b-ad4d-597903340718 | checkpoint | Removal of composite panels in a safe manner from facade, move to lay down area and secure ensuring work area kept tidy
c41cccc9-3f06-4212-a554-cb38a42cbd04 | checkpoint | Removed composite panels stacked neatly and securely strapped within the shipping container in manner suitable for transport
8770dc59-b1fc-4b68-b7fc-25a34584b5bb | section | Assessment of Structure and Aluminium Framing Installation
bce7cc78-3d9d-467b-8965-0d6588a20c60 | checkpoint | Visually check existing structure for condition. Identify any visible cracked welds, missing fixtures and connections and take photo graphic evidence
b57475d0-176b-4e10-b01b-9de85ffc304d | checkpoint | Identify existing structure. Capture images with tape measure showing type, size, spans, centers and connections at selected locations
3fc44d66-e15f-5db5-8eda-c758bc6a0c5d | note | Insert Photos showing existing structure showing member sizing, spans, centers & connections at selected locations and general structure at location.
75651f13-0d7b-42c1-80e1-c24f16d01593 | checkpoint | Install wall wrap ensuring material is lapped and sealed to all adjacent structures
8a4881cf-5fb2-474c-96ff-ca50cf155874 | checkpoint | Refer to design documents to ensure tophat span design sizes are not going to be exceeded for the project. 30mm Tophat max span 1000mm at 600 & 750mm spacing
b5d68c20-d678-4947-ac71-e3eb16623616 | checkpoint | Ensure mill finished aluminium extrusion are utilized as per Jabin Tophat Design
7369b8da-e61d-4583-8587-f0d16fab5e4c | checkpoint | Check fixings types of aluminium subframe into structure: Fixings to be B8 Tek screws.
11513048-34d2-4591-8d48-b6a875e3ec95 | checkpoint | Ensure aluminium frames setout reflects shop drawing setout are installed plumb, level and are packed to suit existing build out as required with aluminium packers
45e2e52e-7623-470c-8a2c-bbfd310db052 | checkpoint | Prior to commencement of cladding installation: Ensure other services are complete: Ensure all framing requirements are met
1bcc2c64-de81-5599-9194-166a45717fa7 | note | Insert Photos showing completed aluminum framing with components identified showing spans, tophat sizes, fixings at selected locations
3ee80cd9-30c7-4993-a579-dadc90ab92a4 | section | Installation of 50mm Volcore Panel
303edba8-7695-4bf7-99a2-80d4e057f67b | checkpoint | Ensure cladding material is correct by referencing shop drawings - Volcore 50mm Flat panel
9dc9f01a-e4e4-4ff1-9a72-b4a565c5cba2 | checkpoint | Ensure male & female edges of panels are uniform & free from damage
aa23ef8b-f68c-489a-a189-02b8d1b97800 | checkpoint | Ensure Volcore is fixed to structure as per Jabin engineering comments
e3da4bfe-c23d-4a3c-a888-96bf3a2f24ee | checkpoint | Ensure panels are installed flush and mating correctly
584f6544-a530-472d-9dd6-dad2fd9b17c4 | checkpoint | Ensure panel joint consistency is maintained
015dd7fa-261e-499b-8bc1-804b9e6a2d31 | checkpoint | Ensure there are no large gaps between the Volcore panel and the existing/surrounding structure
ae8fd73e-70b7-5c9d-87f4-dbb595e35fc4 | note | Insert Photos of installed panel, panel widths, junctions, 12ga bi metal screws and fixing centers at selected locations
a0ea8cc9-0111-4a7f-8a5c-2a73d22b2889 | section | Installation of 4mm Alpolic NC
bbb24568-b6c7-492d-903f-b0329d33b034 | checkpoint | Ensure cladding material and colour is correct by referencing shop drawings - Alpolic NC
93bae950-8f22-4794-8920-9dac671b7633 | checkpoint | Ensure appropriate stiffeners are located in back of panel as per Jabin Design documents & Skypanel Shop drawings
0ff6243c-54ce-43fe-a903-0f7547aff0df | checkpoint | Ensure specific stiffener details are achieved as noted in corner situations i.e. High wind corner stiffener support connection
932efbe6-b9ae-4f3c-ac4c-bc47ef08cbe8 | checkpoint | Ensure 3mm aluminum mill finished angles are installed with structural silicone to the back of panels to support all corner folds as per Jabin documents
48b580c3-b330-42a0-ab5c-948fed4c4807 | checkpoint | Ensure rivet fixing of Z bracket to panel return edges spaced no more than 300mm apart
0333cbd8-fa71-46ae-ac70-c4783d0997f1 | checkpoint | Ensure panels are defect free with no scratches and dents
84808edd-f5a1-46c8-9867-8440fe27f01c | checkpoint | Install cladding panels by mechanically fixing through 'Z' brackets to tophat support framing with 10g B8 screws at nominated fixing centers.
0a04e235-542d-4c55-9b12-8c5a5889b6c3 | checkpoint | Ensure all panels of the same colour are installed in the same direction as indicated on the protective film
16893132-c236-4f5b-b4d8-f53a6476a7b2 | checkpoint | Ensure panel joint consistency is maintained
61fb9221-9820-46f3-9017-e4910741199d | checkpoint | Ensure panels are installed plumb, square and true, and within Skypanel tolerances
eae5b3b9-e08d-456a-b600-ea7e3b52e61c | checkpoint | Ensure panels are installed in correct positions by checking engraving on back of sheet corresponds with position on shop drawings
563f5f82-dfa2-5c72-8292-d2ccdd09f453 | note | Insert Photos of installed panel, panel widths, junctions, screws and fixing centers at selected locations
b2e10d6e-62ef-4401-96fe-a6fb91465bcd | section | Caulking of panels
0319b69d-e8bf-4962-8cfe-145edf9e05df | checkpoint | Ensure backing rod is applied correctly
26dbe950-15b7-4bc2-9512-aef52bd3963a | checkpoint | Ensure Black Dowsil 791 sealant is installed correctly and consistently.
23aa13ef-e724-44e4-bbca-33486a98a6b0 | checkpoint | Ensure all penetrations are caulked
e9a1a3ff-c9db-4c0d-b2e5-57669fa35249 | checkpoint | Ensure plastic film is removed and caulking and glue residues are properly cleaned from cladding surface
53538620-2b4b-53db-86bb-8542408c2884 | note | Insert photos of sealed panels at selected locations
0cf48893-2cc7-4878-a95b-98519886a0e4 | signoff | Hold Point - Approval of caulking required by Superintendent before demobilising from area