## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | 30.01 - Dense Graded Asphalt | itp
| section | Details
| checkpoint | Submission of Asphalt Quality Plan (7 days)
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Milestone
| note | Reference - MRTS30 Cl 5.2
| signoff | HOLD POINT
| checkpoint | Recommencement of production after non conforming Tensile Strength Ratio
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - HOLD POINT
| note | Reference - MRTS30 Cl 7.2.5
| checkpoint | Submission of Asphalt Mix Design Certificate (7 days)
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Milestone
| note | Reference - MRTS30 Cl 7.3.3
| checkpoint | Incorporation of asphalt into the Works
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - HOLD POINT
| note | Reference - MRTS30 Cl 7.4.1
| signoff | HOLD POINT
| checkpoint | Acceptance of a non conforming or nonstandard mix design for incorporation into the Works
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - HOLD POINT
| note | Reference - MRTS30 Cl 7.4.1
| signoff | HOLD POINT
| checkpoint | Approval to place asphalt over weak substrate substrate
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Witness Point
| note | Reference - MRTS30 Cl 8.2.2
| signoff | HOLD POINT
| checkpoint | Proof rolling of substrate
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Witness Point
| note | Reference - MRTS30 Cl 8.2.2
| checkpoint | Mark out of cracks to be filled substrate
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Witness Point
| note | Reference - MRTS30 Cl 8.2.3
| checkpoint | Marking out the areas on which strain alleviating fabric strips are to be applied
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Witness Point
| note | Reference - MRTS30 Cl 8.2.4
| checkpoint | Approval to place asphalt at a nonconforming layer thickness
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Witness Point
| note | Reference - MRTS30 Cl 8.6.2
| signoff | HOLD POINT
| checkpoint | Approval to place asphalt at a nonconforming pavement temperature
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Witness Point
| note | Reference - MRTS30 Cl 8.7
| note | HOLD POINT
| checkpoint | Placing of the nominated mix (after placement trial)
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Witness Point
| note | Reference - MRTS30 Cl 8.11
| note | HOLD POINT
| checkpoint | Final Verification
| note | Project Manager Verify that the Above has been Constructed according to Specification
| textbox | Print Name:
| date | Date:
| note | Client Verify that the Above has been Constructed according to Specification
| textbox | Print Name:
| date | Date:
| signoff | Signature