## ITP Cover Page
Noise Wall 1 - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 008 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 008
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | For Approval
ITP Description: |  |  | Noise Wall 1 |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-STR (SET)
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project Specification: 18.6 - Noise walls
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 17/07/2024 |  | Cordelia Girdler-Brown | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | For Approval | 2024-07-30 |  | WSP | [5 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Chris Benson | [5 empty] | Downer PM |  | Chris Benson
Downer QM |  | Cordelia Girdler-Brown | [5 empty] | Downer QM |  | Cordelia Girdler-Brown
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body_BC
Noise Wall 1 - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 008 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
1.1 | MATERIAL TESTING - STRUCTURAL STEEL
1.1.1 | All metalwork to be approved by the engineer after fabrication | Hot dip galvanised to standard hdg 900 | Engineers Approval | PS 18.6.3 | Visual inspection | Prior to construction | HP | ENG
1.1.2 | Hot rolled steel plates | All hot rolled steel sections shall be grade 300 complying with AS/NZS 3679: part 1 | Grade 300 - AS/NZS 3679 Part 1 | PS 18.6.3 | Supplier data sheet/ Mill certs | Prior to construction | WP | SE
1.1.3 | Cold formed steel plates | All cold formed steel sections shall be grade 350lo complying with AS/NZS 1163 | Grade 350 lo - AS/NZS 1163 | PS 18.6.3 | Supplier data sheet / Mill certs | Prior to construction | WP | SE
1.1.4 | Mild Steel plates | All mild steel plate shall be hot rolled grade 350 complying with AS/NZS3678 (AS/NZS 3678-350) | Grade 350 - AS/NZS 3678 (AS/NZS 3678-350) | PS 18.6.3 | Supplier data sheet / Mill certs | Prior to construction | WP | SE
1.1.5 | Round bar/rod | To be grade 300 to AS/NZS 4671 | Grade 300 - AS/NZS 4671 | PS 18.6.3 | Supplier data sheet / Mill certs | Prior to construction | WP | SE
1.1.6 | Bolts and treaded rods | All bolts and threaded rods shall be category 4.6/s to AS 1252 | Category 4.6/s to AS 1252 | PS 18.6.3 | Supplier data sheet / Mill certs | Prior to construction | WP | SE
1.1.7 | Rough or sharp edges | All rough or sharp edges or protrusions to be buffed smooth | All rough or sharp edges or protrusions to be buffed smooth | PS 18.6.3 | Visual inspection | During construction | WP | SE
1.1.8 | Epoxy Coating to the Steel column | High build epoxy paint all round the UC column concrete interface | all columns must be coted with epoxy at steel and concrete interface | WSP-DR-STR-0306 | Visual inspection | During construction | WP | ENG
1.1.9 | Butynol sheeting - membrane | Butynol or any similar approved shall be used between timber and steel | Membrane seal | PS18.6.3 | Supplier data sheet and Engineers approval | Prior to construction | HP | ENG
1.2 | TIMBER
1.2.1 | Timber | Timber shall be VS8 grade radiate pine complyng with NZS 3603 and graded to NZS 3631 | VS8 Grade radiate pine with a Timber strength - 11.7MPa | PS 18.6.3 | Supplier data sheet | Prior to construction | I | SE
1.2.2 | Timber - in contact with the ground | Round or rough sawn piles in contact with the ground to be H5 | H5 | PS 18.6.3 | Supplier data sheet | Prior to construction | I | SE
1.2.3 | Timber - not in contact wth the ground | Rough sawn timber not in contact with the ground to be H3.2 | H3.2 | PS 18.6.3 | Supplier data sheet | Prior to construction | I | SE
1.2.4 | All timber components of noise wall | Timber treatment shall comply with requirements of the NZ Timber Preservation Council incorporating - MP 3640. All timber shall be branded to NZS3640:2003 and must be treated not less than 2 months prior to use. | MP 3640 NZS3640:2003 | PS 18.6.3 | Supplier data sheet | Prior to construction | I | SE |  |  |  |  | Are both these items required as they are both mentioning a treatment however noting two different standards?
1.2.5 | All timber components of noise wall | Timber shall have a moisture content less than 18% at time of installation to avoid excessive shrinkage effects. | Timber shall have a moisture content less than 18% at time of installation to avoid excessive shrinkage effects. | PS 18.6.3 | Supplier data sheet | Prior to construction | I | SE
1.2.6 | All timber components of noise wall | Treat all cut surfaces with clear zinc naphthenate preservative and in accordance with NZ 3602. | Treat all cut surfaces with clear zinc naphthenate preservative and in accordance with NZ 3602. | PS 18.6.3 | Supplier data sheet | Prior to construction | I | SE
1.2.7 | Galvanised bolts | All galvanised bolts in contact with H5 treated timber shall be protected using CP grease in pre-greased holes | All galvanised bolts in contact with H5 treated timber shall be protected using CP grease in pre-greased holes | PS 18.6.3 | Supplier data sheet | Prior to construction | I | SE
1.3 | FIXINGS
1.3.1 | FH Nails | General structural use 75mm x 3.15mm FH nails . All nails shall be flat headed, unless otherwise shown, hot dip galvanised and fully driven | 75mm x 3.15mm FH Nails | PS 18.6.3 | Delivery dockets and supplier data sheet | Prior to construction | I | SE
1.3.2 | Bolts | Bolts shall be M12 hot dip galvanised engineers bolts fitted with 50x50x5 galvanised square washers both ends. Washers for coach screws shall be provided in accordance with NZS 3604 | M12 hot dipped, 50x50x5 galvanised square washers | PS 18.6.3 | Delivery dockets and supplier data sheet | Prior to construction | I | SE
1.3.3 | Bolts within 100mm of ground | Bolts within 100mm of ground to be stainless steel. | Stainless steel bolts | PS 18.6.3 | Delivery dockets and supplier data sheet | Prior to construction | I | SE
1.3.4 | Coach screws | All screws shall be hot dip galvanised and screw fixings shall be pre-bored. | Hot dip galvanised | PS 18.6.3 | Delivery dockets and supplier data sheet | Prior to construction | I | SE
SECTION 2 – CONSTRUCTION ACTIVITY
2.1 | NOISE WALL CONSTRUCTION
2.1.1 | Setting out of Noise wall 1 all Posts | Setting out to follow design coordinates and levels within tolerance as specified in PS 18.5.7 section (e). | Engineers Approval | PS 18.6.1 | Visual inspection | Engineers Approval | WP | ENG
2.1.2 | Geo Technical investigation on each post holes | Holes are to be 400mm dia and 2.8m deep. Shear vane testing to be completed to a strength of 60kpa | Shear vane strength of 60kpa | PS 18.6.2 | Shear vane test report/Visual inspection | Engineers Approval | HP | ENG
2.1.3 | Noise wall footing concrete | 17.5 MPA Concrete | 28 days concrete strength test of 17.5MPA | PS 18.6.2 | Concrete Delivery Docket | During Construction | I | SE
2.1.4 | Installing Wooden Railings | with sufficient embeddment of nails and connecting details as per drawings |  | PS 18.6.3 | Noise wall Checksheet | During Construction | I | SE
SECTION 3 – POST CONSTRUCTION ( HANDOVER)
3.1 | As-builts | As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets. | All changes to design need to be captured on the noise wall drawing set |  | Redpen Markup | During construction and after finishing | WP | SE

## Sheet1
1.2 | MATERIAL TESTING - CONCRETE WORKS
1.2.1 | Noise wall footing | All materials and workmanship shall be in accordance with NZS3109 | Concrete strength : 17.5MPA | PS 18.6.3 | Approved concrete mix design - 17Mpa | Prior to construction | HP | ENG

## concrete inspection checklist
Quality Control Checklist- Concrete Inspection Record
Project: |  |  |  |  | Project No.
Structure: |  |  |  |  | Lot No.
Element |  |  |  |  | Concrete Grade (MPA)
Drawing No. |  |  |  |  | Revision
Date |  |  |  |  | Concrete Volume (m3)
Formwork | Checked (DNZ/WSP) |  | Acceptance |  | Comments
| initial | Date | Y | N
Correct dimensions
Formed surfaces straight
Cleaned and oiled
Embedded items located
Adequately braced and suported (formwork more than 600mm height requires sighoff by PE)
Corner fillet installed
Special
Reinforcement | Checked (DNZ/WSP) |  | Acceptance |  | Comments
| initial | Date | Y | N
Size/position/spacing
Starters/dowels correctly located
Lap location and lengths
Rigidity and cover acceptable
clean surfaces
linkage bars (if applicable)
Special
Joints | Checked (DNZ/WSP) |  | Acceptance |  | Comments
| initial | Date | Y | N
Type
Location/Position
Preparation
False work and support | Checked (DNZ/WSP) |  | Acceptance |  | Comments
| initial | Date | Y | N
founding and sole plates
Alignment (vertical, horizontal)
Bracing
Soffit release clearance
Pre-Pour Checks Sign Off
Site/Project Engineer
Name: | Date |  | Time |  | Signature:
Designers Representative (MSQA)
Name: | Date |  | Time |  | Signature:
Wet Concrete Check | Checked (DNZ/WSP) |  | Acceptance |  | Comments
| initial | Date | Y | N
Correct Mix delivered
Slump/Flow Target
Test Cylinders Taken: 1 set per 50m3
Concrete Vibrated
Finish Surface
Surface to required finish ie F3,F4
Retarder/Curing applied
Concrete Supply Dockets Collected
Post Concrete Inspection | Checked (DNZ/WSP) |  | Acceptance |  | Comments
| initial | Date | Y | N
Curing Carried out acceptable
Sufficient strength for striking formwork
Preparation of construction Joints
Defects- Repaired/Rectified
The above works have been inspected and are considered compliant with the drawings, specifications and instructions.
Post-Pour Checks Sign Off
Site/Project Engineer
Name: | Date |  | Time |  | Signature:
Designers Representative (MSQA)
Name: | Date |  | Time |  | Signature: