## ITP Cover Page
Fencing Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 016 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 016
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Draft
ITP Description: |  |  | Fence |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-UDL
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification:
Quality Specified:
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-07-29 | [7 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON |  |  |  |  | 2024-07-17 | Downer PM |  | CHRIS BENSON
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 2024-07-17 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Fencing Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 016 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.1 | GENERAL
1.1.1 | Extent of Line Setout | Ensure line and level of Fences has been marked out and agreed with Engineer in accordance with fence drawings. | Engineers Approval | Design Drawings | ITP Sign Off | Prior to Construction & Every Revision of IFC Drawings/Data. | M | ENG
1.1.2 | Existing Fences system | Confirmation of existing Fence network. | Survey Information's | Appendix V | Survey data | Prior to Construction | HP | ENG
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2.1 | MATERIAL TESTING
2.1.1 | Timber (Rails/palings/battens) Posts | Treatment | H4 H5 if touching ground otherwise H4 | PS 27.5.5 NZS3607:1989 | Delivery docket | Prior Construction | M | SE
2.1.2 | Steel (Wire/Metal fence) | Standard galvanised high tensile steel wire | 2.4mm 12 gauge | PS 27.5.1 PS 22.5.6 | Delivery Docket | Prior Construction | M | SE
2.1.3 | Chain Link Net | Standard galvanised high tensile steel wire | 50*50 Max grid size Powder coated black finish | PS 14.6.1 | Delivery Docket | Prior Construction | M | SE
2.1.4 | Material (Fixings/fasteners/hinges/chains) | Jointing | Hot dip galvanised | PS 27.5.1 | Delivery Docket | Prior Construction | M | SE
SECTION 3 – CONSTRUCTION ACTIVITY
3.1 | SECURITY FENCE
3.1.1 | Wetlands Fence | Install around the wetland Black powder coated finish | 1.5M high Hot dip Galvanised | PS 2-32735.02-WSP-DR-UDL-0407 PS 27.5.1 PS 27.5.2 | Delivery docket | During installation | M | SE
3.2 | TIMBER BOUNDARY FENCE
3.2.1 | Timber fence | Preserve timber exposed faces Post imbedded in ground | 1.8m high Exposed timber faces neatly protected with 2 coats of timber preservative (Metalex) 1800mm in ground with 17.5MPa concrete Minimum 100mm extend around the post | PS 27.5.5 | Delivery docket | During installation | M | SE
3.3 | POST AND WIRE FENCE
3.3.1 | Post and Wire Farm Fence | 8 Steel wire Timber post located at max 5m centre and securely rammed Battens affixed to wire and timber evenly spaces | Wire and ground distance <125mm Top wire to > 1m from ground top of post > 50mm top wire Wires not attached on road side First 3 wire separation 125mm Min 3 battens between posts | PS- 27.5.6 NZS 2566 | Visual inspection | During Construction | M | SE
3.3.2 | Strainer Posts | At new and existing fence terminations At each corner distance between corner and/or termination strainer exceeds 200m | Double footing and tight wire secured to the post using 4mm wire | PS 22.5.6.b | Visual inspection | During Construction | M | SE
3.4 | FALL PROTECTION FENCE
3.4.1 | Chain Link fence | As per drawings Headwall and Wingwall fencing Secured with posts and top rails Spacing between two post must be equal | Tie wire on every second diamond Spacing<2400mm | PS 2-32735.02-WSP-DR-UDL-0407 | Visual inspection | During Construction | M | SE
SECTION 4 – HANDOVER
4.1 | As-built
4.1.1 | Survey As-Builts | Quality Check on New Works based on the tolerances in RITS | Meets spec and thickness requirements as per drawings | PS-21.7.7 | Red pen markup only | Post works completion of a lot | H | ENG/PE