## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-008 ITP Noisewall 1 Rev 1 | itp |  |  |  |  | DN1210-008 ITP Noisewall 1 Rev 1
section | SECTION 1 – PRE-CONSTRUCTION - MATERIAL, PERSONNEL & THIRD PARTY APPROVALS
checkpoint | 1.1.1 - All metalwork to be approved by the engineer after fabrication
label | Detail - Hot dip galvanised to standard hdg 900
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Hot rolled steel plates
label | Detail - All hot rolled steel sections shall be grade 300 complying with AS/NZS 3679: part 1
label | Acceptance / Conformance Criteria - Grade 300 - AS/NZS 3679 Part 1
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet/ Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - SE
checkpoint | 1.1.3 - Cold formed steel plates
label | Detail - All cold formed steel sections shall be grade 350lo complying with AS/NZS 1163
label | Acceptance / Conformance Criteria - Grade 350 lo - AS/NZS 1163
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet / Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - SE
checkpoint | 1.1.4 - Mild Steel plates
label | Detail - All mild steel plate shall be hot rolled grade 350 complying with AS/NZS3678 (AS/NZS 3678-350)
label | Acceptance / Conformance Criteria - Grade 350 - AS/NZS 3678 (AS/NZS 3678-350)
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet / Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - SE
checkpoint | 1.1.5 - Round bar/rod
label | Detail - To be grade 300 to AS/NZS 4671
label | Acceptance / Conformance Criteria - Grade 300 - AS/NZS 4671
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet / Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - SE
checkpoint | 1.1.6 - Bolts and treaded rods
label | Detail - All bolts and threaded rods shall be category 4.6/s to AS 1252
label | Acceptance / Conformance Criteria - Category 4.6/s to AS 1252
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet / Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - SE
checkpoint | 1.1.7 - Rough or sharp edges
label | Detail - All rough or sharp edges or protrusions to be buffed smooth
label | Acceptance / Conformance Criteria - All rough or sharp edges or protrusions to be buffed smooth
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - SE
checkpoint | 1.1.8 - Epoxy Coating to the Steel column
label | Detail - High build epoxy paint all round the UC column concrete interface
label | Acceptance / Conformance Criteria - all columns must be coted with epoxy at steel and concrete interface
label | Standard / Specification - WSP-DR-STR-0306
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 1.1.9 - Butynol sheeting - membrane
label | Detail - Butynol or any similar approved shall be used between timber and steel
label | Acceptance / Conformance Criteria - Membrane seal
label | Standard / Specification - PS18.6.3
label | Verifying Document - Supplier data sheet and Engineers approval
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.1 - Timber
label | Detail - Timber shall be VS8 grade radiate pine complyng with NZS 3603 and graded to NZS 3631
label | Acceptance / Conformance Criteria - VS8 Grade radiate pine with a Timber strength - 11.7MPa
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.2.2 - Timber - in contact with the ground
label | Detail - Round or rough sawn piles in contact with the ground to be H5
label | Acceptance / Conformance Criteria - H5
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.2.3 - Timber - not in contact wth the ground
label | Detail - Rough sawn timber not in contact with the ground to be H3.2
label | Acceptance / Conformance Criteria - H3.2
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.2.4 - All timber components of noise wall
label | Detail - Timber treatment shall comply with requirements of the NZ Timber Preservation Council incorporating - MP 3640. All timber shall be branded to NZS3640:2003 and must be treated not less than 2 months prior to use.
label | Acceptance / Conformance Criteria - MP 3640 NZS3640:2003
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.2.5 - All timber components of noise wall
label | Detail - Timber shall have a moisture content less than 18% at time of installation to avoid excessive shrinkage effects.
label | Acceptance / Conformance Criteria - Timber shall have a moisture content less than 18% at time of installation to avoid excessive shrinkage effects.
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.2.6 - All timber components of noise wall
label | Detail - Treat all cut surfaces with clear zinc naphthenate preservative and in accordance with NZ 3602.
label | Acceptance / Conformance Criteria - Treat all cut surfaces with clear zinc naphthenate preservative and in accordance with NZ 3602.
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.2.7 - Galvanised bolts
label | Detail - All galvanised bolts in contact with H5 treated timber shall be protected using CP grease in pre-greased holes
label | Acceptance / Conformance Criteria - All galvanised bolts in contact with H5 treated timber shall be protected using CP grease in pre-greased holes
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.3.1 - FH Nails
label | Detail - General structural use 75mm x 3.15mm FH nails . All nails shall be flat headed, unless otherwise shown, hot dip galvanised and fully driven
label | Acceptance / Conformance Criteria - 75mm x 3.15mm FH Nails
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.3.2 - Bolts
label | Detail - Bolts shall be M12 hot dip galvanised engineers bolts fitted with 50x50x5 galvanised square washers both ends. Washers for coach screws shall be provided in accordance with NZS 3604
label | Acceptance / Conformance Criteria - M12 hot dipped, 50x50x5 galvanised square washers
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.3.3 - Bolts within 100mm of ground
label | Detail - Bolts within 100mm of ground to be stainless steel.
label | Acceptance / Conformance Criteria - Stainless steel bolts
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.3.4 - Coach screws
label | Detail - All screws shall be hot dip galvanised and screw fixings shall be pre-bored.
label | Acceptance / Conformance Criteria - Hot dip galvanised
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 2 – CONSTRUCTION ACTIVITY
checkpoint | 2.1.1 - Setting out of Noise wall 1 all Posts
label | Detail - Setting out to follow design coordinates and levels within tolerance as specified in PS 18.5.7 section (e).
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 18.6.1
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 2.1.2 - Geo Technical investigation on each post holes
label | Detail - Holes are to be 400mm dia and 2.8m deep. Shear vane testing to be completed to a strength of 60kpa
label | Acceptance / Conformance Criteria - Shear vane strength of 60kpa
label | Standard / Specification - PS 18.6.2
label | Verifying Document - Shear vane test report/Visual inspection
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.3 - Noise wall footing concrete
label | Detail - 17.5 MPA Concrete
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 17.5MPA
label | Standard / Specification - PS 18.6.2
label | Verifying Document - Concrete Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.4 - Installing Wooden Railings
label | Detail - with sufficient embeddment of nails and connecting details as per drawings
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 18.6.3
label | Verifying Document - Noise wall Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 3 – POST CONSTRUCTION (HANDOVER)
checkpoint | 3.1 - As-builts
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria - All changes to design need to be captured on the noise wall drawing set
label | Standard / Specification -
label | Verifying Document - Redpen Markup
label | Testing Quantity Required (based from schedule qtys) - During construction and after finishing
label | Verification Activity: Activity - WP
label | Verification Activity: By - SE
checklist | DN1210-016 ITP Fencing Rev 1 | itp |  |  |  |  | DN1210-016 ITP Fencing Rev 1
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.1.1 - Extent of Line Setout
label | Detail - Ensure line and level of Fences has been marked out and agreed with Engineer in accordance with fence drawings.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Design Drawings
label | Verifying Document - ITP Sign Off
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction & Every Revision of IFC Drawings/Data.
label | Verification Activity: Activity - M
label | Verification Activity: By - ENG
checkpoint | 1.1.2 - Existing Fences system
label | Detail - Confirmation of existing Fence network.
label | Acceptance / Conformance Criteria - Survey Information's
label | Standard / Specification - Appendix V
label | Verifying Document - Survey data
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 2.1.1 - Timber (Rails/palings/battens) Posts
label | Detail - Treatment
label | Acceptance / Conformance Criteria - H4
label | ○ H5 if touching ground otherwise H4
label | Standard / Specification - PS 27.5.5, NZS3607:1989
label | Verifying Document - Delivery docket
label | Testing Quantity Required (based from schedule qtys) - Prior Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 2.1.2 - Steel (Wire/Metal fence)
label | Detail - Standard galvanised high tensile steel wire
label | Acceptance / Conformance Criteria - 2.4mm 12 gauge
label | Standard / Specification - PS 27.5.1, PS 22.5.6
label | Verifying Document - Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Prior Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 2.1.3 - Chain Link Net
label | Detail - Standard galvanised high tensile steel wire
label | Acceptance / Conformance Criteria - 50*50 Max grid size
label | ○ Powder coated black finish
label | Standard / Specification - PS 14.6.1
label | Verifying Document - Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Prior Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 2.1.4 - Material (Fixings/fasteners/hinges/chains)
label | Detail - Jointing
label | Acceptance / Conformance Criteria - Hot dip galvanised
label | Standard / Specification - PS 27.5.1
label | Verifying Document - Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Prior Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
section | SECTION 3 – CONSTRUCTION ACTIVITY
checkpoint | 3.1.1 - Wetlands Fence
label | Detail - Install around the wetland
label | ○ Black powder coated finish
label | Acceptance / Conformance Criteria - 1.5M high
label | ○ Hot dip Galvanised
label | Standard / Specification - PS 2-32735.02-WSP-DR-UDL-0407, PS 27.5.1, PS 27.5.2
label | Verifying Document - Delivery docket
label | Testing Quantity Required (based from schedule qtys) - During installation
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 3.2.1 - Timber fence
label | Detail - Preserve timber exposed faces
label | ○ Post imbedded in ground
label | Acceptance / Conformance Criteria - 1.8m high
label | ○ Exposed timber faces neatly protected with 2 coats of timber preservative (Metalex)
label | ○ 1800mm in ground with 17.5MPa concrete
label | ○ Minimum 100mm extend around the post
label | Standard / Specification - PS 27.5.5
label | Verifying Document - Delivery docket
label | Testing Quantity Required (based from schedule qtys) - During installation
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 3.3.1 - Post and Wire Farm Fence
label | Detail - 8 Steel wire
label | ○ Timber post located at max 5m centre and securely rammed
label | ○ Battens affixed to wire and timber evenly spaces
label | Acceptance / Conformance Criteria - Wire and ground distance < 125mm
label | ○ Top wire to > 1m from ground
label | ○ Top of post > 50mm top wire
label | ○ Wires not attached on road side
label | ○ First 3 wire separation 125mm
label | ○ Min 3 battens between posts
label | Standard / Specification - PS- 27.5.6, NZS 2566
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 3.3.2 - Strainer Posts
label | Detail - At new and existing fence terminations
label | ○ At each corner distance between corner and/or termination strainer exceeds 200m
label | Acceptance / Conformance Criteria - Double footing and tight wire secured to the post using 4mm wire
label | Standard / Specification - PS 22.5.6.b
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 3.4.1 - Chain Link fence
label | Detail - As per drawings
label | ○ Headwall and Wingwall fencing
label | ○ Secured with posts and top rails
label | ○ Spacing between two post must be equal
label | Acceptance / Conformance Criteria - Tie wire on every second diamond
label | ○ Spacing < 2400mm
label | Standard / Specification - PS 2-32735.02-WSP-DR-UDL-0407
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
section | SECTION 4 – HANDOVER
checkpoint | 4.1.1 - Survey As-Builts
label | Detail - Quality Check on New Works based on the tolerances in RITS
label | Acceptance / Conformance Criteria - Meets spec and thickness requirements as per drawings
label | Standard / Specification - PS-21.7.7
label | Verifying Document - Red pen markup only
label | Testing Quantity Required (based from schedule qtys) - Post works completion of a lot
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG/PE