## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | 1. Standard |  | 1.Standard | d2b2529c-9aa7-4b6a-927f-7fea06d84ba1
| section | Precast Element Details (Project Manager)
| checkpoint | Concrete Details Complete
48b4964b-4f5e-5a73-8202-8376847b9b0a | textbox | Concrete Volume
dd5cca62-e351-59f6-9513-d2041b663d88 | textbox | Concrete Strength
282f747d-a59e-5507-a595-4cc49537cf92 | textbox | Enter Drawing Revision Number
1126ee27-7e41-5708-a871-f4a717b28a72 | textbox | Cast Date
3525fb4a-ef83-5945-bae7-4b0d0272c87d | textbox | Admixture Required
| section | Reinforcing Yard Checks (Reinforcing Supervisor)
| checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
| checkpoint | Cast in Items coordinated and marked on cage (Dross Ducts, Inserts Weld Plates)
| checkpoint | Overall cage dimensions in plan checked and there will be sufficent concrete cover to edges
| checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
| checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
| section | Formwork Set Up Checks (QA)
| checkpoint | Length/Width/Thickness/Cutouts/Diagonals
| checkpoint | Edge Details & Rebates
| checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
| checkpoint | MF roughening's
| checkpoint | Sides Straight & Magnets Fastened
| checkpoint | Mould Face Clean
| section | Prepour Checks (QA)
| checkpoint | Mould Cleaned & Oiled
| checkpoint | Check covers on all sides, MF and TF, openings
| checkpoint | Starters (Size, Grade, Setout and Length)
| checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
| checkpoint | Lifters
| checkpoint | Tie wire Trimmed
| checkpoint | Panel fully clean
| checkpoint | General Photos Attached
| checkpoint | Concrete Docket Attached
| checkpoint | Shop Drawing Checked Off (attach photo)
| section | Post Pour (QA)
| checkpoint | Confirm formwork has not shifted during placing of concrete
| checkpoint | Face lifters placed in correct location
| checkpoint | Roughening Lines Correct
| section | Demould Inspection (Yard Supervisor)
| checkpoint | Mould Face Acceptable?
| checkpoint | Trowel Face acceptable?
| checkpoint | Item Labelled?
| checkpoint | Drossbachs cleaned out and clear?
| checkpoint | Top lifters are cleared out and eyes are free of concrete?
| checkpoint | Drossbachs drilled ?
| checkpoint | Nail plates removed?
| checkpoint | Jet washed?
| checkpoint | Weld plates are cleaned and free of concrete?
| checkpoint | Starter bars bent for transportation?
| checkpoint | Structural repair required?
| checkpoint | Chamfer Inspection
| checkpoint | Silicone Inspection
| checkpoint | Honey combing from Vibrating
| checkpoint | Final check with drawing
| section | Loading Out (Yard Supervisor)
| checkpoint | Photo taken of Panel on Truck
| checkpoint | No remedial work required on site
| section | Test Results, Certificates and Documentation (QA)
| checkpoint | Upload reinforcing detail sheets
| checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
| checkpoint | Upload Concrete test results
3a2edcf7-94ef-451e-b661-8c2c021a9af7 | checklist | Add Defect/Remedial |  | Remedial - | a28654fb-28bf-4f39-bc8d-85fca885653a
e970f2e8-38be-47ea-88e8-55a317040604 | checkpoint | Defect Details Inputted
02fb74a6-9297-5b69-8d8f-5d0c48b9c66b | dropdown | What is the Defect | Chip in panel, Crack in the panel, Level of finish inadequate, Incorrect Location of Cast in Items, Missing Cast In Items, Other Remedial - Specify below
5643327d-d65b-5388-9530-86f7463e6f6b | textbox | Other Defect (specify here if applicable)
0a0c215a-1923-5c54-9bd7-a2a864f6723e | textbox | Defect Location on Panel (Attach Photo)
7152a2c6-2eb2-5247-8f3c-096388865e18 | textbox | Remedial Work Required
502296f5-6918-4b50-a34e-45b8d43935b1 | checkpoint | Panel Location Inputted
96be865a-2544-5cb4-9d0c-5574d44c5bb8 | textbox | Panel Location
98dc4c4e-edbc-4b97-8033-8b15d5166725 | checkpoint | NCR Raised if Required
883a5a98-2c88-4d02-aa0d-e0db0e558895 | checkpoint | Remedial completed - (Attach Photo)
496ad6f2-797a-4b17-a0c0-69cd3b3dcd4a | checklist | Compliance Documentation Checklist |  | Compliance Documentation | f3e79d28-e6a7-4307-a43d-740ee207ed7e
f58889c0-5e6b-482f-bec0-0ae5a115ed21 | checkpoint | Concrete Test Results
066d13f7-4c78-53cf-ae07-c6288d05b188 | note | Pass once all test results for this project are attached
4fe06e26-34cc-58f5-876f-027f90ea4833 | textbox | Concrete test requirements for this project
a40742db-3201-4a72-ac32-2faed3ed3e97 | checkpoint | Mill Certification
95c90d50-faae-57db-8f9a-9e8b3b1bada8 | note | Pass once all mill certs for this project are attached
75aa4f73-99ce-4d2a-a05b-d954d6eb38ed | checkpoint | PS1 Attached (if applicable)
49b1e850-1ca9-4741-8c28-ee80ef9b1a01 | checkpoint | PS3 Attached (if applicable)
2e7a2ce4-b667-435d-b89d-f639ced12998 | checkpoint | PS4 Attached (if applicable)
cb39f9e7-7e8f-4740-8ac4-ef68fc245ea4 | checklist | Job Details Checklist |  | Job Details | ed41acee-d06d-4515-84d2-177bddfc14a8
3d098030-e418-4675-b5b1-7520caf5ee77 | checkpoint | Project details entered below
8724734a-b967-59e4-b175-c5c6f1db0e60 | textbox | Job File Number
45b6015f-22e3-5b0c-8117-3a27221048ee | textbox | Project Name
ef1b5d06-622a-5aca-84c2-8a00931e8d8a | textbox | Site Address
31c83e66-7544-5cd3-a918-a8f6baca03e9 | textbox | Main Contractor (e.g. Teak)
b1590901-5990-5ddc-9dee-19725346ccbb | textbox | Main Contractor POC
04d29bad-dab1-5357-9860-e83c0c02444f | textbox | Structural Engineer
78611fa4-7a52-594c-8bc7-427229a97b3c | textbox | Architect
| checklist | Site Works Defect #1 (Siteworks Manager) |  | Site Works Defect #1 (Siteworks Manager) | b8795d90-66d3-4d71-84c0-712e536fc127
| section | Details
| checkpoint-no-value | Site Works Defect #1
043c897d-151c-5bb7-898e-f3ceda3641c4 | date | Date when scoping document was created
| checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
| checkpoint | Remedial required
fabe9aad-f2d4-5e11-b77c-11c5b22ab73e | tickbox | Grind
7ee9e524-cd07-52ee-9cd6-ad7540ba48e6 | tickbox | Sand
a519a11e-71de-5930-bbbd-084d32e669df | tickbox | Fill
827ad856-333f-513d-8589-2a0c835bdd80 | tickbox | Drill
1221cc09-97e6-5741-b8ff-0b490ee71eae | tickbox | Plaster
0fe1b80a-928e-5b0a-8609-b5366da5bc0a | tickbox | Paint
9e40fa3c-6003-5edc-a67b-e21965d7e1a6 | tickbox | colour match
15fb3d68-9875-5bfc-812b-63dc536db89f | tickbox | Epoxy Reo
3ed7ae3a-9fbf-5161-b557-7dca39d654dd | dropdown | PHQ, Dayworks, | PHQ, Dayworks,
| checkpoint | NCR Raised if Required
| checkpoint | Remedial completed (Take photo to evidence)
8e30fd24-809d-54c9-849b-8d67c54e5b8f | date | Date remedial completed
| signoff | Remedial acceptable and signed off by client
| checklist | Site Works Defect #2 (Siteworks Manager) |  | Site Works Defect #2 (Siteworks Manager) | eceef6cd-e05b-4238-944d-8cae10e2a811
| section | Details
| checkpoint-no-value | Site Works Defect #2
ebb7c796-5fa7-56f4-aa2c-9796cac73dea | date | Date when scoping document was created
| checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
| checkpoint | Remedial required
7f40ba8b-fc83-5d5e-961c-9b34d7930bbd | tickbox | Grind
e52ebb4d-32b4-5962-8c33-1bdff16d8f37 | tickbox | Sand
af3a14f4-bfe1-55cd-a0c9-83cd8f86ca08 | tickbox | Fill
e2f95db6-e368-550f-b4ce-54e890fe882b | tickbox | Drill
554edf63-916d-5ce0-a2a8-45d90730e023 | tickbox | Plaster
822bed33-5db4-58bd-bc5e-1cb9c424ae53 | tickbox | Paint
89b7fe5e-15e6-5008-8c7b-9e917ec10659 | tickbox | colour match
b2393393-da9d-5782-9b8e-29972a9cd357 | tickbox | Epoxy Reo
ad95eaea-8ccb-5438-8ca0-f21b31ec20a0 | dropdown | PHQ, Dayworks, | PHQ, Dayworks,
| checkpoint | NCR Raised if Required
| checkpoint | Remedial completed (Take photo to evidence)
3602cfe0-e6c6-58b4-835f-0c41abadff77 | date | Date remedial completed
| signoff | Remedial acceptable and signed off by client
| checklist | Site Works Defect #3 (Siteworks Manager) |  | Site Works Defect #3 (Siteworks Manager) | c47b51a6-c810-4ede-83bc-cb20a526a2b7
| section | Details
| checkpoint-no-value | Site Works Defect #3
a23f5ad8-e47f-5f55-9417-91e4e8edd382 | date | Date when scoping document was created
| checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
| checkpoint | Remedial required
2037ea65-8c11-568f-a28b-4bdb40b5cb85 | tickbox | Grind
2530cd09-9f0a-55b4-8224-c4c07b61a39f | tickbox | Sand
86ccf1c4-7c75-59f8-9c1c-adf62bf4f9ea | tickbox | Fill
8c36bb6f-05ad-5021-9068-a0eb27b77d25 | tickbox | Drill
065d97b3-67d7-5f64-bcac-3c05852e2286 | tickbox | Plaster
a68c7514-57c4-5d74-9625-0ef27e216405 | tickbox | Paint
228c8006-4584-5ce0-b75c-843d328132d9 | tickbox | colour match
00844929-40cf-58d5-bd2c-3a10e9c3c87c | tickbox | Epoxy Reo
964dbfb9-ce33-582b-98e7-c5839e4986a5 | dropdown | PHQ, Dayworks, | PHQ, Dayworks,
| checkpoint | NCR Raised if Required
| checkpoint | Remedial completed (Take photo to evidence)
08fe3e6b-3698-51a8-a5bb-6e523d98de7b | date | Date remedial completed
| signoff | Remedial acceptable and signed off by client
| checklist | Site Works Defect #4 (Siteworks Manager) |  | Site Works Defect #4 (Siteworks Manager) | 43bc4d7f-57ad-4ac4-81ab-cf3c38096e60
| section | Details
| checkpoint-no-value | Site Works Defect #4
aded4b8d-d46b-56a7-8b83-c00bef27c857 | date | Date when scoping document was created
| checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
| checkpoint | Remedial required
d491400a-65ed-5863-9b32-25857971f5be | tickbox | Grind
b6cf4d1c-29c7-5a25-b3fc-4b4bac1d826a | tickbox | Sand
378385bd-479c-57ba-867f-e818db1770dd | tickbox | Fill
7ccdb2e0-5589-5aca-945e-b6403c04adac | tickbox | Drill
2bdd6e98-14fa-55b7-981a-e06490d5699b | tickbox | Plaster
99fe5295-31b0-5fed-adc3-ec5f3359c030 | tickbox | Paint
a114f091-d474-5ea8-90f4-8e2a31f50137 | tickbox | colour match
b684ef68-cf80-535e-8ee9-48a0989dc3a7 | tickbox | Epoxy Reo
20ba3340-49bc-5411-ae25-674b56449c73 | dropdown | PHQ, Dayworks, | PHQ, Dayworks,
| checkpoint | NCR Raised if Required
| checkpoint | Remedial completed (Take photo to evidence)
69329b9d-68be-5b42-b6ca-3ea888e1a950 | date | Date remedial completed
| signoff | Remedial acceptable and signed off by client
| checklist | Site Works Defect #5 (Siteworks Manager) |  | Site Works Defect #5 (Siteworks Manager) | 2514ad55-886b-4f77-ad92-5d85799b6a8c
| section | Details
| checkpoint-no-value | Site Works Defect #5
d191602d-7519-54c5-a164-d82d6c3b3b07 | date | Date when scoping document was created
| checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
| checkpoint | Remedial required
2f1d4bb1-7b8b-500f-ba93-71628e09f2fd | tickbox | Grind
ce82ed98-b2e3-56d8-b3f2-a8943e2b665e | tickbox | Sand
57a6f61c-0854-5fe6-a3fc-fa2cdbc3adba | tickbox | Fill
3f66a26f-5733-5e73-9880-79ede90540cb | tickbox | Drill
c168feb5-1c91-57d2-9270-6a550bcca95e | tickbox | Plaster
ffff90d3-9fd2-5f91-bb44-d0f92910c204 | tickbox | Paint
3ac2d130-eff8-5e91-ae53-9624d6bb9a8c | tickbox | colour match
4a759194-a346-5f04-bf1a-715086129918 | tickbox | Epoxy Reo
86d34241-8697-5f60-a3e9-be05c4dd293a | dropdown | PHQ, Dayworks, | PHQ, Dayworks,
| checkpoint | NCR Raised if Required
| checkpoint | Remedial completed (Take photo to evidence)
8627f45b-8084-5b3a-b3bd-fa7fc2a08d6a | date | Date remedial completed
| signoff | Remedial acceptable and signed off by client