## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Area Ready Checklist |  |  |  |  | Yes | Area Ready Checklist | 0e12bd4e-610f-4f7e-8f7f-86300baab40f
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Substrate Acceptable
checkpoint-status |  |  | checkpoint | Wet Area Screed Installed
checkpoint-group |  |  | section | Walls / Ceiling
checkpoint-status |  |  | checkpoint | Ceiling Installed
checkpoint-status |  |  | checkpoint | Gyprock
checkpoint-status |  |  | checkpoint | Plastered
checkpoint-status |  |  | checkpoint | Plaster Sanded
checkpoint-status |  |  | checkpoint | Painted
checklist-flat |  |  | checklist | Variation |  |  |  |  | Yes | Variation | 4deec017-b9d6-4600-8475-af35cc55f606
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 42c2c931-f476-536f-abcc-581377348a8d |  | textbox | Reference/Drawing/Instruction Number
text | 9f95cb7b-9964-55c4-9e84-13c644e5bb95 |  | textbox | Variation Area
text | 514de06a-9f83-55c9-b733-99003855da92 |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-flat |  |  | checklist | Drawings |  |  |  |  | Yes | Drawings | 927f06e7-f1b3-42d8-8d62-5235e12fb1d6
checkpoint-status |  |  | checkpoint | Attach Drawings
checklist-sectioned |  |  | checklist | Floor Finishes ITP |  |  |  |  | Yes | Floor Finishes ITP | 947f73c1-18bf-4e5a-bdd3-87a7c19e5a52
checkpoint-group |  |  | section | Subfloor, Floor Preparation, Adhesive
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Subfloor mechanically diamond ground
checkpoint-status |  |  | checkpoint | Floor preparation product installed in accordance with manufacturer's instructions
checkpoint-status |  |  | checkpoint | Floor transitions installed as per instructions from builder
checkpoint-status |  |  | checkpoint | Waterproof tested for falls, and water test completed by waterproofers
checkpoint-status |  |  | checkpoint | Mediseal installed to carpet areas as per plans - min 24 hours curing time observed
select | 86245bd2-51ee-53d5-b783-f838c89aa7b7 |  | dropdown | Product: | MAPEI PLANIPREP SC, 3-4 Mapei Floor Leveller
text | e74890ad-ff27-59a6-8883-87ed1f69903b |  | textbox | Average thickness: |  |  | mm
checkpoint-status |  |  | checkpoint | Correct adhesive used
select | 0b6b9b6f-7480-50e9-8c65-0eeb4dcca109 |  | dropdown | Adhesive: | V4 Evolution Vinyl Adhesive, Monstertack PS Carpet Adhesive, G19 WET AREA ADHESIVE, Capitol PS Adhesive
checkpoint-group |  |  | section | Carpet / Vinyl
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
text | 816e9de8-57c3-5c07-a814-163ceb401b2e |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Vinyl installed as per plan
select | 877a165b-e9db-5ae3-844a-fa9eee43060b |  | dropdown | Material: | RF01 - ARMSTRONG ACCOLADE FOOTHOLD CAMDEN GREY, RF02 - ARMSTRONG ACCOLADE PLUS MINTARO SLATE, RF02A - ARMSTRONG ACCOLADE FOOTHOLD MINTARO SLATE, RF03 - ARMSTRONG SAFEGUARD R12 STORM GREY, RF04 - INSPIRED GRANIT
checkpoint-status |  |  | checkpoint | Carpet installed as per plan
select | b857c296-e895-503f-91d6-a6498fd5ea27 |  | dropdown | Material: | CPT01 - Inspired Carpet Tiles - Mist
text | 93229d1e-328c-58a0-9f28-8d24bccd4db3 |  | textbox | Other colour:
checkpoint-status |  |  | checkpoint | Joints sealed with heat welded seams and mitres as per AS 1884-2012
checkpoint-status |  |  | checkpoint | Vinyl skirt and coving used as per finishes markup - 150mm height
text | 64555191-4f70-5898-a01c-916c186535c8 |  | textbox | Custom height:
checkpoint-status |  |  | checkpoint | Installer Sign Off: Carpet / Vinyl installed as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Add-Floors Sign Off
checkpoint-status |  |  | checkpoint | Foreman installation sign off
checkpoint-group |  |  | section | Wall Finish
checkpoint-status |  |  | checkpoint | Wall Finish installed as per plan
select | 9e1ffd71-d650-5dac-88f0-2ebdf2b5581a |  | dropdown | Material: | WV - ARMSTRONG WALLFLEX ALABASTER
checkpoint-group |  |  | section | Protection and Handover
checkpoint-status |  |  | checkpoint | Installation complete, checked and reviewed - as per specification
text | 6b6fcef8-9aad-54f9-9970-bd6e0e5b9fb9 |  | textbox | General comments / observations
checkpoint-status |  |  | checkpoint | Floor protected with bubbleweave floor protection or polyweave
checkpoint-status |  |  | checkpoint | Installer Sign Off: Protection installed as per manufacturer's instructions
checklist-flat |  |  | checklist | Delivery Checklist |  |  |  |  | Yes | Delivery Checklist | c46bd10a-4b27-4c7d-a476-27e9540c6461
checkpoint-status |  |  | checkpoint | Delivery details input
text | 078acb0a-efbd-5926-ad62-59b1b040f477 |  | textbox | Date
text | 55d1dbd8-a8e9-51ed-b9a6-4e7efe28c6d4 |  | textbox | Delivered by
text | e2046b65-441a-5c87-af86-fa85f97202c8 |  | textbox | From
text | 68d89367-f9a5-51f9-859e-688181094670 |  | textbox | Description
text | 803ae47c-b8d0-5e4b-9216-0e04ee5498a7 |  | textbox | Comments
text | 54e68448-fba1-54d8-b21e-aa3040b84ae1 |  | textbox | Stored where
checkpoint-status |  |  | checkpoint | Materials checked
boolean | a18c74d1-66b6-57c7-89e9-ca65930eca2f |  | tickbox | Materials in good order
boolean | 58bfed5f-a2b9-5d18-b715-b430a8809451 |  | tickbox | Photo of materials
boolean | 71978de9-4de3-55bc-b492-6c35db7d2f71 |  | tickbox | Photo of Con Note
boolean | b87a645e-fc5a-5e53-875f-ca8a5f34c41c |  | tickbox | Photo Packing Slip / Slips
text | 5c5e4458-4269-50dd-b4ca-bd81a20164f2 |  | textbox | Comments