## ITP - Pavement
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # GT4-ITP-009
[11 empty] | Revision : 01 | Date : 31/05/2023
Client: |  | Hobart International Airport Pty Ltd |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Project Mercury Early Works At Hobart International Airport |  | Unbound Flexible Pavement Construction |  | Name: | Zac Buick | Name: | Tristan Black |  | Name:
Contract No: |  | MER-EW-001 |  | Specifications: Hobart Airport Project Mercury Early Works Civil Specification. AS 3600, 1379
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Hobart International Airport |  | Date : | 2023-05-31 | Date : | 2023-07-27 |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Independent QA Verifier | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing works | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP` | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.3 | Plant and Equipment |  | Prior to commencing works | Plant and equipment used in the Works are appropriate to achieve specification requirements and is inducted | N/A | Visual Inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2 | Placement
2.1 | The commencement of construction of base and subbase |  | Prior to placing subbase | After the sub-grade has been compacted to approval, the crushed rock shall be spread in even layers of 150 mm maximum loose thickness. The material shall be spread to produce the required consolidated thickness by means of approved mechanical spreader. The material shall be maintained within +/- 2% of OMC, with additional water being added if required during compaction. Materials shall be spread without segregation of large and small particles, between approved edge boards or kerbs | C.9.2 | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.2 | Shape |  | Each lot | Rolling shall be performed in such a manner as to eliminate bumps and irregularities with the finished surface true to the required grades and cross-section. | C.9.3 | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.3 | Delivery Dockets |  | Each lot | Where material is scheduled for measurement by loose volume in delivery vehicles or by mass, a delivery docket for each load shall be issued to the Superintendent at the point of delivery. | Work Procedure | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.4 | Layer Thickness |  | Each layer | Material is to be compacted to the overall thickness shown in the drawings (dependent on pavement type), Subgrade to be within +5mm or - 30mm of design Subbase to be within + 10mm or - 20mm of design Basecourse thickness to be 0mm from design level | EW-CE-DRW-406-001 EW-CE-DRW-416-001 C.7.4 | Visual and Measure | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.5 | Conformity with Drawing |  | Each lot | Width of each side of the pavement shall not be less than the specified offset width or more than + 300mm outside the specified offset width when measured at right angles from the centre line or design line. Where pavement is to be constructed to the lip level of kerb and channel, it shall be constructed flush with the lip of the channel or not more than 5 mm above. Any material that has been compacted and then trimmed from the compacted surface to conform | C.7.4 Work Procedure | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.6 | Jointing |  | Each lot | (a) material shall be spread in such a manner as to minimise the number of joints (b) transverse joints shall be offset from one layer to the next by not less than 2m (c) longitudinal joints shall be offset from one layer to the next by not less than 150mm | Work Procedure | Visual Inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
3 | Testing and Conformance
3.1 | Test Rolling |  | Each lot | All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with table 5 of section C.7.2 prior to acceptance of the layer. | C.7.2 | Test Roll | This ITP signed | HP* | Site Engineer / QAV | N/A
3.2 | Compaction of road pavement |  | Every Lot | The minimum compaction achieved shall be 100% of the Standard Maximum Dry Density in the base course, and 98% of the Standard Maximum Dry Density in the sub-base course | C.9.4 | Test point | This ITP signed | HP | Site Engineer | N/A
3.3 | Completed Surface Level Compliance |  | Each lot | Surveyed as constructed drawings to be provided showing finished contour levels. Spreading, scraping and consolidation of the various layers of the pavement shall proceed with each layer having a construction tolerance of; Subbase: + 10mm or - 20mm Base: + 10mm or - 10mm | C.7.2 C.9.4 | Survey | This ITP signed | SCP | Site Engineer | N/A |  | N/A
3.4 | Shape |  | Each lot | Layer to be finished to a smooth and uniform surface and after compaction and meeting the following tolerances: Crossfall: + or - 0.5% of design Surface: + or - 15mm when tested with a 3m straight edge, laid in any direction. Longitudional Grades: The gutter grade shall be + or - 20% of the design grade. | C.7.4 | Test Point | This ITP signed | TP | Site Engineer | N/A |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Fulton Hogan | Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent