## ITP - Earthworks
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [8 empty] | Document # GT4-ITP-011
[12 empty] | Revision : 0 | Date: 20/07/2023
Client: |  | Hobart International Airport Pty Ltd |  | Construction Process: |  | Prepared by: |  |  | Reviewed by : |  |  | Approved by :
Project: |  | Project Mercury Early Works At Hobart International Airport |  | Earthworks - Cut, Fill and Subgrade Preperation |  | Name: | Zac Buick |  | Name: | Tristan Black |  | Name:
Contract No: |  | MER-EW-001 |  | Specifications: Hobart Airport Project Mercury Early Works Civil Specification. AS 3600, 1379, 'SCHERZIC' GEOTECHNICAL REPORT No. 7345B
|  |  |  | Structure / Component: |  | Signed : |  |  | Signed : |  |  | Signed :
|  |  |  | Location: Hobart International Airport |  | Date : | 2023-07-20 |  | Date : | 2023-07-27 |  | Date :
Lot No: |  |  | Lot Details: | [6 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents |  | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Superintendant | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: -using Issued for Construction (IFC) drawings -using the correct and complete set of drawings -all drawings are the latest revision | IFC drawings and drawing registers |  | Document Review / Visual inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: OHSMP, EMP, TMP, SWMS & WP. Access and egress inspected and assessed for stability. | OHSMP, EMP, TMP, SWMS, WP |  | Visual Inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.3 | Survey set-out |  | Prior to commencing | Prior to any excavation, the general areas within the definded limit of works as part of the Early Works package, and site works within the contract shall be set out by suitable hurdles, pegs or markers. Levels shall be established and pegged from a common datum. All setting out shall be carefully checked against the drawings prior to commencement, and any discrepancies clarified before construction commences. | C.2.3 |  | Visual Inspection | Survey records and pegs on the ground | IP | Site Engineer | N/A |  | N/A
1.4 | Ground Penetration Permit |  | Each Lot | A ground penetration permit must be issued prior to excavation commencing. Plant and equipment must be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation. | Ground Penetration Permit |  | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
1.5 | Protection of Services |  | Prior to commencing | The Contractor shall and all personnel on Site shall familiarise themselves, under his direction, with the location of all existing services on and adjacent to the site. The existing services shown on the Drawings may not be representative of all services within the site of works. It is the Contractor’s responsibility to locate all services both in plan and depth to avoid damage and disruption to authority assets | C.2.4 |  | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
2 | Earthworks
2.1 | Material Categorisation |  | Each Lot | Prior to commencing excavation in any area and during excavation work, the contractor and Superintendent shall inspect and agree upon the type / category of material encountered | Work Procedure |  | Verify | This ITP signed | HP* | Site Engineer / QAV | N/A
2.2 | Stripping of Topsoil |  | Each Lot | Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining. Spoil from site to be taken to 15-alpha in accordance with CEMP | Work Procedure CEMP |  | Visual Inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.3 | Protection of Works |  | Each Lot | Temporary earth drains shall be constructed where necessary to prevent water flowing onto the construction works and to take away water from the works. These drains shall discharge into a permanent outfall. Pumps shall be provided where necessary to dewater excavations. | C.2.7 |  | Visual Inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.4 | Unsuitable Material |  | Each Lot containing unsuitable material | Subgrade to be free of soft spots; if localised soft patches are encountered an additional 150mm of excavation, replaced with subbase material shall be undertaken with survey records showing extents. If multiple soft patches identified, contact Superintendent for assessment prior to undertaking further measures. Should subgrades become saturated any unsuitable material is to be removed and made good with type B general fill and/or lime/cement stabilized as required in order to maintain subgrades. | C.9.2 EW-CE-DRW-007-001 |  | Verify | This ITP Signed | HP | Site Engineer / QAV | N/A
2.5 | Subgrade Material |  | Each Lot | The subgrade shall consist of a uniform type material, free of soft patches, oversize particles, topsoil, deleterious and/or perishable matter. Where the in-situ material varies then the Construction project manager shall direct any over excavation and replacement with approved material, either from site or off site to achieve a stable subgrade. The sand filling over the site is considered a suitable subgrade for new pavements and only minimal proof rolling will be require preparation for pavement construction. Note that sands will dilate if over compacted and minimal passed with a smooth drum vibratory roller are only required. Large rollers (>6 tonne) should be avoided to proof roll the sand and sand filling. | C.9.2 C.3.2 C.3.3 C.3.4 4.2 of 7345B |  | Verify | Test Report | TP | Site Engineer | N/A |  | N/A
2.6 | Placing of Fill |  | Each Layer | Fill to be placed in uniform horizontal layers of 200mm maximum depth and compacted in accordance with the requirements of AS 3798. All finished surfaces shall achieve a minimum compaction of 98% standard dry density. Type A material shall comply with the requirements of Table 1 in C3.2 Type B material shall be in accordance with section C.3.3 Type C material shall be in accordance with section C.3.4 | EW-CE-DRW-007-001 C.3.2 C.3.3 C.3.4 |  | Visual Inspection / Measure | This ITP signed | IP | Site Engineer | N/A |  | N/A
3 | Testing and Surface Preperation
3.1 | Test Rolling |  | Each layer | Test Rolling shall be undertaken in accordance with section C.3.8c and the Contractor shall advise the Superintendant when the proof compaction is due to be carried out, giving a minimum of 48 hours’ notice. The frequency of the test rolls shall be in accordance with table 5 in section C.7.2 of the project specification for the relevant pavement layer. | C.3.8c C.7.2 |  | Visual Inspection | This ITP signed | HP* | Site Engineer / QAV | N/A
3.2 | Cut and Fill Tolerances |  | Each Lot | The design surface levels are the levels on the completed earthworks including respread topsoil where applicable. The completed earthworks levels shall be – a. within + 100mm to - 0mm of the design levels where there are no retaining walls; or b. within + 50mm to - 0mm of the design levels where retaining walls exist, are proposed, or will exist in the future. Where material layer thicknesses are specified they shall be – a. within + 100mm to - 0mm of the design thickness for Type A1 – Structural Fill (Sand), Type A2 – Structural Fill (Gravelly Sand) and any other material described as ‘sand’ or ‘structural fill’; or b. within ± 50mm of the design thickness for all other material types. | C.3.13 |  | Verify | This ITP signed | SCP | Site Engineer | N/A |  | N/A
3.3 | Subgrade level conformity |  | Each Lot | Finished subgrade level tolerances to be + 5mm or - 30mm ( +0mm ) | C.7.4 |  | Verify | This ITP signed, Survey report | SCP | Site Engineer | N/A |  | N/A
3.4 | Fill Material Compaction & Moisture Content Requirements |  | Each Lot | Sub-grade shall be compacted to not less than 100% of the standard maximum dry density to a minimum depth below the surface of 300mm. The moisture content of subgrade is to be +/- 2% of Standard Optimum Moisture Content (OMC). Sub-grade to be formed to grade, crossfall etc. to ensure that an even thickness of pavement can be finally achieved. No further stage of construction to be commenced until the completed sub-grade has been inspected and approved by the Superintendant and the Local Authority. | C.9.3 |  | Verify | This ITP signed | HP | Site Engineer | N/A
3.5 | CBR Testing of Subgrade |  | Each lot | Contractor shall test subgrade for minimum California Bearing Ratio (CBR) at frequency nominated in Table 5 to ensure the site CBR conforms to design pavement assumption. The minimum site CBR is to be 5%, unless noted otherwise. | C.9.2 |  | Test Point | This ITP signed | HP | Site Engineer | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Fulton Hogan | Print Name: |  | Position: |  |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent