## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | GT4-ITP-009 - Unbound Flexible Pavement Construction | itp |  |  |  | Yes | GT4-ITP-009 - Unbound Flexible Pavement Construction
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents: Drawings and drawing registers
label | Inspection / Test Method: Visual inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing works
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP`
label | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.3 - Plant and Equipment
label | Frequency: Prior to commencing works
label | Acceptance Criteria: Plant and equipment used in the Works are appropriate to achieve specification requirements and is inducted
label | Reference Documents: N/A
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 2 - Placement
checkpoint | 2.1 - The commencement of construction of base and subbase
label | Frequency: Prior to placing subbase
label | Acceptance Criteria: After the sub-grade has been compacted to approval, the crushed rock shall be spread in even layers of 150 mm maximum loose thickness.
label | • The material shall be spread to produce the required consolidated thickness by means of approved mechanical spreader. The material shall be maintained within +/- 2% of OMC, with additional water being added if required during compaction.
label | • Materials shall be spread without segregation of large and small particles, between approved edge boards or kerbs
label | Reference Documents: C.9.2
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.2 - Shape
label | Frequency: Each lot
label | Acceptance Criteria: Rolling shall be performed in such a manner as to eliminate bumps and irregularities with the finished surface true to the required grades and cross-section.
label | Reference Documents: C.9.3
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.3 - Delivery Dockets
label | Frequency: Each lot
label | Acceptance Criteria: Where material is scheduled for measurement by loose volume in delivery vehicles or by mass, a delivery docket for each load shall be issued to the Superintendent at the point of delivery.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.4 - Layer Thickness
label | Frequency: Each layer
label | Acceptance Criteria: Material is to be compacted to the overall thickness shown in the drawings (dependent on pavement type),
label | • Subgrade to be within +5mm or - 30mm of design
label | • Subbase to be within + 10mm or - 20mm of design
label | • Basecourse thickness to be 0mm from design level
label | Reference Documents: EW-CE-DRW-406-001, EW-CE-DRW-416-001 C.7.4
label | Inspection / Test Method: Visual and Measure
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.5 - Conformity with Drawing
label | Frequency: Each lot
label | Acceptance Criteria: Width of each side of the pavement shall not be less than the specified offset width or more than + 300mm outside the specified offset width when measured at right angles from the centre line or design line.
label | • Where pavement is to be constructed to the lip level of kerb and channel, it shall be constructed flush with the lip of the channel or not more than 5 mm above.
label | • Any material that has been compacted and then trimmed from the compacted surface to conform
label | Reference Documents: C.7.4 Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.6 - Jointing
label | Frequency: Each lot
label | Acceptance Criteria: (a) material shall be spread in such a manner as to minimise the number of joints
label | (b) transverse joints shall be offset from one layer to the next by not less than 2m
label | (c) longitudinal joints shall be offset from one layer to the next by not less than 150mm
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 3 - Testing and Conformance
checkpoint | 3.1 - Test Rolling
label | Frequency: Each lot
label | Acceptance Criteria: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with table 5 of section C.7.2 prior to acceptance of the layer.
label | Reference Documents: C.7.2
label | Inspection / Test Method: Test Roll
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer / QAV
text | Date Completed:
checkpoint | 3.2 - Compaction of road pavement
label | Frequency: Every Lot
label | Acceptance Criteria: The minimum compaction achieved shall be 100% of the Standard Maximum Dry Density in the base course, and 98% of the Standard Maximum Dry Density in the sub-base course
label | Reference Documents: C.9.4
label | Inspection / Test Method: Test point
label | Record of conformity: This ITP signed
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Completed Surface Level Compliance
label | Frequency: Each lot
label | Acceptance Criteria: Surveyed as constructed drawings to be provided showing finished contour levels.
label | ○ Spreading, scraping and consolidation of the various layers of the pavement shall proceed with each layer having a construction tolerance of;
label | • Subbase: + 10mm or - 20mm
label | • Base: + 10mm or - 10mm
label | Reference Documents: C.7.2, C.9.4
label | Inspection / Test Method: Survey
label | Record of conformity: This ITP signed
label | SCP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.4 - Shape
label | Frequency: Each lot
label | Acceptance Criteria: Layer to be finished to a smooth and uniform surface and after compaction and meeting the following tolerances:
label | • Crossfall: + or - 0.5% of design
label | • Surface: + or - 15mm when tested with a 3m straight edge, laid in any direction.
label | • Longitudional Grades: The gutter grade shall be + or - 20% of the design grade.
label | Reference Documents: C.7.4
label | Inspection / Test Method: Test Point
label | Record of conformity: This ITP signed
label | TP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP