## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | GT4-ITP-011 - Earthworks - Cut, Fill and Subgrade Preparation | itp |  |  |  | Yes | GT4-ITP-011 - Earthworks - Cut, Fill and Subgrade Preparation
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | – using Issued for Construction (IFC) drawings
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents: IFC drawings and drawing registers
label | Inspection / Test Method: Document Review / Visual inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: OHSMP, EMP, TMP, SWMS & WP. Access and egress inspected and assessed for stability.
label | Reference Documents: OHSMP, EMP, TMP, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.3 - Survey set-out
label | Frequency: Prior to commencing
label | Acceptance Criteria: Prior to any excavation, the general areas within the definded limit of works as part of the Early Works package, and site works within the contract shall be set out by suitable hurdles, pegs or markers.
label | • Levels shall be established and pegged from a common datum.
label | • All setting out shall be carefully checked against the drawings prior to commencement, and any discrepancies clarified before construction commences.
label | Reference Documents: C.2.3
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: Survey records and pegs on the ground
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.4 - Ground Penetration Permit
label | Frequency: Each Lot
label | Acceptance Criteria: A ground penetration permit must be issued prior to excavation commencing.
label | • Plant and equipment must be appropriate for the task.
label | • Excavation operations shall not disturb areas outside the limit of excavation.
label | Reference Documents: Ground Penetration Permit
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.5 - Protection of Services
label | Frequency: Prior to commencing
label | Acceptance Criteria: The Contractor shall and all personnel on Site shall familiarise themselves, under his direction, with the location of all existing services on and adjacent to the site.
label | • The existing services shown on the Drawings may not be representative of all services within the site of works. It is the Contractor’s responsibility to locate all services both in plan and depth to avoid damage and disruption to authority assets
label | Reference Documents: C.2.4
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 2 - Earthworks
checkpoint | 2.1 - Material Categorisation
label | Frequency: Each Lot
label | Acceptance Criteria: Prior to commencing excavation in any area and during excavation work, the contractor and Superintendent shall inspect and agree upon the type / category of material encountered
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer / QAV
text | Date Completed:
checkpoint | 2.2 - Stripping of Topsoil
label | Frequency: Each Lot
label | Acceptance Criteria: Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining.
label | • Spoil from site to be taken to 15-alpha in accordance with CEMP
label | Reference Documents: Work Procedure, CEMP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.3 - Protection of Works
label | Frequency: Each Lot
label | Acceptance Criteria: Temporary earth drains shall be constructed where necessary to prevent water flowing onto the construction works and to take away water from the works. These drains shall discharge into a permanent outfall. Pumps shall be provided where necessary to dewater excavations.
label | Reference Documents: C.2.7
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.4 - Unsuitable Material
label | Frequency: Each Lot containing unsuitable material
label | Acceptance Criteria: Subgrade to be free of soft spots; if localised soft patches are encountered an additional 150mm of excavation, replaced with subbase material shall be undertaken with survey records showing extents.
label | • If multiple soft patches identified, contact Superintendent for assessment prior to undertaking further measures.
label | • Should subgrades become saturated any unsuitable material is to be removed and made good with type B general fill and/or lime/cement stabilized as required in order to maintain subgrades.
label | Reference Documents: C.9.2 EW-CE-DRW-007-001
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP
label | Responsibility: Site Engineer / QAV
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Subgrade Material
label | Frequency: Each Lot
label | Acceptance Criteria: The subgrade shall consist of a uniform type material, free of soft patches, oversize particles, topsoil, deleterious and/or perishable matter. Where the in-situ material varies then the Construction project manager shall direct any over excavation and replacement with approved material, either from site or off site to achieve a stable subgrade.
label | • The sand filling over the site is considered a suitable subgrade for new pavements and only minimal proof rolling will be require preparation for pavement construction.
label | • Note that sands will dilate if over compacted and minimal passed with a smooth drum vibratory roller are only required. Large rollers (>6 tonne) should be avoided to proof roll the sand and sand filling.
label | Reference Documents: C.9.2, C.3.2, C.3.3, C.3.4, 4.2 of 7345B
label | Inspection / Test Method: Verify
label | Record of conformity: Test Report
label | TP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.6 - Placing of Fill
label | Frequency: Each Layer
label | Acceptance Criteria: Fill to be placed in uniform horizontal layers of 200mm maximum depth and compacted in accordance with the requirements of AS 3798.
label | • All finished surfaces shall achieve a minimum compaction of 98% standard dry density.
label | • Type A material shall comply with the requirements of Table 1 in C3.2
label | • Type B material shall be in accordance with section C.3.3
label | • Type C material shall be in accordance with section C.3.4
label | Reference Documents: EW-CE-DRW-007-001, C.3.2, C.3.3, C.3.4
label | Inspection / Test Method: Visual Inspection / Measure
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 3 - Testing and Surface Preparation
checkpoint | 3.1 - Test Rolling
label | Frequency: Each layer
label | Acceptance Criteria: Test Rolling shall be undertaken in accordance with section C.3.8c and the Contractor shall advise the Superintendant when the proof compaction is due to be carried out, giving a minimum of 48 hours’ notice.
label | • The frequency of the test rolls shall be in accordance with table 5 in section C.7.2 of the project specification for the relevant pavement layer.
label | Reference Documents: C.3.8c, C.7.2
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer / QAV
text | Date Completed:
checkpoint | 3.2 - Cut and Fill Tolerances
label | Frequency: Each Lot
label | Acceptance Criteria: The design surface levels are the levels on the completed earthworks including respread topsoil where applicable.
label | • The completed earthworks levels shall be –
label | a. within + 100mm to - 0mm of the design levels where there are no retaining walls; or
label | b. within + 50mm to - 0mm of the design levels where retaining walls exist, are proposed, or will exist in the future.
label | • Where material layer thicknesses are specified they shall be –
label | a. within + 100mm to - 0mm of the design thickness for Type A1 – Structural Fill (Sand), Type A2 – Structural Fill (Gravelly Sand) and any other material described as ‘sand’ or ‘structural fill’; or
label | b. within ± 50mm of the design thickness for all other material types.
label | Reference Documents: C.3.13
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | SCP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.3 - Subgrade level conformity
label | Frequency: Each Lot
label | Acceptance Criteria: Finished subgrade level tolerances to be + 5mm or - 30mm ( +0mm )
label | Reference Documents: C.7.4
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed, Survey report
label | SCP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.4 - Fill Material Compaction & Moisture Content Requirements
label | Frequency: Each Lot
label | Acceptance Criteria: Sub-grade shall be compacted to not less than 100% of the standard maximum dry density to a minimum depth below the surface of 300mm. The moisture content of subgrade is to be +/- 2% of Standard Optimum Moisture Content (OMC). Sub-grade to be formed to grade, crossfall etc. to ensure that an even thickness of pavement can be finally achieved.
label | • No further stage of construction to be commenced until the completed sub-grade has been inspected and approved by the Superintendant and the Local Authority.
label | Reference Documents: C.9.3
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - CBR Testing of Subgrade
label | Frequency: Each lot
label | Acceptance Criteria: Contractor shall test subgrade for minimum California Bearing Ratio (CBR) at frequency nominated in Table 5 to ensure the site CBR conforms to design pavement assumption. The minimum site CBR is to be 5%, unless noted otherwise.
label | Reference Documents: C.9.2
label | Inspection / Test Method: Test Point
label | Record of conformity: This ITP signed
label | HP
label | Responsibility: Site Engineer
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP