## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | GT4-ITP-013 - Precast Installation | itp |  |  |  | Yes | GT4-ITP-013 - Precast Installation
section | 1 - Preliminary Works
checkpoint | 1.1 - Check that current revision drawings are being used
label | Frequency: Prior to Commencing Work
label | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | Reference Documents: IFC Project Drawings/ Drawing Register
label | Inspection / Test Method: Document review
label | Record of conformity: Latest revision IFC drawings, ITP signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents: OHSMP, EMP, TMS, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
section | 2 - Material Conformance
checkpoint | 2.1 - Materials & source Approval - In-Situ Pits
label | Frequency: Prior to works commencing, 1 per delivery
label | Acceptance Criteria: Precast item resources and bedding specified or as shown on the Drawings.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: Receival inspection checklist
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.2 - Materials & source Approval - Pit Covers
label | Frequency: Prior to works commencing, 1 per delivery
label | Acceptance Criteria: Pit covers shall be either cast iron, precast concrete covers or gratings as per drawings and shall be constructed and fixed to pits in accordance with relevant Tasmanian Standard Drawings
label | Reference Documents: EW-CE-DRW-526-001 - Pit Schedule C.5.16
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: Receival inspection checklist
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 2.3 - Source In-situ Pit Material
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete shall be at minimum 28-day strength, F’c of 32 MPa and when placed shall be well rammed to ensure thorough consolidation.
label | Reference Documents: C.5.15
label | Inspection / Test Method: Verify
label | Record of conformity: Mix Design
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 3 - Installation
checkpoint | 3.1 - Bedding
label | Frequency: Each Lot
label | Acceptance Criteria: Foundation and/or bedding as per drawings and specifications
label | Reference Documents: EW-CE-DRW-526-001 C.5.15
label | Inspection / Test Method: Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 3.2 - Installation of Precast Element
label | Frequency: Each Lot
label | Acceptance Criteria: Precast element level and position confirm with the the deisgn drawings and specifications
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 4 - Cast Insitu Lids/Frames
checkpoint | 4.1 - Formwork
label | Frequency: Each Lot
label | Acceptance Criteria: Pit lids / surrounds shall be constructed to the detail shown on the drawings
label | Reference Documents: EW-CE-DRW-526-001
label | Inspection / Test Method: Inspection
label | Record of conformity: Concrete pour record and delivery docket
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 4.2 - Reinforcing
label | Frequency: Each Lot
label | Acceptance Criteria: Checks
label | – Position and spacing check
label | – Cover checked
label | – Reinforcing supports checked
label | – Laps at required length
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: Completion of prepour inspection checklist
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 4.3 - Concrete Pour
label | Frequency: Each Lot
label | Acceptance Criteria: Precast concrete cover or cast iron concrete infill as specified
label | Reference Documents: EW-CE-DRW-526-001 AS 3996
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer
text | Date Completed:
section | 5 - Post Pour Details and Inspections
checkpoint | 5.1 - Allowable Tolerances Level & Alignment
label | Frequency: Each Lot
label | Acceptance Criteria: The horizontal deviation of any piped or box culverted drain shall not exceed 25mm from the true alignment. There shall be no obvious sharp changes of direction.
label | • The maximum deviation from grade shall not exceed + or - 10mm for grades flatter than 1 in 500 and + or - 20mm for grades steeper than 1 in 500.
label | • The grade of any piped, box culverted, or open drain shall not exceed + or - 5% for grades flatter than 1 in 500 and + or - 10% for grades steeper than 1 in 500.
label | • Invert levels at structures shall not exceed + or - 10mm from the design invert.
label | • As-built survey completed for lot
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | SCP
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 5.2 - Backfilling Around Pits
label | Frequency: Each Lot
label | Acceptance Criteria: Backfilling to match pavement design and to occur min. 72 hours post concrete pour.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Inspection
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Sign ITP