## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP003 - Plant Mixed Foamed Bitumen Stabilised Pavements | itp |  |  |  | Yes | ITP003 - Plant Mixed Foamed Bitumen Stabilised Pavements | fed39c4a-7156-44be-bc9c-89ef599284e3
checkpoint-group | 1.0 Preliminary Activities
checkpoint-status | 1.1 - The current revision drawings are being used including subcontractors copy.
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex
label | Reference Documents - Aconex
label | Inspection / Test Method - Verify
label | Record of Conformity - This signed ITP
label | HP*
label | Responsibility - Fulton Hogan
checkpoint-status | 1.2 - Work Method Statement
label | Frequency - Prior to commencing works
label | Acceptance Criteria - No stabilisation works shall be commenced until the construction procedure for the stabilisation works including all required compliance test results is acceptable to, and approved by, the Administrator.
label | Reference Documents - MRTS09 cl.5.2
label | Inspection / Test Method - Verify
label | Record of Conformity - Approved Work Method Statement
label | HP
label | Responsibility - Fulton Hogan / AECOM
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 1.3 - Material Compliance
label | Frequency - Prior to commencing works
label | Acceptance Criteria - No material shall be incorporated into the works unless it has been demonstrated to the Administrator’s satisfaction that all the material to be used comply with all the requirements of the Technical Specification. Compliant test results noted below to be submitted to contract administrator: • Aggregates [Class 2 Crushed Rock (ex Fulton Hogan Tylden Quarry), Class 1 Crushed Rock (ex Holcim Oaklands Junction Quarry) and RAP (ex Melbourne Airport)] – Compliant with VicRoads Section 812. Coarse Aggregate compliant with 10-1 and fine aggregate compliant with 10-2.
label | Reclaimed Asphalt Pavement (RAP) – Use of up to 15% by mass of the aggregate
label | Primary Binder – Class 170 bitumen and penetration grade 70/100 complying with AS 2008. Minimum content is 2.5% of the dry mass density. Compliant with Table 10-3: o Expansion Ratio ≥10 o Half Life ≥20 seconds
label | Secondary Binder – GP Cement compliant with AS3972. Maximum cement content in is 2% by mass of dry mix Foaming Agent – Compliant with MRTS09 Water – Compliant with 10.5.6: o Total Soluble Salts ≤1,000mg/l o Chloride Ion ≤600mg/l o ≤ 400 parts per million of sulphate ion o ≤1% by mass of undissolved solids
label | Reference Documents - MRTS09 cl.7.1 & AECOM - MAP MP2.0 Spec. cl. 10.5
label | Inspection / Test Method - Verify / Test Results
label | Record of Conformity - Approved materials and material sources
label | HP
label | Responsibility - Fulton Hogan / AECOM
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 1.4 - Production Testing
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Supply information with respect to production testing of the unbound granular material utilised for the FBB mix.
label | Reference Documents - Cl.4 VicRoads Section 812 & AECOM - MAP MP2.0 Spec. cl. 10.5.1
label | Inspection / Test Method - TP
label | Record of Conformity - Approved Production Testing Results
label | TP
label | Responsibility - Fulton Hogan / AECOM
checkpoint-status | 1.5 - Mix Compliance
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The mix design report must be submitted to the Contract Administrator at least 7 days prior to the plant production trials for review. Approval of the mix design report prior to commencing the production trial is a HOLD POINT. The mix design report must include the requirements stated in cl 10.6.2 of the AECOM specification.
label | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.6.2
label | Inspection / Test Method - Verify / Test Results
label | Record of Conformity - Approved mixed design
label | HP
label | Responsibility - Fulton Hogan / AECOM
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 1.6 - Plant Production Trials
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor must undertake a production trial at their mixing plant to validate the approved Laboratory Design Mixture and to confirm the mix meets the requirements of the Specifications detailed in Table 10-5. The Contractor must issue an updated mix design report with the details of the Job Mixture (Laboratory Design Mixture modified) within 3 working days after completion of the production trial. Resilient Modulus: 1 test per mix design for plant production – Table 10-5 Requirements:
label | • 3-day-curing Resilient Modulus ≥1,000 • Soaked after 7-day curing Resilient Modulus ≥1,500 • Soaked after 14-day curing Resilient Modulus ≥1,800
label | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.6.1 Table 10-5 & 10.6.3
label | Inspection / Test Method - Verify / Test Results
label | Record of Conformity - Approved mixed design
label | HP
label | Responsibility - Fulton Hogan / AECOM
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 1.7 - Construction Trial
label | Frequency - Prior to commencing works
label | Acceptance Criteria - A trial section shall be constructed using the same construction plant, processes and methodology that it is proposed to be used for the remainder of the works. The trial section must be compliant with all testing requirements within the specification.
label | Reference Documents - MRTS09 cl.8.1.2.4 & cl.8.7.2.1
label | Inspection / Test Method - Verify / Test Results
label | Record of Conformity - This signed ITP
label | HP
label | Responsibility - Fulton Hogan / AECOM
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 1.8 - Foamed Bitumen Properties
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The bituminous stabilising agent shall not be incorporated into the material to be stabilised where the foaming properties of it do not comply with the requirements of the technical specification. The bitumen is to be tested at the start of each bitumen tanker and every 400T of production for the following parameters: Expansion ratio greater than 10 Half-Life greater than 20 seconds
label | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.5.3 & MRTS09 cl.8.8.5 Table 5.4
label | Inspection / Test Method - Verify / Test Results
label | Record of Conformity - Test Results
label | HP
label | Responsibility - Fulton Hogan / AECOM
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 1.9 - Stockpiling of Materials
label | Acceptance Criteria - Stockpiles shall be located on clear, even, firm, well drained ground and in a location where they can be clearly identified. All stockpiles shall be separated from other stockpiles by at least two metres and shall not be more than four metres high. The feedstock lot size is defined as 2500T.
label | The Contractor can delineate individual stock piles by either of the following methods: A.) Separate stock pile formed for each lot B.) Material of the same mix to be added to a single stockpile incrementally. Prior to adding the next portion of material, the initial/existing stockpile must be compliant with the specifications No stockpile that, in the opinion of the Administrator, is excessively wet shall be used in the stabilisation works.
label | Reference Documents - MRTS09 cl. 6.6 & MRTS05 cl. 7.7
label | Inspection / Test Method - Verify
label | Record of Conformity - This ITP signed
label | WP
label | Responsibility - Fulton Hogan / AECOM
checkpoint-status | 1.10' - Feed Stockpile Testing
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The following items must be tested for in the feed stockpile: Relative Moisture Ratio of Feed Stockpile: 4 tests per feedstock lot. Particle size distribution: 1 test per 1250T and a minimum of 2 tests per feedstock lot Fines Ratio: 1 test per 1250T and a minimum of 2 tests per feedstock lot Liquid Limit: 1 test per 1250T and a minimum of 2 tests per feedstock lot Linear Shrinkage: 1 test per 1250T and a minimum of 2 tests per feedstock lot Sulfate Content (water): 1 test per water source
label | Reference Documents - MRTS09 Cl. 8.8.6 & Table A2(c) & A3 AECOM - MAP MP2.0 Spec. cl. 10.5.6
label | Inspection / Test Method - Verify / Test Results
label | Record of Conformity - Test Results
label | TP
label | Responsibility - Fulton Hogan / AECOM
checkpoint-group | 2.0 Construction Process
checkpoint-status | 2.1 - Testing of FBB Material for Stabilising Agent Contents and Resilient Modulus
label | Frequency - Each Lot
label | Acceptance Criteria - Bituminous stabilising agent content: Recorded at least once per 100T with a minimum if one recording in any production shift. Secondary stabilising agent: Recorded once per 100T with a minimum of one recording in any production shift. Resilient Modulus: 0 to 5000T: 1 Test 5000 to 15000T: 1 Test 15000 to 30000T: 1 Test Beyond 30000T: 1 Test per 20000T
label | Reference Documents - MRTS09 Table A3
label | Inspection / Test Method - Verify / Test Results
label | Record of Conformity - Test Results
label | TP
label | Responsibility - Fulton Hogan / AECOM
checkpoint-status | 2.2 - Surface Preparation
label | Frequency - Each Lot
label | Acceptance Criteria - For all surfaces, preparation shall include the removal of all foreign and loose material. The Contractor shall ensure the surface onto which a stabilised layer is to be constructed is well compacted, trimmed and prepared before material for the overlying stabilised layer is placed.
label | Reference Documents - MRTS09 cl. 8.8.9.1 & 8.8.9.3
label | Inspection / Test Method - Verify
label | Record of Conformity - This ITP signed
label | WP
label | Responsibility - Fulton Hogan / AECOM
checkpoint-status | 2.3 - Placement of FBB
label | Frequency - Each Lot
label | Acceptance Criteria - The FBB is to be placed in a single layer. The maximum compacted thickness of an individual layer is 300mm. The minimum compacted thickness should be equal to the design thickness stated on the drawings. The surface level at the topmost FBB layer shall not deviate from design level at the specified points by 0mm,-10mm. Surface Levels to be picked up following profiling, and prior to placement of Asphalt.
label | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.7 & Table 6-3 MRTS09 cl. 8.9.5.2.2 & 8.9.5.3.1
label | Inspection / Test Method - Visual Inspection
label | Record of Conformity - Survey Report and Visual Inspection
label | HP*
label | Responsibility - Fulton Hogan
checkpoint-status | 2.4 - Proof Rolling
label | Frequency - Each Lot
label | Acceptance Criteria - Proof rolling of the completed layer must be undertaken at least 24 hours after the completion of the bitumen stabilised layer. The area must be uniformly covered with a minimum of 8 passes with either a pneumatic tyred roller or water cart not exceeding 6km/h.
label | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.8.3
label | Inspection / Test Method - Verify
label | Record of Conformity - This ITP signed
label | WP
label | Responsibility - Fulton Hogan / AECOM
checkpoint-status | 2.5 - Proof Rolling Report
label | Frequency - Each Lot
label | Acceptance Criteria - Proof roll report must be submitted to the Contract Administrator and Principal’s Design Consultant as soon as practical after completion of proof rolling.
label | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.8.7.2
label | Inspection / Test Method - Verify / Proof Rolling Report
label | Record of Conformity - Aconex
label | HP
label | Responsibility - Fulton Hogan / Principal’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 2.6 - Proof Roll Failure
label | Frequency - Each Lot
label | Acceptance Criteria - In the event of a failed proof roll the contractor must rectify the stabilised material to the extent and methodology identified in the proof rolling report. Area and depth of replacement to be agreed with CA prior to replacing.
label | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.8.7.3
label | Inspection / Test Method - Verify
label | Record of Conformity - This signed ITP
label | HP*
label | Responsibility - Fulton Hogan
checkpoint-status | 2.7 - Testing Requirements
label | Frequency - Each Lot
label | Acceptance Criteria - The foamed bitumen basecourse must be compacted to characteristic dry density ratio ≥98% modified compaction and a minimum of 4 test points per lot must be undertaken. Lots that contain in-situ material that failed the proof roll at subgrade level must be compaction tested in the location of the failed proof roll.
label | Characteristic Construction Moisture Content to be within the limits of 60 – 80% and a minimum of 4 test points per lot must be undertaken.
label | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 5.10.3.2, 10.8.3, 10.8.4 & MRTS09 Table A3
label | Inspection / Test Method - Verify / Test Results
label | Record of Conformity - This ITP signed
label | TP
label | Responsibility - Fulton Hogan
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP