## Sheet1
checklist | Exterior Balconies /Tiling (V3) | key
section | Substrate Check |  | existing checklist
checkpoint | Adequate drying time has elaspsed |  | add to checkist
checkpoint | Substrate, finish/fall correct as per design and perimeter angle installed
checkpoint | General phots and obsevations during installation
checkpoint | Approval to install tanking - Consultant & Council inspections carried out
section | Tanking Installation
checkpoint | Product checked and correct as per specification
checkpoint | All prestart checks completed and approval given to install
checkpoint | Matt installed as per product specification
checkpoint | General photos, comments and observations during install
checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint | Tanking to area completed, checked and approved as per specifications
checkpoint | Initial testing complete
checkpoint | Any remedials completed
holdpoint | Request Signoff from façade engineer
holdpoint | Request signoff from architect
holdpoint | request signoff from Manufacturer
checkpoint | Area protected
Section | Downpipes & Deck Outlets
checkpoint | Downpipes installed & Complete with Brackets & ring clamps
checkpoint | Trade QA received ad reviewed
checkpoint | Deck outlet grates and locking clamps installed
checkpoint | Council inspection completed & past
checkpoint | Handed over to Clients Tiler
Section | Tiling
checkpoint | Correct jacks being used as per specification
checkpoint | Correct tiles ( type/colour ) confirmed
checkpoint | All tiles have been installed and deck finished
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Archtects inspection complete