## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Townhouse Exterior Works |  |  |  |  | Yes | Townhouse Exterior Works | 01529ac1-6930-4fb4-8969-8fd638ccfd3e
checkpoint-group |  |  | section | TH-Exterior Balconies Waterproofing
checkpoint-status |  |  | checkpoint | Waterproofing completed and water tested
holdpoint |  |  | signoff | Request inspections
checkpoint-status |  |  | checkpoint | Inspections complete
boolean | f5ef1179-daf8-5039-a8f3-a22a54866cc6 |  | tickbox | Façade engineers remedials complete and signed off
boolean | b564fac2-56dd-50fa-a9cf-0c804fd85128 |  | tickbox | Architects remedials complete and signed off
boolean | e0889773-7eba-5b57-b79d-490e0d6e6ad4 |  | tickbox | Council remedials complete and signed off
checkpoint-group |  |  | section | Fabworx Blaustrades
checkpoint-status |  |  | checkpoint | Waterproofing installed and signed off
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Spot check with Subcontractor - Installed in correct place and correct fixings
checkpoint-status |  |  | checkpoint | Request Inspections
boolean | c3c11b64-8c8e-536e-8a24-8ce37da07e4c |  | tickbox | Façade engineers remedials complete and signed off
boolean | 28ae4f55-c374-5b77-993f-4f309fb652c1 |  | tickbox | Architects remedials complete and signed off
boolean | 2cc9df0a-3381-5d4c-94e3-7da92327cb63 |  | tickbox | Council remedials complete and signed off
boolean | 91f90248-d0a2-55f6-b064-63ab76596760 |  | tickbox | Structural engineer remedials completed
checkpoint-group |  |  | section | Deck Framing
checkpoint-status |  |  | checkpoint | Correct jacks being used as per specification
checkpoint-status |  |  | checkpoint | Correct size/treatment bearers and fixings to jacks used
boolean | d2e93f50-768f-5113-854a-90c3292839fc |  | tickbox | Position checked
boolean | 6b0e9bf1-14ba-558c-85f5-cedc44a93cc2 |  | tickbox | Reduced levels at top of bearers checked
boolean | 88fc1db5-7f19-5354-ab1d-e6cc89bf6384 |  | tickbox | Approval given to install timber joists
text | 7970277e-e923-561e-9d36-118d341b4b31 |  | textbox | Relevant Drawing Numbers & Revisions
checkpoint-status |  |  | checkpoint | Correct joist size /teatment installed
boolean | ab583f49-f3b9-55dc-9e10-b94c96bc87e9 |  | tickbox | Dimensions / locations checked and accurate
boolean | a534b384-bc70-5187-bece-0679a8cfec96 |  | tickbox | All frames are square & Level
boolean | 3ebfd8bb-76a0-55bf-b475-cdc88ab6f27b |  | tickbox | Fixings are correct type and installed correctly
boolean | bbe92582-1ba2-5b11-a191-3ac4d46e8649 |  | tickbox | Any bracing requirements installed
checkpoint-status |  |  | checkpoint | General additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
boolean | 3dc40be3-f72c-5b27-9c26-b4d5b8ca6ef2 |  | tickbox | Architects remedials complete and signed off
boolean | da8915c2-7a0a-5289-ab98-ddab36fc79c5 |  | tickbox | Council remedials complete and signed off
holdpoint |  |  | signoff | Request Inspections
checkpoint-group |  |  | section | Intertenancy Screens
checkpoint-status |  |  | checkpoint | Waterproofing installed and signed off
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Spot check with Subcontractor - Installed in correct place
checkpoint-group |  |  | section | Timber Decking
checkpoint-no-status |  |  | checkpoint | Review orentation of decking
text | e0875997-00a0-54cd-a582-99eab08da22c |  | textbox | Relevant Drawing Numbers & Revisions
holdpoint |  |  | signoff | Review orentation of decking
checkpoint-status |  |  | checkpoint | Installation of timber decking
boolean | 89be6a81-13d1-5606-9359-897596f556af |  | tickbox | Dimensions / locations checked and accurate
boolean | 502317f3-bf6a-5861-bd82-f912035acb94 |  | tickbox | All frames are square & Level
boolean | cc0c64b5-8513-51cb-b1c2-8998bb87e4ec |  | tickbox | Fixings are correct
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request trades QA / Signoff
checkpoint-no-status |  |  | checkpoint | Request Inspections
boolean | 86a770b9-56c7-5b5a-afa6-0233fdb68316 |  | tickbox | Architects remedials complete and signed off
boolean | 7c976c1d-33a7-512d-ad55-69684027afa0 |  | tickbox | Council remedials complete and signed off
holdpoint |  |  | signoff | Request Inspections
checklist-sectioned |  |  | checklist | Pour - |  |  |  |  | Yes | Concrete Pour Checklist - Suspended Floors - QA | 0551aa1e-960d-447f-9b0a-eeec8fa6254c
checkpoint-group |  |  | section | Pre Pour
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | 93770ec4-6d35-4679-8ac0-e8b38ea2a88e |  | textbox | Drawing reference:
text | 40ccf95e-506a-4bb6-a694-aff83a0a3ad1 |  | textbox | Subcontractor:
checkpoint-status |  |  | checkpoint | Formwork Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Penetrations located/boxed & approved
checkpoint-status |  |  | checkpoint | Reinforcing Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Reinforcing Install completed and reviewed
boolean | 3cb924d9-b168-4a2b-8d27-2f7e3e52dc4a |  | tickbox | Reinforcing - Size and type correct to specification
boolean | bfecbf94-de2a-499a-9bed-0e94d553650f |  | tickbox | Reinforcing - spacing and location correct
boolean | baa5b081-6ef9-46cd-8341-687756568f07 |  | tickbox | Specified covers checked/correct
boolean | 2de63ccc-702a-40b9-8022-461fdbe15807 |  | tickbox | Splice laps checked/correct
boolean | ac4eeade-fef5-4711-b2d0-f60a63d8d8ce |  | tickbox | Any starter bars are installed correctly (location, size and spacing )
boolean | 619836ff-f665-4eb4-b366-06b00af6e7e7 |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Structural Steel cast in plates installed/ checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Bottom of foundation is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | All services completed
checkpoint-status |  |  | checkpoint | Engineer informed of pour, checks completed (see Holmes folder and ensure observations are closed out)
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
checkpoint-status |  |  | checkpoint | Trades Post Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour checks completed and any remedial work closed out
checklist-flat |  |  | checklist | Daily Site Report - Facade Works |  |  |  |  | Yes | Daily Site Report - Facade Works | 07ece856-3762-4438-ab6e-5585fd0372b9
checkpoint-status |  |  | checkpoint | Hours Worked & Weather Conditions Recorded
text | 162c0462-b2ea-4451-9254-0fd1fae9819a |  | textbox | My Hours Worked (start & finish)
select | 16970da8-a201-45e0-995f-3704a8e9e5df |  | dropdown | Weather Conditions AM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
select | 31e987da-73ef-4975-aaed-fb802080b858 |  | dropdown | Weather Conditions PM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
checkpoint-status |  |  | checkpoint | Visitors to Site (Record name, company & purpose)
checkpoint-status |  |  | checkpoint | Site Instructions Issued (Any relevant site instructions issued are documented here)
checkpoint-status |  |  | checkpoint | Day Works Agreed (Any relevant Day Works issued are documented here)
checkpoint-status |  |  | checkpoint | Subcontractors on site (all recorded area, man power, name)
button | 50dd3d18-5adc-4f2b-8bb5-cc68bd10f19b |  | button | Onsite (Terracotta) -Area & Manpower | yes, no
text | 1b61c1f9-044d-4af0-b132-79a1bc1c4442 |  | textbox | Area Working ( Onsite)
text | 563bbcce-53dd-4379-8964-46217f1779a6 |  | textbox | Manpower (Onsite)
button | a581eb2d-05d3-4679-8125-a5ef79ea05c6 |  | button | Nebulite Windows - Area & Manpower | yes, no
text | 4d37bb46-a431-4fc0-a63b-9a07aaf8312d |  | textbox | Area Working (Nebulite)
text | 154ee8a2-b8df-4d9b-9970-27ad7e711217 |  | textbox | Manpower (Nebulite)
button | 7d2eb628-5c08-45fb-bb2a-8860765be69a |  | button | Sto- Area & Man power | yes, no
text | 973c4fcd-c332-4eb2-b11a-aac40e8fc4cf |  | textbox | Area Working Sto
text | 6c63056f-90d0-4b1c-a80a-3f84a2bf7e23 |  | textbox | Man Power (Sto)
button | 2dcff094-cc32-4f40-9fa2-2fecdcb24da7 |  | button | Fabworx ( metalworks)- Area & Man power | yes, no
text | e423daee-b37f-488b-9da2-be7352beaed4 |  | textbox | Area Working (Fabworx)
text | 2aa82af2-14be-4f96-8df8-6bfe413205b4 |  | textbox | Manpower (Fabworx)
button | daff4701-b5c8-49f7-b9b1-28e411512e3f |  | button | Metro Glass ( Balustrade & Canopy) | yes, no
text | fa558aef-d79f-4994-87a3-697e68dc4a1f |  | textbox | Area Working (Metro Glass)
text | 3b6dfea8-757a-482c-bcef-213c4334dfc3 |  | textbox | Manpower (Metro Glass)
button | 714c5ff0-2835-4e49-b673-179517bea1bb |  | button | Turfrey- Roof - Area & Manpower | yes, no
text | ef40a19f-1825-4c7d-a23b-b47d41d9aec9 |  | textbox | Area Working Turfrey
text | 898e4006-db9d-4b42-8a39-e6898b5114bc |  | textbox | Manpower (Turfrey - Main steel )
button | 5a0b7913-1a31-473c-858e-87f2f4cab9ff |  | button | Arid Waterproofing- Area & Manpower | yes, no
text | 0fd360bb-3976-4099-9d0b-610aaf3e4eed |  | textbox | Area Working (Arid)
text | e3545888-e105-4cde-9a77-3ac836626a24 |  | textbox | Manpower (Arid)
button | 3e672956-dc6b-465b-860e-7b1e48ef9b4c |  | button | Jensen - secondary steel Area & Manpower | yes, no
text | 8b42ad50-15e5-45c3-bc89-cdfb172ba3a6 |  | textbox | Area Working -Jensens sencondary
text | 8350261f-2bdc-448e-bf10-23057dd62ac3 |  | textbox | Man Power (Jensen secondary steel)
button | 904c2a4c-bca7-48ef-8023-f720cb34b030 |  | button | Hawkins carpentry- Name, Area & Manpower | yes, no
text | 0d3b0443-27e6-48c8-8d84-2a89ceba598c |  | textbox | Area working hawkins carpentry
text | 63fbe77e-7830-4f6b-b7eb-52091095a12a |  | textbox | Manpower hawkins carpentry
button | 0f4fe906-1c9b-4106-be32-bab6fe287341 |  | button | Alpha - Area & Manpower | Yes,No
text | e0200942-5786-447e-8de2-7dd9af3d11da |  | textbox | Area Working - Alpha
text | 166675eb-e8cf-4460-80b6-32ca5e10bc6c |  | textbox | Manpower (Alpha)
button | f1042130-ecda-4a82-914a-058d5b4190da |  | button | Metro Commercial - Area & Manpower | Yes,No
text | 527fe805-ae12-497a-840c-7fad8bf4c9c4 |  | textbox | Area working - Metro Commercial
text | f3832e11-e437-4607-8374-50e0b563e401 |  | textbox | Man Power (Metro Commercial)
button | 9243f10e-a9d2-4d08-9811-4479d07b79e8 |  | button | Tony Tie - Area & Man Power | Yes,No
text | 8a9b0b31-ca8e-448c-a77c-748bc16be152 |  | textbox | Area Working (Tony Tie)
text | 0aa1c33b-9c00-4893-b0ff-7e56cb8ffb73 |  | textbox | Manpower (Tony Tie)
button | d37f82cf-3804-429f-9a3d-ac2d5b61a458 |  | button | Trade - Name, Area & Man power | yes, no
text | 9bd5dd7e-c57c-4f46-8c91-bc849ae3de6a |  | textbox | Company
text | c88524ff-351f-4c8c-876f-0061b9d1c078 |  | textbox | Area
text | 6cbcf452-d4e1-4ae9-b384-9a83cf62dd75 |  | textbox | Manpower
button | 115b5574-9c06-49bb-9f21-dec51aaeab55 |  | button | Trade- Name, Area & Man power | yes,no
text | 977a8c01-25c2-48b1-a99c-74db65b08a80 |  | textbox | Company
text | 4fd1acad-850b-40e4-be6f-27745d597352 |  | textbox | Area
text | 66c862ee-7489-409a-b956-5b5793246442 |  | textbox | Manpower
button | 25627f65-3916-4380-922b-75b7a70eb452 |  | button | E&S Builders - Area & Man Power | yes,no
text | 3567ed0e-4e86-4e51-a168-f8448227a369 |  | textbox | Area Working (E&S Builders)
text | 0b485563-820b-461a-aebb-51bc721ae282 |  | textbox | Manpower (E&S Builders)
checkpoint-status |  |  | checkpoint | Subcontractors contacted today (document name & date trade is required / conversation details)
checkpoint-status |  |  | checkpoint | Progress (quantities & location) - include photos
checkpoint-status |  |  | checkpoint | Unsatisfactory Progress - include photos (Fail if of serious concern - Pass once resolved)
checkpoint-status |  |  | checkpoint | Subcontractor/Supplier -Items delaying progress (Fail if of serious concern - Pass once resolved)
checkpoint-status |  |  | checkpoint | Design - items delaying progress
checkpoint-status |  |  | checkpoint | Disruption /Mitigation (subcontractor / design)
checklist-sectioned |  |  | checklist | Townhouse Preclosure Inspections |  |  |  |  | Yes | Townhouse Preclosure Inspections | 0873449c-aeb5-4a12-a976-bbb4c0591d4e
checkpoint-group |  |  | section | RAB
checkpoint-status |  |  | checkpoint | RAB board installed & complete (pass once below all signed off)
boolean | 3c297e67-fad8-5a8c-bc52-c0ab8bdcae7c |  | tickbox | Correct fixings type & patterns/Spacing
boolean | 71ec63c6-a6e5-52e8-aed8-c4bbaa75dde9 |  | tickbox | Flashings installed checked and correct
boolean | 29a5b5a1-bb47-5f3d-b067-b2afd85ef5a8 |  | tickbox | All joints/penetrations/openings taped as per specs
boolean | 4f7ae6b4-e0b7-51d6-ba58-6a4d865b9d65 |  | tickbox | Services checked, type and location
checkpoint-status |  |  | checkpoint | RAB QA received, reviewed, attached and approved
holdpoint |  |  | signoff | RAB Request inspection by Façade Engineer/Architect/Council
checkpoint-status |  |  | checkpoint | RAB inspections by Architect done & signed off
boolean | ee008992-84c2-52cc-b8c3-0b0810c4b4ba |  | tickbox | RAB Façade engineers remedials done and signed off
boolean | 59d1115b-c35b-5e79-990e-197773308193 |  | tickbox | RAB Architects remedials done and signed off
boolean | 59b080fd-65f9-5536-8c57-b8fb877081ce |  | tickbox | RAB Council inspections carried out any remedials done
checkpoint-group |  |  | section | Building Wrap & Flashing Tape Installed
checkpoint-status |  |  | checkpoint | RAB board installed and signed off
checkpoint-status |  |  | checkpoint | Building wrap and flashing tape installed
boolean | bb4c3fa2-5760-5a81-a16a-715a70f0859d |  | tickbox | Correct fixing types & Pattern/Spacing
boolean | fa1a2098-15d8-5d53-8af3-35c1f7d4786d |  | tickbox | Flashings installed checked and correct
boolean | 5c9d74ef-04da-5ca5-82a4-112683f119ed |  | tickbox | All joints/penetrations/openings taped as per specs
boolean | bfceff88-3520-5e9d-963e-77050d477340 |  | tickbox | Services checked, type and location
checkpoint-status |  |  | checkpoint | Building Wrap QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Requst Inspection by façade enigneer /Council and Architec
checkpoint-status |  |  | checkpoint | Building Wrap Inspections
boolean | 1518d860-60ba-59c4-890d-78cb4575aa53 |  | tickbox | Building Warp - Architect remedials completed and signed off
boolean | f7e69853-fe27-59d2-b3ec-6a1c8c6f3a9e |  | tickbox | Building Wrap - Façade engineers remedials done and signed off
boolean | 0ee24999-fd2f-5e3b-aadc-f357873fbeda |  | tickbox | Building Wrap - Council inspection carried out and any remedials complete
checkpoint-group |  |  | section | Cavity Batten - Espan Area
checkpoint-status |  |  | checkpoint | Building wrap and flashing tape installed and signed off
checkpoint-status |  |  | checkpoint | Cavity batten correct type and fixings installation completed, checked and approval to clad
boolean | 3f25efcd-09dc-5ccf-bacc-74a555f24c45 |  | tickbox | Appropriate fixings for cavity (as per design)
boolean | a81a3e7c-7981-55dc-bd0d-a225743b17ae |  | tickbox | Service penetrations complete
checkpoint-status |  |  | checkpoint | Cavity Batten QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Cavity Batten - Request inspection
checkpoint-status |  |  | checkpoint | Cavity Batten - Inspection architect done and signed off
boolean | 823e015c-d656-5340-ae22-5898a28828c4 |  | tickbox | Cavity Batten - Façade remedials complete and signed off
boolean | e10c12d6-6400-5fd1-8adc-089448213c66 |  | tickbox | Cavity Batten - Architects remedials done and signed off
boolean | f2a07346-314a-5d19-9247-58e149cc5af2 |  | tickbox | Cavity Batten - council remedials complete and signed off
checkpoint-group |  |  | section | Cavity Batten - Axon Areas
checkpoint-status |  |  | checkpoint | Building wrap and flashing tape installed and signed off
checkpoint-status |  |  | checkpoint | Cavity batten correct type and fixings installation completed, checked and approval to clad
boolean | 3c6316d5-869c-5fed-9c62-970e622d9635 |  | tickbox | Appropriate fixings for cavity (as per design)
boolean | ef136997-4b8d-574c-8a58-c2fe9c7222af |  | tickbox | Service penetrations complete
checkpoint-status |  |  | checkpoint | Cavity Batten QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Cavity Batten - Request inspection
checkpoint-status |  |  | checkpoint | Cavity Batten - Inspection completed and signed off
boolean | 9df6bec2-e422-5c61-a7a5-5d06385d3b41 |  | tickbox | Cavity Batten - Façade remedials complete and signed off
boolean | 48df275d-750d-58a0-96c6-94baaca264b7 |  | tickbox | Cavity Batten - Architects remedials done and signed off
boolean | de8c7e9e-bd31-524e-82e2-86187dedf0cc |  | tickbox | Cavity Batten - council remedials complete and signed off
checkpoint-group |  |  | section | Cavity Flashings
checkpoint-status |  |  | checkpoint | Cavity battens installed and signed off
boolean | 5ba29807-e076-5fc4-9b61-d3881f87e212 |  | tickbox | Correct material ordered
checkpoint-status |  |  | checkpoint | Flashings Critical Lines
text | 08d4469c-9017-5184-88c4-402cad98e468 |  | textbox | Number,Location , elevation
checkpoint-status |  |  | checkpoint | Cavity flashings QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Cavity flashings Ssot check with Subcontractor - Installed/fixed in correct place
holdpoint |  |  | signoff | Request Cavity flashings inspections - Architect/Façade engneer
checkpoint-status |  |  | checkpoint | Cavity Flashings Archtiect/Façade Engineer Sign off
boolean | 4acacacd-fd8b-5bf7-9c6f-3dd48c6ae1b6 |  | tickbox | Façade engineers remedials done and signed off
boolean | 25967ae4-8a16-56e1-9750-846c729462e0 |  | tickbox | Architect remedials completed and signed off
checkpoint-group |  |  | section | Soffit Install - Level 1 & 2
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
boolean | 59e856fb-4f2f-5e20-9111-b66eea2612a4 |  | tickbox | Soffit Framing completed, checked and accurate inclusing sheet joins/blocking
boolean | abafcf83-a8e2-506e-a96b-d2b6ac0bc988 |  | tickbox | Relevant services first fix and nogging completed
checkpoint-status |  |  | checkpoint | General photos, comments and observations during installation
holdpoint |  |  | signoff | Consultant/Council Inspections requested
checkpoint-status |  |  | checkpoint | Inspections completed
boolean | 79a497eb-bbec-5868-b0ac-7bc41ab8f91c |  | tickbox | Façade engineers remedials done and signed off
boolean | 4a81513f-2a2a-5edf-ba6a-09fc81ecbdef |  | tickbox | Architect remedials completed and signed off
boolean | bed2ff5b-0d21-5cdf-a13d-aceac539e29f |  | tickbox | Council inspections complete
boolean | f2f0afab-defe-5e5a-9b28-bcd9afa0847e |  | tickbox | Steel studd engineer remedials completed and signed off
checkpoint-group |  |  | section | Metal Roof underlay etc
checkpoint-status |  |  | checkpoint | Roof underlay installed - ply and confirmed ok to fix over
checkpoint-status |  |  | checkpoint | Correct wrap used and fixed as per specification
checkpoint-status |  |  | checkpoint | Cavity battens installed at correct spacings and fixings for Windloading
checkpoint-status |  |  | checkpoint | Product checked and correct as per specification including fixings for windloading
checkpoint-status |  |  | checkpoint | All prestart checks completed and approval given to install Veedek
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Relevant Services considered, checked and approved where applicable
holdpoint |  |  | signoff | Approved for roofing install Signoff
checkpoint-group |  |  | section | Gutters Install
checkpoint-no-status |  |  | checkpoint | Install
boolean | 55165129-e796-5ee5-8d3b-44c6b5fcec7a |  | tickbox | Support framing complete
boolean | a6e68002-f90d-5f4a-98e9-e1753e26a313 |  | tickbox | Spot checks done on falls
boolean | 4e49edfd-b4d0-50e2-8855-528f5461d11e |  | tickbox | Material order made
boolean | ebe21bfa-6ac8-50b8-94e6-c6c0b9c44121 |  | tickbox | Where required waterpoofing complete
checkpoint-status |  |  | checkpoint | General comments and photos of additional paint application
checklist-sectioned |  |  | checklist | Site Sound Readings |  |  |  |  | Yes | Site Sound Readings V2 - H&S | 0aef8cbd-4efe-463f-aac6-e37e77a01e75
checkpoint-group |  |  | section | General Information
checkpoint-status |  |  | checkpoint | General Information (Pass once recorded below)
text | b0e3fc79-c6ae-4d8e-bdc3-c0c86f0391d7 |  | textbox | Date
text | 73cad199-9b52-4d52-b931-d1e171063c4c |  | textbox | Time
label | ea1abf95-db1b-4001-aa1c-5f69b1ab594a |  | note | Equipment Make : Plusar 49K
label | 139cfc4a-7ce3-4e11-ac0b-ef4d5fed1816 |  | note | Sound Level meter :Model 43
label | 17e99f30-2e00-4bda-9da0-e43e6daf1067 |  | note | Microphone: Class 1 PM1
label | 87c6998b-6b86-4914-82a1-b62d97f14de8 |  | note | Sites 2 & 5 deleted
text | c320dd80-f339-4cbd-a0f7-b12c940be1b2 |  | textbox | Decription of sound source- Construction Noise
text | 88792bf5-e45a-4054-b0f9-3589dc56c001 |  | textbox | Weather
text | 5e823765-065b-42a7-b204-f6ebcec07bf9 |  | textbox | Wind speed
text | bac232c9-fb64-4e7b-ab86-c978a0612ac6 |  | textbox | Wind direction
text | 24e8b331-00d2-4017-85c8-0160dee5befc |  | textbox | Max Gust Speeds
text | a92a78da-a174-4983-99ff-58e1f607be67 |  | textbox | Cloud cover
text | 5dfa6e62-71d1-4c50-abf2-f711a169bd68 |  | textbox | Temp
text | 3cd0f9cc-ec91-4cd4-b15d-954fd6550277 |  | textbox | Visibility
checkpoint-group |  |  | section | Test Results
checkpoint-status |  |  | checkpoint | Site 1- Pure Print Carpark (Time elasped)
label | 5a3ceaf9-83b8-4a42-9a9f-445dd71bd120 |  | note | Sound Observations
text | da642fd1-daa4-46ac-99fe-7939ebe32f96 |  | textbox | 00.00 dB(A) Leq
text | bf7cc87b-532c-4d0d-a5ef-a71e514c5e96 |  | textbox | 00.00 dB(A) Lmax
text | 8c6cd4e8-8d3f-4cc6-a88f-0892d394e9ea |  | textbox | 01.00 dB(A) Leq
text | 8deff514-2d66-4ee9-80f1-1bef9269fd77 |  | textbox | 01.00 dB(A) Lmax
text | 994c96c7-20d3-4208-b299-34373d3bc9de |  | textbox | 02.00 dB(A) Leq
text | 20de4c6a-7cde-43a9-8062-bb17c41efa6f |  | textbox | 02.00 dB(A) Lmax
text | a7458e62-36ac-4372-a8d3-b821ae74201d |  | textbox | 03.00 dB(A) Leq
text | a557cf49-d3de-408b-9322-a948872c42f3 |  | textbox | 03.00 dB(A) Lmax
text | c1ed420d-5e52-4ec4-b124-1bb439b1b860 |  | textbox | 04.00 dB(A) Leq
text | d9e703e1-41cc-4702-994e-2b794c9cd218 |  | textbox | 04.00 dB(A) Lmax
text | 402385ba-931c-4399-abec-8c12440db53e |  | textbox | 05.00 dB(A) Leq
text | 24a755f1-3f37-4c45-8e15-30196ca2acf7 |  | textbox | 05.00 dB(A) Lmax
text | fd84f99b-18bd-4566-a246-180de911d8e6 |  | textbox | 06.00 dB(A) Leq
text | b66390ef-33e1-4593-b20b-1d8a714f7df8 |  | textbox | 06.00 dB(A) Lmax
text | 1495b1f6-774c-4374-93c6-2b0f19ddb275 |  | textbox | 07.00 dB(A) Leq
text | 3379c2a2-eea2-429b-9131-3a3576d1753a |  | textbox | 07.00 dB(A) Lmax
text | d868fa1f-ec69-49de-80e6-eae352da008e |  | textbox | 08.00 dB(A) Leq
text | 465682da-69ca-4c26-826e-922e4f9ca441 |  | textbox | 08.00 dB(A) Lmax
text | d730160d-d321-4aa7-8dbe-2aab885c01b1 |  | textbox | 09.00 dB(A) Leq
text | 898777f6-1f23-4b28-bf20-d3738638850a |  | textbox | 09.00 dB(A) Lmax
text | 55f08986-0e9f-43b3-9f30-1d7cd17a2e1c |  | textbox | 10.00 dB(A) Leq
text | b7af74ad-3580-4007-8d30-7970d9b86e88 |  | textbox | 10.00 dB(A) Lmax
text | 0d86b466-340f-492d-91c6-491d8aeb811f |  | textbox | 11.00 dB(A) Leq
text | 5f6b3530-2f0c-4aee-b84d-a7f077024bcf |  | textbox | 11.00 dB(A) Lmax
text | 14e07de8-8f22-4c23-b331-51b877ec7084 |  | textbox | 12.00 dB(A) Leq
text | a096a01e-15f6-4abf-af59-c1957a468ab0 |  | textbox | 12.00 dB(A) Lmax
text | 1cc06c0b-6505-4702-89ad-dc2c0d61ca7e |  | textbox | 13.00 dB(A) Leq
text | 4f16ca85-f1c4-46b9-8053-010d9315b3c2 |  | textbox | 13.00 dB(A) Lmax
text | 507f555c-39bd-46a9-b8d4-4cdbc2a9ef81 |  | textbox | 14.00 dB(A) Leq
text | abe839d5-160f-496b-a0fb-aa99c9431c11 |  | textbox | 14.00 dB(A) Lmax
text | ec63742e-dc4f-4f9f-9952-e8ee9720c35a |  | textbox | 15.00 dB(A) Leq
text | ba4ef872-2538-4a42-bc63-f1af995ed31c |  | textbox | 15.00 dB(A) Lmax
checkpoint-status |  |  | checkpoint | Site 3- 6 Elizabeth Street- Grass area - (Time Elapsed)
label | 237bcdc5-5efc-4a14-ba86-47d2d2984d3d |  | note | Sound Observations
text | e8373c88-fd7e-476c-b2bf-89d65087a9c8 |  | textbox | 00.00 dB(A) Leq
text | 8953a061-6874-41a8-9421-7fcd2fdfab40 |  | textbox | 00.00 dB(A) Lmax
text | 3210379c-fd1d-467c-aef6-0858dce14a52 |  | textbox | 01.00 dB(A) Leq
text | 86c3a5da-9919-4691-9fb9-a9f8a9f7c58d |  | textbox | 01.00 dB(A) Lmax
text | 38418845-aba1-472b-9a11-be5497c5e2c8 |  | textbox | 02.00 dB(A) Leq
text | 6f75f9a3-3045-488a-ab42-b449e554b753 |  | textbox | 02.00 dB(A) Lmax
text | 05df0ba2-87de-4560-9401-ee3508e7a426 |  | textbox | 03.00 dB(A) Leq
text | 77a4fa1d-88d0-4d6e-9b07-7dcdc18d7eaf |  | textbox | 03.00 dB(A) Lmax
text | d22ae9fb-59b7-4c8a-b8f7-233bf68e67be |  | textbox | 04.00 dB(A) Leq
text | 97bda32b-12dd-47b3-be17-567bfbcfe81d |  | textbox | 04.00 dB(A) Lmax
text | 5dff2c1e-b1eb-4a5f-b0aa-3ec74d9cec98 |  | textbox | 05.00 dB(A) Leq
text | 6705be1e-2197-4893-9126-b91c9372dced |  | textbox | 05.00 dB(A) Lmax
text | 9c3b7414-2be8-43bb-abae-8221cc3a442a |  | textbox | 06.00 dB(A) Leq
text | db6cbcab-e176-4a3f-be9a-7e1932bb4b2d |  | textbox | 06.00 dB(A) Lmax
text | 16018001-7bbf-4155-85e8-160a111a3c3a |  | textbox | 07.00 dB(A) Leq
text | 2f715469-c37b-48fa-8eca-ebaf14cfe180 |  | textbox | 07.00 dB(A) Lmax
text | 7fb59f71-d821-49d0-b560-0788d0f21755 |  | textbox | 08.00 dB(A) Leq
text | a118116f-0b61-4924-b3e3-2526f9a2ee47 |  | textbox | 08.00 dB(A) Lmax
text | 42477f2e-e493-4925-8d44-13c871107667 |  | textbox | 09.00 dB(A) Leq
text | 78f068be-4ce4-47a5-ad15-7b9d45c1d848 |  | textbox | 09.00 dB(A) Lmax
text | cda50e48-1f3e-4cb3-85d2-29e19946f006 |  | textbox | 10.00 dB(A) Leq
text | 77d73367-fba8-4bc6-8c7e-b08386e4cfc7 |  | textbox | 10.00 dB(A) Lmax
text | eed451d9-d36f-4269-87d7-4029708e4d2a |  | textbox | 11.00 dB(A) Leq
text | 4194c129-34f6-4e7b-bdb3-5e4eb04546ef |  | textbox | 11.00 dB(A) Lmax
text | 630d381e-87ce-4ff2-9d65-75bbdac7b15e |  | textbox | 12.00 dB(A) Leq
text | 014883d2-f73f-4838-8279-77b8793c836a |  | textbox | 12.00 dB(A) Lmax
text | 854b894d-0a2b-44c1-8520-6f7530350ce2 |  | textbox | 13.00 dB(A) Leq
text | 267d9d63-0180-43f1-9021-3e90f9550d0c |  | textbox | 13.00 dB(A) Lmax
text | f620c997-c46f-43f4-8d38-24c99827d587 |  | textbox | 14.00 dB(A) Leq
text | 74d61ac2-c55b-49ee-8247-5888118e854b |  | textbox | 14.00 dB(A) Lmax
text | 006b7f61-e438-41e3-bcf8-664a965023dc |  | textbox | 15.00 dB(A) Leq
text | 1f941fb8-0d7b-48c3-8d05-280f3e16ecf3 |  | textbox | 15.00 dB(A) Lmax
checkpoint-status |  |  | checkpoint | Site 4 -Coffee Club Elizabeth Street
label | 21a610ac-cd2d-4d97-8d92-7dfd9ff5f21a |  | note | Sound Observations
text | 8afa6310-e3bb-4602-9937-0c55534cf909 |  | textbox | 00.00 dB(A) Leq
text | cb6d546a-cc6a-437f-9bdc-efe29fb1a961 |  | textbox | 00.00 dB(A) Lmax
text | 18e3a5a7-9d13-429d-b48f-8a612a66be84 |  | textbox | 01.00 dB(A) Leq
text | 6844e54f-3e34-4ceb-832b-f927af0bb2b5 |  | textbox | 01.00 dB(A) Lmax
text | 394a82b7-cbe5-4a3b-a2af-64799ef8ff96 |  | textbox | 02.00 dB(A) Leq
text | 447b5273-447f-4b92-b828-04b4afe6cfb1 |  | textbox | 02.00 dB(A) Lmax
text | f0240d83-b6c1-4853-a6d8-9d56cf6747f3 |  | textbox | 03.00 dB(A) Leq
text | 75cc4480-f277-42e4-b73f-90ecd2c0da13 |  | textbox | 03.00 dB(A) Lmax
text | de9eb5cf-2a52-4d2e-9133-cc7fa275723f |  | textbox | 04.00 dB(A) Leq
text | d7c7a69b-6ede-4399-b98f-3d608e1e2ae0 |  | textbox | 04.00 dB(A) Lmax
text | a7fd7364-9323-4e1f-9f11-b8a4a771c28e |  | textbox | 05.00 dB(A) Leq
text | 1d42e7f2-36ee-4c33-acf6-25f375d78ee6 |  | textbox | 05.00 dB(A) Lmax
text | 960e4ee6-fe16-482a-935b-5c58099ae7b0 |  | textbox | 06.00 dB(A) Leq
text | 9e811c00-d21b-4c53-a4cd-af97ff4b8617 |  | textbox | 06.00 dB(A) Lmax
text | c6c2a7ae-a880-4f01-a347-b888d997d1b7 |  | textbox | 07.00 dB(A) Leq
text | 2da149b1-51e3-4046-952f-b5d7198b7200 |  | textbox | 07.00 dB(A) Lmax
text | 77998881-3fe0-493d-8d52-07b092832495 |  | textbox | 08.00 dB(A) Leq
text | 01824a5c-ad3a-4d3a-aaee-2a8e77b410c6 |  | textbox | 08.00 dB(A) Lmax
text | d19a9b32-c07a-416e-a630-9a43a1076265 |  | textbox | 09.00 dB(A) Leq
text | c17ed415-2026-4b14-a279-5079b46446cd |  | textbox | 09.00 dB(A) Lmax
text | 1e163343-517b-4e3c-8461-1e55f4c12051 |  | textbox | 10.00 dB(A) Leq
text | 962f43a2-fd4c-4e81-a454-edb54e48bf7f |  | textbox | 10.00 dB(A) Lmax
text | a1f8d142-c6df-4bfc-a726-bb7d4b17dc9e |  | textbox | 11.00 dB(A) Leq
text | b5fc5fc5-cfc2-4e9f-a989-0b4a971e3d8b |  | textbox | 11.00 dB(A) Lmax
text | b7332abc-2239-4454-a60d-79a5db130ab1 |  | textbox | 12.00 dB(A) Leq
text | 4b145885-75fd-46c7-ad22-cdfabce77789 |  | textbox | 12.00 dB(A) Lmax
text | 8e25d156-8456-4e18-8866-66eeb03e061c |  | textbox | 13.00 dB(A) Leq
text | 9554c455-cb3e-4320-ba8b-dbb937be0874 |  | textbox | 13.00 dB(A) Lmax
text | f7348cae-2a3d-4016-bc20-053f0b4e56a8 |  | textbox | 14.00 dB(A) Leq
text | a8257525-14ce-45dd-b327-ed30dd35a36b |  | textbox | 14.00 dB(A) Lmax
text | e185e4e3-4055-411e-bd3b-aba8bb25e58f |  | textbox | 15.00 dB(A) Leq
text | 6be30708-9ed5-4277-a52f-3ebe6af5bffb |  | textbox | 15.00 dB(A) Lmax
checklist-flat |  |  | checklist | Structural Remedials |  |  |  |  | Yes | Structural Remedial Checklist - QA | 0b162a32-8f50-4804-8d33-60659e6dab23
checkpoint-status |  |  | checkpoint | Location: Zone/Grids ( add picture of mark-up)
text | 51a95dd5-723f-411d-aa94-c1c68c0b758b |  | textbox | Location: Zone/Grids ( add picture of mark-up)
checkpoint-status |  |  | checkpoint | Site Inspection of Area completed with Hawkins
checkpoint-status |  |  | checkpoint | Site Inspection of Area completed with Design team
checkpoint-status |  |  | checkpoint | Defects list Confirmed ( copy attached)
checkpoint-status |  |  | checkpoint | Defects list Agreed with Subcontractor ( copy attached)
checkpoint-status |  |  | checkpoint | Defects Complete
checklist-flat |  |  | checklist | Framing / Strapping |  |  |  |  | Yes | Framing/Strapping Checklist (V1) - QA | 0c1dec38-f0c4-45a5-acd4-a1c4e9dc0143
checkpoint-status |  |  | checkpoint | All framing completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | 05fd5b54-91a4-426c-a101-c17ca6d02834 |  | note | FINAL - Pass when work(s) are completed (any issues please comment below)
boolean | 75768a77-32d3-4e01-8e8c-827ec35feec6 |  | tickbox | Trades - QA received & reviewed
boolean | 60dfdd21-fe29-409f-b7cf-00f4c92ca85c |  | tickbox | Dimensions / locations checked & accurate (openings considered where applicable)
boolean | 217a25ce-6a24-40f9-8c93-b7658006a4bd |  | tickbox | Frames are square, straight & plumb
boolean | 7c099d0a-1d96-4fb9-bf2f-ab0c290cb76b |  | tickbox | Consider stud centres for plasterboard sheet joins
boolean | f4260d39-8760-402f-ba16-47aeda16d08f |  | tickbox | Ensure correct members are selected for lintels & associated bracing hardware installed
boolean | 14bb4b02-2107-43f3-8bc1-b5d466d1aeb6 |  | tickbox | Fixings are correct to specification including any seizmic/bracing requirements (attach relevant photos)
checklist-flat |  |  | checklist | Underground Services Install - Electrical |  |  |  |  | Yes | Underground Services Install Checklist - Electrical - QA | 0d0fea31-0db0-4ce6-a4ae-699138b3e74c
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | 1ab46b2e-69bc-4690-88eb-3df462e3df8c |  | textbox | Subcontractor:
text | eaebaff9-dd92-428e-ac7b-478fa4746524 |  | textbox | Drawing Reference:
checkpoint-status |  |  | checkpoint | Electrical Works complete
boolean | 481501a2-8bb2-40c7-bf62-c799f4330459 |  | tickbox | Pipes cut clean and square
boolean | 3ea4a444-72d8-459c-99e8-132043ba6cb9 |  | tickbox | Located in the correct location
boolean | d055cf10-ad0c-4100-b230-56f1815a893b |  | tickbox | Pipework protected where required
boolean | a478b0a8-b416-4397-a64b-468f57e7ab7d |  | tickbox | Drainage material under pipe
boolean | 17599a38-4c13-4197-a871-eb6d34f37668 |  | tickbox | Levels and inverts correct
boolean | e45f480b-aa7b-4c5b-89bf-0a8f05b93e51 |  | tickbox | Pipework to correct falls
checkpoint-status |  |  | checkpoint | Testing to council requirements pass (pass once inspection is completed and approved)
boolean | a07a7b42-439e-4b4e-8043-eeab4efab1df |  | tickbox | Councils inspection booked
boolean | 9ae6920a-84bb-400d-9707-f639da3b60ca |  | tickbox | Council inspection compete (attached in Council Inspection folder)
checkpoint-status |  |  | checkpoint | Consultant inspection completed & any observations closed out (Inspection attached in Consultants folder)
checklist-sectioned |  |  | checklist | P-Structural Remedials |  |  |  |  | Yes | P-Structural Remedials | 125aa2cb-1185-404b-8298-a0beac363f01
checkpoint-group |  |  | section | Intumescent Paint Remedials
checkpoint-status |  |  | checkpoint | Site Inspection of Area completed with Hawkins/designer
checkpoint-status |  |  | checkpoint | Defects list Confirmed ( copy attached)
checkpoint-status |  |  | checkpoint | Defects list Agreed with Subcontractor ( copy attached)
checkpoint-status |  |  | checkpoint | Defects Complete
checklist-flat |  |  | checklist | Precast Area Handover |  |  |  |  | Yes | Precast Area Handover - H&S | 1dd0ee05-7aeb-4d16-9f3a-25282edfee15
checkpoint-status |  |  | checkpoint | Authorised Person Sign Off (Pass once all inputted)
select | 75ee0d63-caf3-449d-b291-b53f79a461fa |  | dropdown | Authorised Person 1 | Blake, Hiki,David, Cam ,Todd,Luke G,Other
text | 0c7f49a5-9cba-4b1b-9edc-bbd77fd93524 |  | textbox | Sign Off 1 ( if other, type here)
select | b6fb31b4-8155-4fe0-b7fc-8a2f9b99f565 |  | dropdown | 2nd Authorised Person Review | Stu,Paul O,Blake,Cam
text | 046a7bfe-196b-41a0-bddf-7e304331802e |  | textbox | Sign Off 2 - if other type here
text | 90247eaa-9a11-46eb-ba73-37a0698efeef |  | textbox | Grid Reference :
checkpoint-status |  |  | checkpoint | Controls Setup for Area Handover
select | 38166d43-66b3-4767-9046-593446aee92b |  | dropdown | Edge Protection Measures in Place & Adequate? | Yes,No
select | 2bb5e5d1-913f-4fa0-a26c-0fb940036f4b |  | dropdown | Voids Clearly Identified & Protections in Place? | Yes,No
select | c1994344-e2f9-4c53-bb3d-360c3078fd4e |  | dropdown | Penetrations Clearly Identified Place & Noted on Penetrations Register | Yes,No
select | 83c73491-e67a-4b04-8eca-93d5961c7831 |  | dropdown | Safe Access to Work Area in Place | Yes,No
checkpoint-status |  |  | checkpoint | Site Plan -( Pass only when clearly marked plan is attached )
select | 1593c462-f42b-45e2-b4d1-34dc762a1107 |  | dropdown | Is Area Where Work marked | Yes,No
select | 0164262b-d350-4bf4-b1d9-cbe7071108d2 |  | dropdown | Are All Voids Clearly Identified | Yes,No
select | 5e22603b-e3cd-4477-884f-6f8ce9cd4940 |  | dropdown | Are All Exposed Edges Clearly Marked | Yes,No
select | d1a15d70-868d-48da-96b2-314f70c07f30 |  | dropdown | Are All Penetrations Clearly Marked/Access Points | Yes,No
select | 53b141e1-bc58-4a45-85cd-6caf2e41f2b4 |  | dropdown | Are all access points clearly marked | Yes,No
checkpoint-status |  |  | checkpoint | Photos/Additional Comments
checkpoint-status |  |  | checkpoint | Work authorisation
text | be24d75a-f6cf-43da-aa50-33232b44f5ab |  | textbox | Earliest Commencement (Date/Time)
label | 84caab38-152d-4f2d-baf2-79b3d57a841e |  | note | The risk control measure and precautions appropriate for the safe handover have been undertaken as per written authority
select | e7b38d20-2a31-4f20-a599-75ff1da026c6 |  | dropdown | 2nd authorised person | Stu,Paul O,Blake,Cam,Other
text | cb63d766-62e1-4550-97ff-0b0fb69326c7 |  | textbox | sign off 2 - if other type here
checklist-flat |  |  | checklist | Painting Checklist |  |  |  |  | Yes | TH - Painting Checklist | 1fee0ec2-c083-4e2e-a45a-2a3292e11248
checkpoint-status |  |  | checkpoint | Area / substrates acceptable
checkpoint-status |  |  | checkpoint | Paint specifications and colour checked & correct to specification
checkpoint-status |  |  | checkpoint | First coat/ sealant coat completed( attached trade QA )
checkpoint-status |  |  | checkpoint | Light inspection completed & remedials complete
checkpoint-status |  |  | checkpoint | first coat -General comments and photos of additional paint application
checkpoint-status |  |  | checkpoint | Final coat completed,( trade Qa attached)
checkpoint-status |  |  | checkpoint | Final coat -General comments and photos of additional paint application
checklist-flat |  |  | checklist | Clean Up Notice - |  |  |  |  | Yes | Clean Up Notice (V3) - H&S | 2396d045-4eb6-4e0b-91cd-db9c45db712c
checkpoint-status |  |  | checkpoint | All below items closed out
text | 7092ea89-672a-416d-8274-7ba554f73edc |  | textbox | Pass when clean up notice put into Aconex for action (include Aconex reference number)
checkpoint-status |  |  | checkpoint | Observation 1
text | 7bd1b1a0-e531-44d2-9ef0-d9c0cf23128c |  | textbox | Zone /Floor Level & Description
text | 990ca1dc-51e7-4533-857d-6ceaa8a3422b |  | textbox | corrective action required
text | 468f8857-670d-4bff-88b5-3304d57b1ca6 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 2
text | 20f2b44d-279b-41dc-a717-8b76adedf52a |  | textbox | Zone /Floor Level & Description
text | 04e2c3e4-9938-410b-9ef2-48777f12c500 |  | textbox | corrective action required
text | e0e880bb-c3c2-4f5c-919e-89b4648a8f50 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 3
text | db6482a2-4136-48b1-ba7f-335eab633827 |  | textbox | Zone /Floor Level & Description
text | 088edc92-52d8-4744-8ea0-216b92233f20 |  | textbox | corrective action required
text | 15a90cba-3acf-443e-a444-399bb5de03e0 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 4
text | c31012b4-f5fa-4237-bbca-3cc2675a09bc |  | textbox | Zone /Floor Level & Description
text | 6f89b5b8-f951-4f03-bdcd-816fda5ea378 |  | textbox | corrective action required
text | e2c999c9-c478-4c20-a403-5ebeeab6fed2 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 5
text | c3de54fa-2507-429b-ae58-d5de349c1a8f |  | textbox | Zone /Floor Level & Description
text | c4001fae-f6aa-4884-9853-2994c25e87b2 |  | textbox | corrective action required
text | 3705c472-3fcf-4b63-b05b-3e211dba370f |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 6
text | c43f5ff1-7dcf-40d5-8e93-b16704938e75 |  | textbox | Zone /Floor Level & Description
text | a5b620d9-f9b5-4ab7-be79-edaeee8ae8a4 |  | textbox | corrective action required
text | 06c8f923-0119-4d4f-b0aa-0779e375d26a |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 7
text | 942d36b1-4f06-410a-9ae9-1e9ff5f8a134 |  | textbox | Zone /Floor Level & Description
text | 6765886e-60e7-4c62-942e-28b1d749ef29 |  | textbox | corrective action required
text | 62a7cc69-1b1d-4db5-bc71-7177adab144c |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 8
text | e8ada7db-6964-42be-a35a-d5af31505dd4 |  | textbox | Zone /Floor Level & Description
text | 2e9d4ba0-1ba4-4653-abb2-c1296bf72de9 |  | textbox | corrective action required
text | 837dc05c-e741-40b1-bda3-c6cc6b4121af |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 9
text | 090754a2-5508-48af-b0a9-07b8a043fbcf |  | textbox | Zone /Floor Level & Description
text | 26e57efd-e05f-48c6-b00d-a9151a78c018 |  | textbox | corrective action required
text | 0b79b99c-d098-4de9-944f-76115d4809b7 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 10
text | 0a53815e-f093-4ee6-a344-42aae49c6d42 |  | textbox | Zone /Floor Level & Description
text | a2d885ab-767d-403e-b643-36253faecfc4 |  | textbox | corrective action required
text | 04864aaf-df6c-4536-a740-c287358835d1 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 11
text | b7ce1a2c-363d-410f-a594-b6510d2f3535 |  | textbox | Zone /Floor Level & Description
text | 69817edf-eecf-49b8-a707-013670f76ade |  | textbox | corrective action required
text | 097aeff7-10e9-4c95-b0c5-295f35557894 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 12
text | ffb9fe30-a979-49ee-9da8-a7515e1132c8 |  | textbox | Zone /Floor Level & Description
text | 6bc93f78-98b3-4f61-981b-cb037d9de448 |  | textbox | corrective action required
text | 55bbac57-468b-4309-b4ca-b8fbad0d7efb |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 13
text | ebe12864-a4cf-431b-8f1c-939e43938af8 |  | textbox | Zone /Floor Level & Description
text | c01e8ac2-d9ac-4be2-b982-2fadda5f60a6 |  | textbox | corrective action required
text | d1f8f2bb-47b0-4ab2-b0b0-cfbc83e4418c |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 14
text | ea434f70-f83f-4362-ba0a-9a1860ffdf45 |  | textbox | Zone /Floor Level & Description
text | 4b866fa9-2e19-4532-96d6-0d2421fbbf47 |  | textbox | corrective action required
text | eb12508d-8fdc-45e0-b02a-ee2ad114ca32 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 15
text | ae18ec29-bc4f-48ca-ba9e-7e999b399b57 |  | textbox | Zone /Floor Level & Description
text | b904039c-560a-4452-b42e-0bb7bd8e1816 |  | textbox | corrective action required
text | 16117dee-32d3-431d-88a3-4d0cdfeba1ab |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 16
text | 45b9fee7-2145-48da-8333-27d61c91c841 |  | textbox | Zone /Floor Level & Description
text | 9f07cbc5-7dda-47df-97ec-d2f4c8e6a0b7 |  | textbox | corrective action required
text | 49256f87-c3be-4f02-8508-31e4cd2c5c38 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 17
text | 28d7ba05-f295-475f-9f36-2b877b052b82 |  | textbox | Zone /Floor Level & Description
text | 239c25f3-ba7b-4cd6-89ea-ab91c9a300d7 |  | textbox | corrective action required
text | a6703212-79a2-4be9-bf39-e71636cc114f |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 18
text | b7df7a43-a277-43d6-b798-49994a269413 |  | textbox | Zone /Floor Level & Description
text | c4292f56-def1-43b9-a29a-985b1f29f860 |  | textbox | corrective action required
text | 7a3556c5-9c51-44a4-9ac9-28bba32a7376 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 19
text | 73d6eca8-f69a-42dd-8144-49484e8dbfcc |  | textbox | Zone /Floor Level & Description
text | cced1bd2-11a6-480d-807a-4c2538eb05f1 |  | textbox | corrective action required
text | 9374417c-3a9f-4e81-a5b3-9bd57d424a2d |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 20
text | 81aa7db0-0056-4e61-8a45-fb70baad2cdf |  | textbox | Zone /Floor Level & Description
text | 24e9657e-2be5-4ab8-9a9f-d31a71178838 |  | textbox | corrective action required
text | 6daddd35-e270-4fc3-8759-a88c229f82c8 |  | textbox | Allocated to
checklist-flat |  |  | checklist | TW - Balcony Permit to Load |  |  |  |  | Yes | TW - Balcony Permit to Load | 27403886-fef0-48ee-aec2-053ce587c79e
checkpoint-status |  |  | checkpoint | Has all documentation been signed by the Temporary Works Designer and Checker?
checkpoint-status |  |  | checkpoint | Have the drawings been issued with for construction status
checkpoint-status |  |  | checkpoint | Have all comments form the checker been resolved
checkpoint-status |  |  | checkpoint | Has the works been completed in accordance with construction documents
text | e42648d5-d7aa-4277-abdb-8e382e824d38 |  | textbox | Type of propping used
checkpoint-status |  |  | checkpoint | Has relevant QA documentation been completed
boolean | b6df257d-1a62-4f19-b797-86fb788b4c5b |  | tickbox | Jensen survey complete (pre-set)
boolean | 0f4196c6-d781-4d42-8b77-7b9dfb06d346 |  | tickbox | Hawkins height check completed
checkpoint-status |  |  | checkpoint | Has the temporary works designer inspected the works
holdpoint |  |  | signoff | Holdpoint / Request Signoff
checkpoint-status |  |  | checkpoint | Post landing survey completed
boolean | 63337c4e-f875-4683-b057-91eec6142404 |  | tickbox | Jensens survey complete
boolean | fe35ac4e-ebd3-4f56-b080-48c0f6feaaf9 |  | tickbox | Hawkins post load height check
checkpoint-status |  |  | checkpoint | Floor poured and cored
checkpoint-status |  |  | checkpoint | If required, has approval from the permanent works Engineer been granted
checklist-flat |  |  | checklist | Piling Completion/Handover - |  |  |  |  | Yes | Piling Completion/Handover Checklist - QA | 293e108b-ab56-4223-97fb-04c9b2ea029c
checkpoint-status |  |  | checkpoint | CLL QA downloaded and attached
checkpoint-status |  |  | checkpoint | Raise remedial issued for review
checkpoint-status |  |  | checkpoint | All piles completed (locations and heights checked and correct within tolerance)
holdpoint |  |  | signoff | Remedials Signed off
checkpoint-status |  |  | checkpoint | Any additional completion/handover documents completed and attached
checklist-sectioned |  |  | checklist | Fitout / Finishing Checklist - Apartment |  |  |  |  | Yes | Fitout / Finishing Checklist - Apartment | 29524120-d875-4e8a-97a1-bc927b0df359
checkpoint-group |  |  | section | General QA
checkpoint-status |  |  | checkpoint | Wardrobes Install Completed, checked and approved
boolean | 861ab017-b48e-57cb-b506-dd13cbd063a3 |  | tickbox | - Onsite measure
boolean | e8a85c2d-f156-5c3d-9965-0d47eed4e2bf |  | tickbox | - Installation
checkpoint-status |  |  | checkpoint | Second fix door hardware installed and approved
checkpoint-status |  |  | checkpoint | Final Clean Completed & Area ready for handover
checkpoint-status |  |  | checkpoint | All above QA items completed
checklist-flat |  |  | checklist | Daily Site Report - Concrete Works: |  |  |  |  | Yes | Daily Site Report - Concrete Works | 31bbe736-a23b-4098-9126-87cd666ab135
checkpoint-status |  |  | checkpoint | Hours Worked & Weather Conditions Recorded
text | a898e1af-3646-4e72-a899-ccbc51fa137c |  | textbox | My Hours Worked (start & finish)
select | 0832cc70-587e-4746-b358-58c91af9e4e6 |  | dropdown | Weather Conditions AM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
select | 7812bf94-1a1e-4dd6-970f-f4ab3b853a51 |  | dropdown | Weather Conditions PM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
checkpoint-status |  |  | checkpoint | Visitors to Site (Record name, company & purpose)
checkpoint-status |  |  | checkpoint | Site Instructions Issued (Any relevant site instructions issued are documented here)
checkpoint-status |  |  | checkpoint | Day Works Agreed (Any relevant Day Works issued are documented here)
checkpoint-status |  |  | checkpoint | Subcontractors on site (all recorded area, man power, name)
button | f5a2d169-61d2-4aca-9bb4-31bd1f576ee7 |  | button | GHD- Concrete- Area & Man power | yes, no
text | c29a72a6-ef4f-4e18-82e8-bdd8a940febb |  | textbox | Area Working (GHD) Concrete
text | 4e34e7a1-7af8-40be-bdac-3c08b7c82df2 |  | textbox | Man Power (GHD)
button | a894723c-fb2b-4b8e-b0b6-aa7acddff5ea |  | button | Baseup - Area & Man power | yes, no
text | 93890899-4769-4db9-b3e8-ba14d872d798 |  | textbox | Area Working (Baseup) Concrete
text | 7af92394-44c4-4654-86a3-cb7a9635698c |  | textbox | Manpower (Baseup)
button | 0080c241-77fc-4e09-8934-518b52b9cb8b |  | button | Advanced Carpentry - Area & Manpower | yes, no
text | 429b96fb-a606-4966-b8d0-03aaa4015172 |  | textbox | Area Working -Advanced Carpentry
text | 0f596f0e-618f-4b72-86da-ae05acad2c56 |  | textbox | Manpower (Advanced Carpentry)
button | bd2f9911-cdaa-49c5-b8e3-c45853c7e918 |  | button | Jensens- Main structure- Area & Manpower | yes, no
text | ff3609d8-a064-40f4-baba-3f354fb73774 |  | textbox | Area -Jensen main structure
text | c3174861-bc7d-4645-b0ed-50a7734b4337 |  | textbox | Manpower (Jensens - Main steel )
button | e84fa580-8a94-4e2e-ab92-b95c83804af9 |  | button | Arid - ( waterproofing) Area & Manpower | yes, no
text | 564981d0-007c-4cca-8039-c0f33ffc9222 |  | textbox | Area Working- Arid ( waterproofing)
text | cde4de86-8e6c-446c-8b65-6ce0fe8be151 |  | textbox | Manpower -Arid Waterproofing
button | 19e65ed0-9a18-4777-b56c-57ca9adb0741 |  | button | Cake (Intumescent ) Area & Manpower | yes, no
text | 9ebfc9b2-eb53-43d1-9bc0-f7f954e0240d |  | textbox | Area Working ( Cake)
text | 520e163f-fbda-4876-b89d-c0e33c782441 |  | textbox | Manpower (Cake)
button | 165b5565-a203-4535-a3bb-ab8f87849b3b |  | button | Certified Bricklayer - Area & Manpower | yes, no
text | 56a8aa3a-a22b-46dd-84a4-77887dd2cf93 |  | textbox | Area Working ( Certified Bricklayer)
text | 4ffbf316-9121-44e0-8b48-3b86d365ab84 |  | textbox | Manpower (Certified Bricklayers)
button | 53edf564-3939-48d4-a4b8-0aa4781c375e |  | button | Fletcher ( Reo) - Area & Manpower | yes, no
text | ed4919ba-de66-4325-b15f-60c3c44e7720 |  | textbox | Area Working ( Fletcher)
text | 188e39d6-3b15-48c3-b3a2-cff700f13d11 |  | textbox | Manpower (Fletchers)
button | 7666fa04-b686-4559-a363-5a8451625ea7 |  | button | Ironworks( Reo) | yes, no
text | 8d3ddb34-f9f2-4f8b-8c01-8e718020d96d |  | textbox | Area Working Ironworks
text | 10110ad4-8906-41c6-aa58-a4105d180e44 |  | textbox | Manpower (Ironworks)
button | b7714ab6-621b-4ad0-8fee-b98cfb6ccf84 |  | button | Smith Cranes -Area & Manpower | yes, no
text | e235b5a6-0ae9-4ae7-8992-27570379783a |  | textbox | Area working ( Smith cranes)
text | 652b1abd-887c-4222-b9f4-cdcc4cba628f |  | textbox | Manpower (Smith Cranes)
button | fd14f7f1-b674-4061-9e19-b6c3a0a98d28 |  | button | Fabworx ( Metalwork)- Area & Manpower | yes, no
text | d4e894b4-4478-402d-9792-47211e832adc |  | textbox | Area Working Fabworx
text | 4c72b4bd-d5da-4508-9cfb-00a344d9fbc9 |  | textbox | Manpower (Fabworx)
button | 764ab003-4f60-4353-95e6-c2b418aa0472 |  | button | Total Access- Area & Manpower | yes, no
text | 5d441263-dd1c-4a55-acb8-ef107a965491 |  | textbox | Area Working ( Total Access)
text | 0307f50c-a862-4d6f-9061-acffc73ea8aa |  | textbox | Manpower (Total Access)
button | 8a60e1fc-101b-4bc4-9d50-5e885d8fdb94 |  | button | Hawkins Carpentry Area & Manpower | yes, no
text | ea5d6dfe-6a6b-440c-8c64-76404f97602f |  | textbox | Area Working (Hawkins Carpentry)
text | 7543b044-6bc7-4662-b588-197ce1f4aa8d |  | textbox | Manpower (Hawkins Carpentry)
button | beed3354-b0ab-4167-8123-49e67486a19c |  | button | Trade - Name, Area & Man power | yes, no
text | f67858c7-0355-4ef9-af8d-3a9331876fdf |  | textbox | Company
text | 62bdbb33-7460-48cb-99df-ad8fd23ff261 |  | textbox | Area
text | 109662d1-0b6b-46bd-a35e-c4e4a7b74b8c |  | textbox | Manpower
button | 126bbe15-d1bc-431e-8999-e5804e29e9f9 |  | button | Trade - Name, Area & Man power | yes, no
text | 90da47ba-94dd-44ba-adbd-3b971bd1e0f4 |  | textbox | Company
text | a99f1c62-376a-4cc2-9453-cee23f592619 |  | textbox | Area
text | 6e5f61c8-4277-4cd3-96fb-05b3cdf9ddf3 |  | textbox | Manpower
button | 275806ec-b85f-42a4-ba50-d3c157029cb7 |  | button | Trade- Name, Area & Man power | yes, no
text | 073311d2-3fd8-46db-a63c-9783f96726b2 |  | textbox | Company
text | 50db2dff-cdbd-4d10-b40b-606336ebe8f6 |  | textbox | Area
text | 2224bea9-2624-4819-ae0b-b3d79bce976e |  | textbox | Manpower
checkpoint-status |  |  | checkpoint | Subcontractors contacted today (document name & date trade is required / conversation details)
checkpoint-status |  |  | checkpoint | Progress (quantities & location) - include photos
checkpoint-status |  |  | checkpoint | Unsatisfactory Progress - include photos (Fail if of serious concern - Pass once resolved)
checkpoint-status |  |  | checkpoint | Subcontractor/Supplier -Items delaying progress (Fail if of serious concern - Pass once resolved)
checkpoint-status |  |  | checkpoint | Design - items delaying progress
checkpoint-status |  |  | checkpoint | Disruption /Mitigation (subcontractor / design)
checklist-flat |  |  | checklist | Area Completion / Handover |  |  |  |  | Yes | T1&2 Fitout (New) - Area Completion / Handover | 35226db7-1296-4b66-bf77-a358e5a15afa
checkpoint-status |  |  | checkpoint | All above QA items completed
checkpoint-status |  |  | checkpoint | Final Clean Completed & Area ready for handover
checklist-sectioned |  |  | checklist | Walls Services Preline |  |  |  |  | Yes | Walls Preline - Services Checklist (V1) - QA | 35315b36-448f-4f4d-9c6c-ca50ff5782eb
checkpoint-group |  |  | section | Interior Framing Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area ( sign off when spot checks complete)
boolean | b142bf21-30ab-4a48-95b4-063d00d19cf5 |  | tickbox | Spot checks on frames for square
boolean | cc2fd42c-91e6-40b5-8a4a-127d2a327d2e |  | tickbox | Spot checks on frame level
boolean | 6110292d-2722-4b4d-b62b-800738ee832b |  | tickbox | Fixings are correct including seismic requirements
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Plumbing Walls First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | ef8e07f5-87c1-47a9-9157-8d7f0bd8ed01 |  | tickbox | Setout/straightness checked
boolean | d54b6e6b-81b7-466b-b296-9733d8b7e51b |  | tickbox | All required additional noggs placed in framing
text | 743c948e-2e9e-4a7e-b839-336936834afc |  | textbox | Reference Drawings ( add drawing numbers & revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Plumbing install First fix complete - checks done based on current drawings ( pass once all complete)
boolean | 27cb4c60-6e34-4c3f-81be-ac4648f59663 |  | tickbox | Pipes size & type
boolean | bea2a26a-2865-4230-acb7-49d058b534e1 |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly (including seismic where required)
boolean | 5569c957-fda2-4182-98ff-e952dc2df471 |  | tickbox | Correct number of outlets
boolean | 7bebd410-b7f3-4b2a-888a-630f2232613f |  | tickbox | Any valves/vents installed
boolean | 7b0c8e70-d586-45b0-8250-ec802cb0ffe0 |  | tickbox | Pipework protected at holes and notches
boolean | 6bc943fe-3bfe-4bb2-8a61-a5e7fffa6073 |  | tickbox | Heights & positions of pipework's checked ( above ceiling)
boolean | c347c31f-4f8c-45bc-96eb-334aeff82e76 |  | tickbox | All lagging is in place
boolean | c61228f4-51c0-4b7f-ab3d-a8c9db47a405 |  | tickbox | All pipes cleaned/cleared before testing
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Protection Provided for floor wastes and ends of unfinished pipes
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Fire Protection Walls (Sprinklers & Alarms)First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 7e328769-fe2e-4fa3-918d-4c1b2b3686b0 |  | tickbox | Correct wall framing setout/straightness checked
boolean | f4247d95-35f7-4cfc-a70d-a4de0e6f3283 |  | tickbox | All required additional noggs placed in framing
text | d6978cb5-2782-47ce-83b7-39c6a3454902 |  | textbox | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor alarms & Sprinklers- tick when all below are checked and complete
boolean | 447233d9-a85b-4b51-98e2-344582181676 |  | tickbox | Pipes checked for damage/corrosion/Scale
boolean | a9052222-3445-4993-9d07-03d5ce91cb90 |  | tickbox | Pipes size correct and type
boolean | 69868894-fe11-4742-b39f-34590a2ba0d5 |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | b53d0abf-8075-4de9-830e-1f4f103c805b |  | tickbox | Correct number of outlets/droppers for sprinklers
boolean | 5c9ddf0f-b255-443e-b32c-b9774650f8c0 |  | tickbox | Heights of pipework's checked ( above ceiling)
boolean | ee0cbdbc-4dec-4aa8-8626-eea9bd74cf89 |  | tickbox | Any lagging required is in place
boolean | af6d8723-3e65-4d60-8cd2-8e2539ad119b |  | tickbox | all labelling installed for pipework
boolean | 44655cc1-09d9-44a3-89c5-6e6b337cf37e |  | tickbox | Cables are completed and with proper support
boolean | 48bfeabd-f390-43e8-89de-fe196932a242 |  | tickbox | All wiring labelled/identified
boolean | d75469f9-817d-4c9a-841e-cfb027bd37e3 |  | tickbox | all pipes cleaned/cleared before testing
boolean | cc6ce6c1-5314-4744-92a6-bf9ec226f559 |  | tickbox | Correct number of connections for dectors
boolean | ebfcce10-2f9b-4f95-ac05-f400219f8f22 |  | tickbox | All Main Control Panels at correct heights & positions
checkpoint-status |  |  | checkpoint | All required 1st fix testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | FPIS inspection sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Protection Provided for floor wastes and ends of unfinished pipes
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Mechanical Services Wall First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 619ba1e5-4e68-456a-9938-9e1a3cc2accd |  | tickbox | Setout straightness checked
boolean | 0fa65b6b-ac22-4d47-ad3a-e9639115dec2 |  | tickbox | All required additional noggs placed in framing
text | 433910d1-ff09-4e3e-91d5-45d11214add8 |  | textbox | Reference drawings ( add drawing numbers & revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with subcontractor - tick when all below are checked and complete
boolean | febf07de-61bd-46f8-bf3e-5934132ea813 |  | tickbox | Ducts checked for damage/corrosion etc.
boolean | 2512699d-7c4f-4bff-9a56-9d6fc9a4f8dd |  | tickbox | Ducts size correct and type
boolean | 3eb4aea5-2f5a-4cef-bc4d-b12d3953907f |  | tickbox | Duct supports , anchors and hangers/Clips installed correctly including seismic
boolean | dd864320-fcba-46c3-abe3-7c951b69cca7 |  | tickbox | Ducts And pipes insulated and labelled
boolean | 28a8ccda-f2a5-4d85-92d4-79933bd48c42 |  | tickbox | Heights of pipework's checked ( above ceiling)
boolean | f38e8ba8-fc29-46d5-8903-d27758107280 |  | tickbox | all ducts cleaned/and ends capped where needed
boolean | 352cec10-8793-450d-9f2a-79d34f5cec44 |  | tickbox | Cablesfor themostats etc, are completed and with proper support
boolean | a2f1767c-367e-4775-8335-7cf9a3b6dce9 |  | tickbox | All equipment , valves and fire dampers, air outlets louvres, grilles and dampers are in place and accessible where required
boolean | 7d02ab2d-91cf-431c-b64b-87393cc3c6d4 |  | tickbox | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | council signoff
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Protection of all ends & Cleanup Done
checkpoint-status |  |  | checkpoint | any onsite changes documented
checkpoint-group |  |  | section | Electrical Wall First fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 6c2b9a3c-2d27-4f08-8c41-bc48e0c2816f |  | tickbox | Setout/straightness checked
boolean | c32cbb86-4fc9-4969-9072-4f15e13bd6da |  | tickbox | All required additional noggs placed in framing
text | 2a235f5c-d05e-4091-8a42-d913bebe3e76 |  | textbox | Reference drawings ( add drawing numbers & revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
boolean | 42d6b415-e7c1-42de-9c44-21eea36707c4 |  | tickbox | Cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | 260c5f44-743f-4b2c-a853-8e292865182c |  | tickbox | distribution boards in correct place
boolean | 43ba5548-3799-4dd5-84d5-0bd4a61f0ae6 |  | tickbox | All outlets and switches at the correct position & height
boolean | 1cf34692-c8a8-4699-a4ee-2df03b8ddcb3 |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 39caf56a-f05f-492e-9ec3-56c7b17a08b9 |  | tickbox | Power supplies for roller doors, HWC,Sliding doors, fire ,security etc. installed in correct place
boolean | 7a327914-65c2-4e6e-b0d1-5dd94caba9cb |  | tickbox | All wiring labeled/identified
boolean | 488838ca-5570-4008-86f1-766e73c83b10 |  | tickbox | all earthing and cables installed
boolean | 9531e00f-6775-4fb9-9800-f2a2bd2f1f2e |  | tickbox | Cables are installed and with proper support
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Protection /Cleanup Done
checkpoint-status |  |  | checkpoint | any onsite changes documented
checkpoint-group |  |  | section | Data/Security Wall First fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 1908a14c-4aad-42b9-bc2d-12caafb8c215 |  | tickbox | Setout/straightness checked
boolean | 3965927f-c5e8-49f6-b366-880b6771cfc4 |  | tickbox | All required additional noggs placed in framing
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required first fix completed ( pass when checks done)
boolean | 854567b4-7ca2-4f5a-82f6-63e14af89bd4 |  | tickbox | cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | cf9c3a0c-1995-4cc1-9ed8-a02a4090d4b6 |  | tickbox | connections to distribution boards in correct place
boolean | ae739a5b-1af7-48ed-bcda-a1d5e9fcbd80 |  | tickbox | All outlets and switches at the correct position & height
boolean | 3252bad1-7954-4925-9b4b-4bcd52d1c72b |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 7ac2e222-a099-4f54-9233-0c0420914b21 |  | tickbox | Connections for roller doors, HWC,Sliding doors, fire ,security etc. installed in correct place
boolean | 53c1425e-6648-4cfe-906e-9684051cbc7b |  | tickbox | all earthing and cables installed
boolean | 8d514efc-18ca-4c94-b098-41f572077a2e |  | tickbox | Cables are installed and with proper support
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Protection /Cleanup Done
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Insulation/Acoustic Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Insulation pre lining works completed, checked & approved
boolean | 45286433-69df-4d15-9c9b-cb60e4d247d1 |  | tickbox | Spot checks on correct product
boolean | 163f1faa-3347-4f8f-9b96-4633f5c4b8c6 |  | tickbox | Spot checks on correct R value
boolean | 1cc1eab2-de7f-4a35-b1b3-76139bf8735c |  | tickbox | Fitting Snug
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checklist-flat |  |  | checklist | Concrete Testing Results - |  |  |  |  | Yes | Concrete Testing Results Checklist - H&S | 38d7d513-5451-4f72-b217-749811959265
checkpoint-status |  |  | checkpoint | Concrete testing results attached, checked and acceptable
holdpoint |  |  | signoff | Request Documentation / Signoff
checklist-flat |  |  | checklist | Structural Steel - |  |  |  |  | Yes | Structural Steel Checklist - QA | 3d49b051-4fef-4c6d-966e-778411be1fdc
checkpoint-status |  |  | checkpoint | Drawing Details
text | c577514d-0c93-4a4e-b7d8-d5b3c0e44b7f |  | textbox | Drawing Reference:
checkpoint-status |  |  | checkpoint | Steel inspected on arrival, checked and correct (photograph delivery docket)
boolean | 014d7744-c348-490f-9b89-9a1343363e39 |  | tickbox | Fabrication & Mill Cert QA received
boolean | 16e62d8c-c208-476d-a20a-c995267c83aa |  | tickbox | Paint Shop QA received
checkpoint-status |  |  | checkpoint | General photos / comments / observations during install received
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and trade QA received and reviewed
boolean | a674f38c-ed26-4bc7-9e8e-b09fa0cc0321 |  | tickbox | Correct location and orientation
boolean | 545fa21c-7b33-4b59-bb20-b4ce77893d49 |  | tickbox | Level, plumb, correct pitch and braced
boolean | a846cc6e-9a5b-4120-8276-d0be122ffd23 |  | tickbox | All bolts secure/ correctly tensioned
checkpoint-status |  |  | checkpoint | Structural Engineer inspection complete and any remedials signed off
checklist-flat |  |  | checklist | End of Day Lockup/Fire Checklist |  |  |  |  | Yes | End of Day Lockup/Fire Checklist | 41140a26-16ae-4252-a39d-50b063d8d9e4
checkpoint-status |  |  | checkpoint | Lockup Entrances & Stairs clear (comment and check)
boolean | cdcfed56-0eca-5be6-addf-20f4254b009e |  | tickbox | HCL Containers Locked
boolean | 909638f6-c663-562f-b5cc-cf578f0b9f3f |  | tickbox | Gate 4 Locked
boolean | 767be344-8add-58c7-818f-75d41ae36987 |  | tickbox | Turnstile Gate Locked
boolean | 263bd2cd-7f53-5b25-8e9e-2f411d71247b |  | tickbox | Rainwater Pumps on Zone 1, Zone 2 & Zone 6
boolean | 9ee99c8e-d220-5531-b013-77988f923f9f |  | tickbox | Breaker Sub Rooms off
boolean | 6997a740-61af-5c0a-bc78-c570a6cf5d1f |  | tickbox | HCL Work Alone Protocols Completed
boolean | 0ae87ecc-80c4-533a-855c-0722a72c0327 |  | tickbox | Hotworks Register - signed
checkpoint-status |  |  | checkpoint | Building Secure (Doors External/Drainage)
boolean | 87cb41ce-5374-544d-b35c-6764f4382dd9 |  | tickbox | Basement + Loose Items Secured
boolean | f514db52-8345-5b1d-a04e-943c8dbcad84 |  | tickbox | Podium + Loose Items Secured
boolean | d065de06-6753-5d6e-afbf-5057d2052f96 |  | tickbox | Level 2 - External Doors Closed/Loose Items off Bridges
boolean | de81164e-009a-5faa-a979-a50f9250786f |  | tickbox | Level 3 - External Doors Closed/Loose Items off Bridges
boolean | 46e90923-e07f-5fc4-8ed9-295ff4adcd5f |  | tickbox | Level 4 - External Doors Closed/Loose Items off Bridges
boolean | 58f2512b-6001-582b-9b80-705bc92b6c92 |  | tickbox | Level 5 - External Doors Closed/Loose Items off Bridges
boolean | 4539b7dc-4cf1-5dcb-b250-50010ac2f623 |  | tickbox | Level 6 - External Doors Closed/Loose Items off Bridges
boolean | 4ba3329e-4d5b-5b5e-aede-30d486600503 |  | tickbox | Level 7 - External Doors Closed/Loose Items off Bridges
boolean | 8f9159ed-3a54-5aa0-b4b2-cc0e3d83eace |  | tickbox | Level 8 - External Doors Closed/Loose Items off Bridges
boolean | 56e67958-c5d5-5ae5-856f-a842a4b62229 |  | tickbox | Level 9- External Doors Closed/Loose Items off Bridges
boolean | 83683719-5723-56a1-9122-5b6de3fb05a7 |  | tickbox | Level 10- External Doors Closed/Loose Items off Bridges
boolean | c15d6f98-784c-582e-8a42-ca3b7e278f5f |  | tickbox | Townhouse Block 1 - External Doors Closed/Loose Items Secured
boolean | 929136fd-35d7-5b9b-9573-6bf74549a1ee |  | tickbox | Townhouse Block 2 - External doors closed/Loose Items secured
checkpoint-status |  |  | checkpoint | Office Check (pass once all complete)
boolean | c5650058-8956-58c5-8546-da4d370af019 |  | tickbox | Container at back locked
boolean | 4e0242b0-6c50-5fc4-ab2d-1fd24626193a |  | tickbox | All lights off & Alarm set in office
boolean | a9369728-7bdb-5011-8c00-fe9218d9084c |  | tickbox | All Office Doors Locked
boolean | e125b248-1c9d-5b3a-a8bc-389cf18b7803 |  | tickbox | Security Contacted & Team Advised
checklist-flat |  |  | checklist | TW – Permit to Unload |  |  |  |  | Yes | TW – Permit to Unload | 42e84b64-3562-45f4-b0fb-420e27efdfb0
checkpoint-status |  |  | checkpoint | Has the designer specified a permit to unload is required
checkpoint-status |  |  | checkpoint | Have all necessary permanent works for which the temporary works are required for been completed
holdpoint |  |  | signoff | Holdpoint / Request Signoff
checkpoint-status |  |  | checkpoint | Have all necessary permanent works QA documents and hold points been achieved
holdpoint |  |  | signoff | Holdpoint / Request Signoff
checkpoint-status |  |  | checkpoint | Will removal of the temporary works load another structure
checkpoint-status |  |  | checkpoint | Is the structure compete and capable of taking the loads
checkpoint-status |  |  | checkpoint | If required, have any approvals from the Temporary works engineer been granted
checkpoint-status |  |  | checkpoint | If required, have any approval from the permeant works engineer been granted
checkpoint-status |  |  | checkpoint | TWS (Temporary Works Supervisors) given approval to remove
holdpoint |  |  | signoff | Holdpoint / Request Signoff
checkpoint-status |  |  | checkpoint | Have details of any dismantle sequence been communicated to the site foreman?
checklist-flat |  |  | checklist | Wall Preline Approval |  |  |  |  | Yes | Preline Inspection Checklist (V1) - QA | 46c301cb-09bf-4c27-a7e2-4643c01e1880
checkpoint-status |  |  | checkpoint | All above preline elements checked, correct & approval to line
boolean | 3891e7a9-9158-45f0-8705-e1f52bafade8 |  | tickbox | Council inspections carried out & attached in council folder
boolean | a99f1c56-3b5a-4e6f-b463-115949fd4382 |  | tickbox | Relevant consultant inspections carried out & attached in consultants folder
checklist-flat |  |  | checklist | QA Landscaping Checklist |  |  |  |  | Yes | Landscaping Checklist - QA | 47a9ebe4-d08b-4478-b2da-40b97b0e6209
checkpoint-status |  |  | checkpoint | QA Received From Subcontractor
text | 477a53c3-45af-5062-8508-f7c78658ab49 |  | textbox | Add supporting documents/photos attached along with confirmation of submission to client
select | b0e32811-f9c4-5c53-bc2a-1dc916d24f02 |  | dropdown | Received Via: | Aconex, Email, Other
text | ed8edc86-a40e-5a82-9ad7-219fdb972d99 |  | textbox | Reference Number:
text | b88b1a93-99d3-5a68-8b50-96493a0fc960 |  | textbox | Reference Date:
checkpoint-status |  |  | checkpoint | Area inspected by Consultants and remedials signed off
checkpoint-status |  |  | checkpoint | Area signed off by council
checklist-flat |  |  | checklist | Framing / Strapping |  |  |  |  | Yes | Interior - Framing/Strapping Checklist (V2) - QA | 4cf4f6af-7365-41a2-9d31-21a278d641b9
checkpoint-status |  |  | checkpoint | All framing completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | 5c6ade0d-5509-5088-9a11-58a84d0bb345 |  | note | FINAL - Pass when work(s) are completed (any issues please comment below)
boolean | 428740b6-db6f-54d0-9938-29ae17aa7894 |  | tickbox | Trades - Interior framing QA received & reviewed
boolean | cfc1b3e4-cb36-525b-82ab-b3de14d4fab9 |  | tickbox | Dimensions / locations checked & accurate (openings considered where applicable)
boolean | 5c28b92b-cf65-57e5-983d-b4d6580f0928 |  | tickbox | Frames are square, straight & plumb
boolean | a0c1cc15-dbb2-5c54-936e-6abb5eba1801 |  | tickbox | Consider stud centres for plasterboard sheet joins
boolean | 18bdf53e-2a11-5984-9f08-99b7fc75d999 |  | tickbox | Ensure correct members are selected for lintels & associated bracing hardware installed
boolean | 348285f5-143a-540e-a82a-361a620c256b |  | tickbox | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checklist-sectioned |  |  | checklist | Pour - |  |  |  |  | Yes | Concrete Pour Checklist - On Grade Floors - QA | 4f26db97-7034-4970-8ad1-9426f247a7b7
checkpoint-group |  |  | section | Pre Pour
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | 93770ec4-6d35-4679-8ac0-e8b38ea2a88e |  | textbox | Drawing reference:
text | 40ccf95e-506a-4bb6-a694-aff83a0a3ad1 |  | textbox | Subcontractor:
checkpoint-status |  |  | checkpoint | Detailed Excavation complete & accurate -on grade only(Pass before progressing)
checkpoint-status |  |  | checkpoint | Underslab services and drainage
checkpoint-status |  |  | checkpoint | Backfilling Complete - on grade only(Pass before progressing)
checkpoint-status |  |  | checkpoint | Formwork Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Waterproofing Trades Pre Pour QA received, attached, reviewed and approved (on grade only)
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Penetrations located/boxed & approved
checkpoint-status |  |  | checkpoint | Reinforcing Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Reinforcing Install completed and reviewed
boolean | 3cb924d9-b168-4a2b-8d27-2f7e3e52dc4a |  | tickbox | Reinforcing - Size and type correct to specification
boolean | bfecbf94-de2a-499a-9bed-0e94d553650f |  | tickbox | Reinforcing - spacing and location correct
boolean | baa5b081-6ef9-46cd-8341-687756568f07 |  | tickbox | Specified covers checked/correct
boolean | 2de63ccc-702a-40b9-8022-461fdbe15807 |  | tickbox | Splice laps checked/correct
boolean | ac4eeade-fef5-4711-b2d0-f60a63d8d8ce |  | tickbox | Any starter bars are installed correctly (location, size and spacing )
boolean | 619836ff-f665-4eb4-b366-06b00af6e7e7 |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Structural Steel cast in plates installed/ checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Bottom of foundation is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | All services completed
checkpoint-status |  |  | checkpoint | Engineer informed of pour, checks completed (see Holmes folder and ensure observations are closed out)
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
checkpoint-status |  |  | checkpoint | Trades Post Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour checks completed and any remedial work closed out
checklist-sectioned |  |  | checklist | Walls Services Preline |  |  |  |  | Yes | 1CONQA - Walls preline services checklist (V2) | 4f7c51ab-a509-4ad9-b246-353a84130b26
checkpoint-group |  |  | section | Plumbing - Walls First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 05251ee1-32df-511c-864a-3765caff148e |  | tickbox | Setout/straightness checked
boolean | e9a9686b-dfb3-5564-ae09-48739c1ec7a4 |  | tickbox | All required additional noggs placed in framing
text | 8f6da657-0739-5cab-8388-30a61744a103 |  | textbox | Reference drawings ( add drawing numbers & revisions)
checkpoint-status |  |  | checkpoint | Plumbers wall QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Plumbing install first fix complete - checks done based on current drawings ( pass once all complete)
boolean | 680cbc0f-6e5e-5bc3-8303-4f2e2cc7eeef |  | tickbox | Pipes size & type
boolean | 2eed8b77-51fd-5d2a-a0e3-71ca0165a042 |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly (including seismic where required)
boolean | f42d77c9-3168-5824-920b-6af14eb745a2 |  | tickbox | Correct number of outlets
boolean | 60b13c0d-46cf-5be6-8948-6176ca3d1696 |  | tickbox | Any valves/vents installed
boolean | 8bc499d0-2a6e-5f8a-a899-acdb50ad9dd1 |  | tickbox | Pipework protected at holes and notches
boolean | 810719a2-7df0-5fe1-b5d2-e500c94acc10 |  | tickbox | Heights & positions of pipework checked ( above ceiling)
boolean | 73aa0e83-5a75-52cb-8c63-4537c5aba528 |  | tickbox | All lagging is in place
boolean | 1f9a51ce-4043-5a98-af9e-90f9fb50f7c7 |  | tickbox | All pipes cleaned/cleared before testing
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Service Engineer inspection requested
checkpoint-status |  |  | checkpoint | Protection provided for floor wastes and ends of unfinished pipes
checkpoint-status |  |  | checkpoint | Any onsite changes documented ( add a copy here)
checkpoint-group |  |  | section | Fire Protection (Sprinklers & Alarms) - Walls First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | bf201022-b978-57ea-9fae-498d2764e9c6 |  | tickbox | Correct wall framing setout/straightness checked
boolean | 89e3caa2-bdf0-5a6d-a138-0bad8bff49e5 |  | tickbox | All required additional noggs placed in framing
text | 9a7746cd-1b19-59a6-8ec9-8c28f60b1e02 |  | textbox | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Sprinkler & alarms wall QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First fix checks with subcontractor alarms & sprinklers- tick when all below are checked and complete
boolean | f450716e-6485-5481-b031-781fd3b3fc93 |  | tickbox | Pipes checked for damage/corrosion/Scale
boolean | 94b37837-ec1f-516c-af47-c74105ab47a8 |  | tickbox | Pipes size correct and type
boolean | 641a0dc3-7920-5989-8919-cc8b7cfbe5e3 |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | f035d033-9a45-51e3-b027-b3abf8de8ca9 |  | tickbox | Correct number of outlets/droppers for sprinklers
boolean | 3186fb54-0b45-5eac-8061-a781569b307a |  | tickbox | Heights of pipework checked ( above ceiling)
boolean | c2e13774-d739-5e0b-ac70-69e62144f68a |  | tickbox | All labelling installed for pipework
boolean | 76787fa1-a50f-511d-a3e1-b9ae7ddf50d4 |  | tickbox | Cables are completed and with proper support
boolean | 05a0c91f-cfa1-5f7e-b342-47ae6b0469d4 |  | tickbox | All wiring labelled/identified
boolean | c3fbe3d3-cb4a-5fa2-8d7b-983307965e7f |  | tickbox | All pipes cleaned/cleared before testing
boolean | 2bcf85db-0264-5742-bd98-27289c0ea142 |  | tickbox | Correct number of connections for detectors
checkpoint-status |  |  | checkpoint | All main control panels at correct heights & positions
checkpoint-status |  |  | checkpoint | All required 1st fix testing complete
label | 942314f5-af5f-53e3-98b2-97414d52f29d |  | note | All piles to be cleaned and cleared before testing
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | FPIS inspection sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Service engineer Beca inspection requested
checkpoint-status |  |  | checkpoint | Protection provided for floor wastes and ends of unfinished pipes
checkpoint-status |  |  | checkpoint | Any onsite changes documented( add a copy)
checkpoint-group |  |  | section | Mechanical Services - Wall First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 40c2a3c7-98be-561e-9765-1b6079752598 |  | tickbox | Setout straightness checked
boolean | f2433e07-bb92-541c-a0e2-dcc8b0a54335 |  | tickbox | All required additional noggs placed in framing
checkpoint-status |  |  | checkpoint | Reference drawings ( add drawing numbers & revisions)
checkpoint-status |  |  | checkpoint | Mechanical wall QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First fix checks with subcontractor - tick when all below are checked and complete
boolean | bd36a592-4022-5bb0-aeeb-cfc1795e8574 |  | tickbox | Ducts checked for damage/corrosion etc.
boolean | da033819-0899-5d8d-9086-418c3fb14485 |  | tickbox | Ducts size correct and type
boolean | 9ca5b5df-eb5b-5da0-bbdf-57df8a471481 |  | tickbox | Duct supports , anchors and hangers/Clips installed correctly including seismic
boolean | 52164f55-b6ec-5dee-8b14-1ed05a54a811 |  | tickbox | Ducts And pipes insulated and labelled
boolean | 1772ffc6-e19a-5d1e-ba4e-e04bc7c6e612 |  | tickbox | Heights of pipework checked ( above ceiling)
boolean | bcfdf059-334a-5626-9f86-207cae70073d |  | tickbox | All required labeled/identification done
boolean | 916140a4-a245-5d03-8c83-def8e0eef1e2 |  | tickbox | All ducts cleaned
boolean | b4f6e9aa-fecb-581a-8c19-3648571a3ace |  | tickbox | Cables for thermostats etc, are completed and with proper support
boolean | a128d39e-3272-5bdb-a9fa-973a28c698a7 |  | tickbox | All equipment , valves and fire dampers, air outlets louvres, grilles and dampers are in place and accessible where required
boolean | c90919c6-01f7-54c7-8d7b-409010e77018 |  | tickbox | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council signoff
checkpoint-status |  |  | checkpoint | Engineer has signed off seismic restraints
checkpoint-status |  |  | checkpoint | Service engineer Beca - inspection requested
checkpoint-status |  |  | checkpoint | Protection of all ends & cleanup done
checkpoint-status |  |  | checkpoint | Any onsite changes documented(add a copy)
checkpoint-group |  |  | section | Electrical - Wall First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 6f34e491-8e41-59c5-b5d1-a2b0b943021a |  | tickbox | Setout/straightness checked
boolean | f5d805e4-8758-54c6-b6f1-20f86a6934f6 |  | tickbox | All required additional noggs placed in framing
text | 46650f1a-27a3-5bbb-963b-f3ceb596baad |  | textbox | Reference drawings ( add drawing numbers & revisions)
checkpoint-status |  |  | checkpoint | Electrical wall QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First fix checks with Subcontractor - tick when all below are checked and complete
boolean | 537eecd9-cf46-5f9d-ba34-f7fff27ed437 |  | tickbox | Cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | 20b81ad8-730a-5f34-8c36-4e81eb7966e1 |  | tickbox | Distribution boards in correct place
boolean | 9ed124aa-3540-50e6-874c-cecf99611597 |  | tickbox | All outlets and switches at the correct position & height
boolean | 31fa3b2c-7e01-5a96-bc38-f0f1415e8e6c |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 69bd6f1e-13a4-58b0-84a9-b157b6c8573c |  | tickbox | Power supplies for roller doors, HWC,sliding doors, fire ,security etc. installed in correct place
boolean | 2d879c28-616f-55df-90b2-92af5458413d |  | tickbox | All wiring labeled/identified
boolean | edf5459c-d048-5261-b753-98af3e9766a0 |  | tickbox | All earthing and cables installed
boolean | d49e4c78-b7de-5d1c-9eeb-ea3f15b70076 |  | tickbox | Cables are installed and with proper support
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Service Engineers -Beca inspection requested
checkpoint-status |  |  | checkpoint | Protection /cleanup done
checkpoint-status |  |  | checkpoint | Any onsite changes documented(add a copy)
checkpoint-group |  |  | section | Data/Security - Wall First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | da290b04-bcfa-5df5-a731-4fe3745c1632 |  | tickbox | Setout/straightness checked
boolean | 1900aac9-ab56-5e65-b096-9a14217b63ee |  | tickbox | All required additional noggs placed in framing
checkpoint-status |  |  | checkpoint | Data & security wall QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required first fix completed ( pass when checks done)
boolean | 1e730a71-e317-5368-8d23-8ee1d2d23085 |  | tickbox | Cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | 17b74eaf-ad8f-528b-9c30-a9e7407e0d06 |  | tickbox | Connections to distribution boards in correct place
boolean | 5cf6c685-af81-5c49-9f7b-7a39aece6892 |  | tickbox | All outlets and switches at the correct position & height
boolean | 200ba083-90de-5e40-8ae0-9e10298d47a3 |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 8200b602-2bd2-5417-8e6f-f13a343082e6 |  | tickbox | Connections for roller doors, HWC,sliding doors, fire ,security etc. installed in correct place
boolean | b0c57a7c-21e4-581e-ba45-fcb077faca2f |  | tickbox | All wiring labeled/identified
boolean | c6d20a40-080c-5c5f-b514-cf5e4cf54a2a |  | tickbox | All earthing and cables installed
boolean | 2910bb8a-70b3-5a7c-ab17-5a43d055936f |  | tickbox | Cables are installed and with proper support
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Service Engineer Beca - inspection requested
checkpoint-status |  |  | checkpoint | Protection /cleanup done
checkpoint-status |  |  | checkpoint | Any onsite changes documented (add a copy)
checkpoint-group |  |  | section | Insulation/Acoustic Checks
checkpoint-status |  |  | checkpoint | Insulation/Acoustic QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Insulation/Acoustic pre lining wall works completed, spot checks done
boolean | c4e6a5a4-8533-5fe5-82b1-2b0ad5b5b1a3 |  | tickbox | Spot checks on correct product /R value
boolean | 4a560089-ee3f-5a16-aecb-a9b3920e412c |  | tickbox | Insulation is fitting correctly
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checklist-sectioned |  |  | checklist | P-Wall & Ceiling Lining Checklist |  |  |  |  | Yes | P-Wall & Ceiling Lining Checklist | 50cbf1c7-32a2-40bb-9a4c-450a3b64f884
checkpoint-group |  |  | section | Gib Lining Checklist Ceilings
checkpoint-status |  |  | checkpoint | Gib lining QA received, reviewed, attached and approved pass when all below done
boolean | 46169f3c-5e96-5c68-b82e-1bb11ce58b72 |  | tickbox | All preline services completed and approval given to line
text | 984b9ebd-0548-5f65-818f-f79ae6ebf465 |  | textbox | moisture content checked, recorded and acceptable
checkpoint-status |  |  | checkpoint | Lining installed ( pass when all below ticked)
boolean | de3d42b5-d794-5193-9302-882e600f50d8 |  | tickbox | Correct lining type (Checked and approved)
boolean | 96ece109-8ba3-5f63-a331-80d9d263a424 |  | tickbox | Correct fixings used and installed at correct centers
boolean | d6cc2514-29ee-5df0-a087-5b88134280e8 |  | tickbox | Any bracing elements completed to design specification
boolean | 9271e34b-7788-52ff-803e-a81e4bfb8210 |  | tickbox | where required 2nd layer installed
checkpoint-status |  |  | checkpoint | Council inspection complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Walls & Ceilings Gib Stopping Checklist
checkpoint-status |  |  | checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint-status |  |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status |  |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status |  |  | checkpoint | Adequate drying time between applications & No visible bubbling
checkpoint-status |  |  | checkpoint | Gib stopping QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All stopping completed and specified level of finish achieved
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checklist-sectioned |  |  | checklist | Steel Stud & Thermal Break |  |  |  |  | Yes | Facade - Steel Stud & Thermal Break (V1) | 51132065-fa0e-4f65-8381-122835ba878d
checkpoint-group |  |  | section | Steel Stud
checkpoint-status |  |  | checkpoint | Canopy Steel & Secondary Steel signed off
checkpoint-status |  |  | checkpoint | Steel Stud -All framing completed correctly within tolerance in respective area
boolean | 25a48f82-fbc8-57e1-9dc9-16319137ab7c |  | tickbox | Dimensions / locations checked and accurate
boolean | c130bfd3-31e9-5d7d-9db3-4f6bc750b464 |  | tickbox | All frames are square
boolean | 62ffab62-14cf-5825-826f-505d86761119 |  | tickbox | Frames are straight and level
boolean | 319c55ac-34a5-5c73-a15c-43fbe3c19df3 |  | tickbox | Fixings are correct including seismic requirements
checkpoint-status |  |  | checkpoint | Façade Supports critical lines checklist completed
text | 2d6225b3-dc70-53d7-955f-cda4b01c7534 |  | textbox | Critical line number/location & elevation
checkpoint-status |  |  | checkpoint | Steel Stud General photos, comments and observations added
checkpoint-status |  |  | checkpoint | Steel Stud QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Steel stud- Engineer/Architect sign off
checkpoint-status |  |  | checkpoint | Steel stud-Engineer/Architect inspection
boolean | 79141224-4554-5a05-99ac-88819a8a94f5 |  | tickbox | Engineer remedials complete and signed off
boolean | 9c79495c-dce3-5aa5-bce7-6785e9a43d24 |  | tickbox | Architect remedials completed and signed off
checkpoint-group |  |  | section | Thermal Break
checkpoint-status |  |  | checkpoint | Steel stud completed & Signed off
checkpoint-status |  |  | checkpoint | Thermal break fixed/taped correctly
boolean | 647ef22a-3af0-5c7e-bc99-b25aff68302f |  | tickbox | Product as specified
boolean | c49263bd-5c70-51e8-85a5-8eef4e23f342 |  | tickbox | Fixings are correct
checkpoint-status |  |  | checkpoint | Thermal Break QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Thermal Break -Request for Inspections
checkpoint-status |  |  | checkpoint | Thermal Break Inspections
boolean | fbdb89f9-50eb-5fe3-a241-f53b6c3b8250 |  | tickbox | Thermal break façade engineer remedials complete and signed off
boolean | b8045468-56d8-57ad-a2f5-0649aa30872d |  | tickbox | Thermal break architects remedials complete and signed off
checklist-sectioned |  |  | checklist | Townhouse Cladding Installs |  |  |  |  | Yes | Townhouse Cladding Installs | 5498c5fb-3543-4e54-ba0c-e78bb12f7ce4
checkpoint-group |  |  | section | Metal Roof
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint-status |  |  | checkpoint | All roofing elements completed, checked and approved as per specifications
holdpoint |  |  | signoff | Request inspections
checkpoint-status |  |  | checkpoint | Inspections complete
boolean | cd394f7e-dd97-5779-bc13-744827f2d9de |  | tickbox | Façade engineers remedials done and signed off
boolean | a9c09d83-0562-5f67-b9ca-f2b166d1c9b0 |  | tickbox | Architect remedials completed and signed off
boolean | e08b6b9b-0ec0-5d42-a8ca-dc1ebb042be9 |  | tickbox | Council inpection complete
checkpoint-group |  |  | section | Downpipes
checkpoint-status |  |  | checkpoint | Downpipes installed & complete
boolean | 37fe20fd-608f-5c68-91cf-b118a27e0f79 |  | tickbox | Spot checks done
boolean | c3f3a4e1-b030-53ab-81fd-157bc63fc33f |  | tickbox | All inspection points installed
checkpoint-status |  |  | checkpoint | General comments and photos of additional paint application
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Water testing done and past
checkpoint-status |  |  | checkpoint | Council inspections complete
checkpoint-group |  |  | section | Membrane Installation (mark NA where not present)
checkpoint-status |  |  | checkpoint | Product checked and correct as per specification
checkpoint-status |  |  | checkpoint | All prestart checks completed and approval given to install
checkpoint-status |  |  | checkpoint | Mat installed as per product specification
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint-status |  |  | checkpoint | Tanking to area completed, checked and approved as per specifications
checkpoint-status |  |  | checkpoint | Initial testing complete
checkpoint-status |  |  | checkpoint | Any remedials completed
holdpoint |  |  | signoff | Request Inspections
checkpoint-status |  |  | checkpoint | Inspections complete
boolean | 0b6998bb-2d0c-58f8-ae8a-d8315ef093ad |  | tickbox | Manufacturer review if needed
boolean | 8faad9bc-99da-5b9c-91a8-8f3aab05c05c |  | tickbox | Façade engineers remedials done and signed off
boolean | c1665e29-a19f-58ac-abfd-39df57e9ae7c |  | tickbox | Architect remedials completed and signed off
boolean | 44ab3747-f8e1-5e3a-9438-cbd641dcd18f |  | tickbox | TCC inspection complete
checkpoint-group |  |  | section | Aluminium Window
checkpoint-status |  |  | checkpoint | Opening approved (ready for install of seismic frames)
checkpoint-status |  |  | checkpoint | Joinery in correct location
checkpoint-status |  |  | checkpoint | Nebulite QA (frames) received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Inspection completed and joinery install completed as per specification
checkpoint-status |  |  | checkpoint | Water testing done and past
holdpoint |  |  | signoff | Request inspection windows
checkpoint-status |  |  | checkpoint | Window inspections complete
boolean | eefd147e-b38d-5038-8c5f-e3866d8b7511 |  | tickbox | Façade engineers remedials complete and signed off
boolean | c458068d-350c-5c64-b36c-ec3a1c74c3d4 |  | tickbox | Architects remedials complete and signed off
boolean | d531d32b-1b40-542a-9181-fbb71d1282b8 |  | tickbox | Council inspection complete
checkpoint-group |  |  | section | Cladding Axon Panel
checkpoint-status |  |  | checkpoint | Product checked and correct as per specification
checkpoint-status |  |  | checkpoint | All prestart checks completed and approval given to install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Fixing type and spacing checked and correct to specification
checkpoint-status |  |  | checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint-status |  |  | checkpoint | All roofing elements completed, checked and approved as per specifications
boolean | c6e37525-81e4-5cbb-959f-8606709c56ac |  | tickbox | Façade engineers remedials complete and signed off
boolean | 0f756925-cd5b-5ded-9937-7e43a4218b98 |  | tickbox | Architects remedials complete and signed off
boolean | 4cf40573-bfc6-5d7b-a375-eca0f425505b |  | tickbox | Council remedials complete and signed off
holdpoint |  |  | signoff | Request inspections
checkpoint-group |  |  | section | Cladding Espan 340
checkpoint-status |  |  | checkpoint | Product checked and correct as per specification
checkpoint-status |  |  | checkpoint | All prestart checks completed and approval given to install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint-status |  |  | checkpoint | All roofing elements completed, checked and approved as per specifications
holdpoint |  |  | signoff | Request Inspections
checkpoint-status |  |  | checkpoint | Inspections complete
boolean | 23bb1e3b-2a4d-534f-815d-afdcb8ca13e6 |  | tickbox | Façade engineers remedials complete and signed off
boolean | 334949ef-1f85-5126-99ae-ed3af6c1e7eb |  | tickbox | Architects remedials complete and signed off
boolean | 8a486a1b-d091-5121-b622-9082ec1739d3 |  | tickbox | Council remedials complete and signed off
checkpoint-group |  |  | section | Soffit Lining Install - Level 1 & 2
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Soffits complete (pass when all below ticked)
boolean | 1a26ccf4-1c07-5bc6-96bb-85de15c608e9 |  | tickbox | Soffit Framing completed, checked and accurate inclusing sheet joins/blocking
boolean | 1f60cb28-f151-57a1-a87c-f114b4d8e0c0 |  | tickbox | Relevant services first fix and nogging completed
boolean | bf6e40a0-e329-5445-beb2-a479bec6c062 |  | tickbox | Lining product checked and correct, all pre checks completed & approval to line
boolean | 0f118c24-727b-5338-b45e-f6bac60cd24a |  | tickbox | Joints all neat and correct
checkpoint-status |  |  | checkpoint | General photos, comments and observations during installation
holdpoint |  |  | signoff | Inspections requested
checkpoint-status |  |  | checkpoint | Inspections completed
boolean | 272a0353-2586-5c7f-8089-cfababcb9dfc |  | tickbox | Steel studd engineer remedials completed and signed off
boolean | c1edd454-63ee-55b5-ae68-40bd19b07684 |  | tickbox | Architects remedials complete and signed off
boolean | f959ed51-5085-5300-8a36-0efc4e998e50 |  | tickbox | Council remedials complete and signed off
checkpoint-group |  |  | section | Soffit Painting
checkpoint-status |  |  | checkpoint | First coat/ sealant coat completed
checkpoint-status |  |  | checkpoint | General comments and photos of additional paint application
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Final coat completed, no overpainting, finish acceptable as per specification
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Design team inspections completed
boolean | c20e74e6-15c5-5c62-ba7f-e23966ed2624 |  | tickbox | Architects remedials complete and signed off
checklist-flat |  |  | checklist | Floors Checklist |  |  |  |  | Yes | T1&2 Fitout (New) - Floors Checklist | 560355f5-a274-4642-a33c-2818566ad8b9
checkpoint-status |  |  | checkpoint | Floor prep completed, checked and acceptable
checkpoint-status |  |  | checkpoint | Floor levels checked
checkpoint-status |  |  | checkpoint | Carpet flooring completed & correct
checkpoint-status |  |  | checkpoint | Vinyl flooring completed & correct
checkpoint-status |  |  | checkpoint | Tiles flooring completed & correct
checklist-sectioned |  |  | checklist | Wall & Ceiling Lining Checklist |  |  |  |  | Yes | T1&2 Fitout (New) - Wall & Ceiling Lining Checklist | 59108427-5b47-4ec8-bf0c-8845c9139a8a
checkpoint-group |  |  | section | Gib Lining Checklist Ceilings
checkpoint-status |  |  | checkpoint | Gib lining QA received, reviewed, attached and approved pass when all below done
boolean | c05a65e4-76d5-5e66-b28b-a8ec676ead1e |  | tickbox | All preline services completed and approval given to line
text | d58c7073-a3ad-5e4a-840b-c815afedd015 |  | textbox | Moisture content checked, recorded and acceptable
checkpoint-status |  |  | checkpoint | Lining installed ( pass when all below ticked)
boolean | 8a56d4fe-b4b6-5c60-9069-5dc3d43b79bc |  | tickbox | Correct lining type (Checked and approved)
boolean | 6b8fe59e-6339-5d42-9404-b82f88b8849d |  | tickbox | Correct fixings used and installed at correct centers
boolean | 714abd14-370e-51a8-a04a-a374263f7f99 |  | tickbox | Any bracing elements completed to design specification
boolean | 7e54455c-f671-5db0-bd31-363713947ac5 |  | tickbox | Where required 2nd layer installed
checkpoint-group |  |  | section | Walls & Ceilings Gib Stopping Checklist
checkpoint-status |  |  | checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint-status |  |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status |  |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status |  |  | checkpoint | Adequate drying time between applications & No visible bubbling
checkpoint-status |  |  | checkpoint | Gib stopping QA received, reviewed, attached and approved
checkpoint-group |  |  | section | Postline Inspection Checklist
checkpoint-status |  |  | checkpoint | All above postline elements checked, correct & approval
checkpoint-status |  |  | checkpoint | Council inspection complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Shop mark up drawings
checklist-flat |  |  | checklist | Structural Steel Painting |  |  |  |  | Yes | Structural Steel Painting | 5ae98727-b9fe-474b-a0e6-256084ef2ce4
checkpoint-status |  |  | checkpoint | Balconies - Nulifire SC 902 include photos of coatings & RAB reinstatement
checkpoint-status |  |  | checkpoint | Perimeter Steel - firetex FX 2003 - include photos of coatings and RAB reinstatement
checklist-flat |  |  | checklist | H&S - Harness Checklist |  |  |  |  | Yes | Harness Checklist V1 - H&S | 5be21ef0-d3ca-4bca-8c47-6a383758d87c
checkpoint-status |  |  | checkpoint | All below items closed out
text | 1e127cf6-f03b-4224-969a-8f181d961dc3 |  | textbox | Hawkins Team member to "pass" once satisfied all below items have been addressed
checkpoint-status |  |  | checkpoint | Harness check # 1
text | 64fec636-f56e-475a-a61a-ada650d88fc8 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 589e1bea-fc7c-46dc-9377-52aed3404a65 |  | textbox | Description
text | e0dda8bf-2c36-4be3-9cba-8fabb501c568 |  | textbox | Company/Person using
text | fd6f9575-46ed-4ad9-8f56-dab4a433ab5d |  | textbox | Serial Number
text | dd051648-de9d-44b3-8563-44076570e59b |  | textbox | Date of Manufacture
text | ccfd2659-3eca-4d7d-ae6a-9ea394547abf |  | textbox | In service Date
button | 23a561ec-a0f3-4c18-b948-07c230a23c23 |  | button | Currently certified | Yes, No, N/A
button | fe072035-ee96-4920-be3f-32d2994984ac |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 5d10b45f-1f90-4b61-bbce-c159f15fb79b |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | d3b060f7-b62d-443f-89e1-bc1499bd89e4 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 1a984099-1e2c-4feb-92b1-9346e48e46e8 |  | button | is webbing in good condition | Yes, No
button | 81199781-a010-4dbe-8538-4362380a6293 |  | button | Buckles in good condition | Yes, No
button | e72fccb7-cdc3-4faf-b4e1-26e5618364e7 |  | button | Labels - present and legible | Yes, No
button | 8906cade-15de-4264-a1cd-1ec7cf682b3f |  | button | D - Rings - in good condition | Yes, No
button | 80fdd7de-9016-4c7c-af76-024c8835ac1c |  | button | Connectors- in good condition | Yes, No
button | f3c8999a-94a1-48b6-9704-b85bdcb10ba5 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 8a8418ce-82ce-4148-84fd-5812170e10e7 |  | textbox | Action/allocated to
button | c3c4c878-25a0-4845-b0a8-08b628fd3c4b |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 2
text | 0c294228-cfce-43d9-85f0-ed83cd3ee6dd |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 4c240ab8-fc6c-4c0e-94cb-431f9b87e930 |  | textbox | Description
text | a28d241d-6ca2-40a3-9719-65ab99e1fe0f |  | textbox | Company/Person using
text | c9cc2836-63cb-48d2-80e9-1565e6b7eca2 |  | textbox | Serial Number
text | 04c1308c-3d60-4930-b363-07df07dccf68 |  | textbox | Date of Manufacture
text | fa8236cf-2e33-4d76-b0e9-d581f5a16114 |  | textbox | In service Date
button | 2d9df0a7-6f18-440a-9484-213ad21dd456 |  | button | Currently certified | Yes, No, N/A
button | 96bd9ddd-f6a1-4d46-ae88-b12b7bd6d5e0 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | b134f9ab-66f2-4646-b395-eb947bd71883 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 3e4202f3-72fd-4ab3-b1fb-3c99a52fd123 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 3d49a3a5-bc6e-417b-ba10-2412c3de014c |  | button | is webbing in good condition | Yes, No
button | 5f7042a2-7fa5-4e0e-a71a-de29110fc41e |  | button | Buckles in good condition | Yes, No
button | 5d28bc8c-e665-429f-beca-863ab1b35107 |  | button | Labels - present and legible | Yes, No
button | 73328999-0fb5-4d4f-a651-a23375989648 |  | button | D - Rings - in good condition | Yes, No
button | f67fe889-f923-415c-98df-5b13888700da |  | button | Connectors- in good condition | Yes, No
button | 720ef687-99d6-4e09-9b5a-1670a6d70f60 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 9fb3a97d-c66a-49dc-9c7b-fbdba8a3f0fa |  | textbox | Action/allocated to
button | e07b19c2-479b-4d31-8ed4-d92627fd9901 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 3
text | ced9e5d5-4c3c-48ac-8ffa-6b6aee9b07f5 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | dd6bce9a-c989-4413-b616-5a08b8134ca5 |  | textbox | Description
text | b2738de7-42fa-4650-a362-ab2f2a20df64 |  | textbox | Company/Person using
text | c128a18a-6973-4e64-9804-90a68ad2b605 |  | textbox | Serial Number
text | 498d0c94-22f1-423d-becb-7b6c11c13559 |  | textbox | Date of Manufacture
text | 1dcc4118-a955-49dc-8b01-a97d0abe742f |  | textbox | In service Date
button | 94fffdba-17d9-4d28-878f-53b1e3dbdb2a |  | button | Currently certified | Yes, No, N/A
button | dd630562-0c10-4142-96a9-4c28abd6aa28 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 3cee265d-b0b7-4422-a2d8-7e3cfb476ccc |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | f6cbe652-3bfe-4805-bcce-81e85c47376b |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 9d79ee8b-c6c4-40ef-98b2-6abda8a2bff1 |  | button | is webbing in good condition | Yes, No
button | 3c633301-af5a-43ea-9cb6-eda988113e22 |  | button | Buckles in good condition | Yes, No
button | 84e85961-7f30-42fc-8ff5-bb519811bac3 |  | button | Labels - present and legible | Yes, No
button | 788df49c-c5b0-42f3-9c29-0f346eeabb85 |  | button | D - Rings - in good condition | Yes, No
button | 7b3bdc0e-c99c-4103-9b29-5d7036e6fcc2 |  | button | Connectors- in good condition | Yes, No
button | ceac84c6-e5bd-41f2-a955-bfa4cab3b8f2 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | ef1dc316-775e-4334-aaf8-8d0d71865cbd |  | textbox | Action/allocated to
button | 93a2fc01-2166-4d15-bfc9-342ad91a2807 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 4
text | aa629f4f-1785-4baa-b36d-8da9e8e7ccc0 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 0361a70c-a489-4889-8155-8532aa7dbcec |  | textbox | Description
text | d6b7594a-3b8a-4f69-8631-063b335a2895 |  | textbox | Company/Person using
text | 2b32c93f-4f11-40ed-aad7-ebfb5e0b468e |  | textbox | Serial Number
text | 29460859-2d23-4b87-8b81-c14023be5cd7 |  | textbox | Date of Manufacture
text | bcb35d05-29f0-4a6b-8f13-7a90222a8571 |  | textbox | In service Date
button | d4ae8f42-0a0c-4c9d-8e35-7910dcc067aa |  | button | Currently certified | Yes, No, N/A
button | 4d8bb004-dcfa-4213-ab08-7f335fb38bc5 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 445ef437-dc18-43e9-b780-c841ca2c8c52 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 66211e28-50ee-46a3-9836-7b0e4d138cb2 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | f691214c-bd8b-4e35-bf0e-506e25857fd5 |  | button | is webbing in good condition | Yes, No
button | e597f5cf-bdd9-4083-b152-ce0a6d3abe25 |  | button | Buckles in good condition | Yes, No
button | 890d933b-8861-432e-9da5-5b01ce2d6189 |  | button | Labels - present and legible | Yes, No
button | 58948496-a17a-4ea0-b966-845f331b182b |  | button | D - Rings - in good condition | Yes, No
button | 2f49d855-b194-4867-ad22-7b18535cc710 |  | button | Connectors- in good condition | Yes, No
button | 67017ad7-a9ee-42ad-aa73-7d2f9ad1d510 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 6bd48221-f292-4429-a001-27753368b49b |  | textbox | Action/allocated to
button | 13c16179-dc16-45db-a104-6986e36fbdc7 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 5
text | 5c35eddf-925c-40e5-b3bd-11d7077881a7 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | b2876476-747a-4985-9ebd-ef3e7d2b9aa1 |  | textbox | Description
text | 61d6d1d3-5c6b-4dc3-b69d-c4bc2b73bc28 |  | textbox | Company/Person using
text | 743e4401-e11b-4ed3-8b22-df7a0487a034 |  | textbox | Serial Number
text | 5acd6e32-1c5e-4f53-9674-a0048638bd04 |  | textbox | Date of Manufacture
text | f5b2b0cf-d9b0-4395-826d-450761ab8df8 |  | textbox | In service Date
button | 717a80ac-8cc6-4fa4-b9ce-a17815799e9c |  | button | Currently certified | Yes, No, N/A
button | 1ff70ee5-dfbd-43f5-b18b-3b36dc168aad |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 2c2d2725-5715-4444-9ab7-3880e0922170 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | dee46915-45cf-4448-82f1-f9a2b5fa64f4 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 74bb9935-302b-49e0-b08c-c6afacb72eb9 |  | button | is webbing in good condition | Yes, No
button | 5c25f3ff-f493-452a-adb2-9ed50092fe11 |  | button | Buckles in good condition | Yes, No
button | 8a5a85ca-70b6-42e3-844a-e3462d31b5af |  | button | Labels - present and legible | Yes, No
button | 8a3cdf67-c9aa-4a30-82b9-e51cb4f0498d |  | button | D - Rings - in good condition | Yes, No
button | e266682b-9259-4b4c-b31f-ec18446e01d9 |  | button | Connectors- in good condition | Yes, No
button | 88403691-ad03-420e-8f79-6c6f29e34bb4 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 2cdbadd6-0152-4543-bb3e-9e531b99150c |  | textbox | Action/allocated to
button | 5fd6254d-32c0-4534-951a-b932bfd27df7 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 6
text | efa01722-a529-4b03-8649-1e52edf09737 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 7e7e85ab-3f8c-414d-8046-7722ab3fcc94 |  | textbox | Description
text | 1d6c01ae-b83b-4098-86c9-113dbd5dc774 |  | textbox | Company/Person using
text | 8ad7c0a1-ad58-444b-a40b-00442ce28b6c |  | textbox | Serial Number
text | bb608c36-b1d1-4369-9b4f-3ea06145aa64 |  | textbox | Date of Manufacture
text | a118dee6-9e59-484d-824d-55af7674f59c |  | textbox | In service Date
button | 11d21a80-1f01-4ebd-8df6-2963e12ec999 |  | button | Currently certified | Yes, No, N/A
button | c7aa7737-8447-4884-8476-aeed816ae3be |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 5af677ef-828a-44d3-816f-eee0cf72c96a |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 233b1f19-cc61-47de-8a2e-532b552f4832 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 9e09c4ce-a1e9-4d13-890c-c8adf3c31ac4 |  | button | is webbing in good condition | Yes, No
button | 3afc0380-32f4-402c-bc66-8706533cf9bc |  | button | Buckles in good condition | Yes, No
button | 21503d4b-8245-4b10-a5ee-e357c5149c08 |  | button | Labels - present and legible | Yes, No
button | acb29bf8-09b7-4fa1-8d61-7a0451bb8ee2 |  | button | D - Rings - in good condition | Yes, No
button | a3d88535-116e-47f7-85df-2e316d46e3c3 |  | button | Connectors- in good condition | Yes, No
button | d467f015-8a1a-4fcd-85ff-476d41334b9c |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | a1a5db1b-182d-4585-b596-f41944ff9b5e |  | textbox | Action/allocated to
button | 9dd1d8cb-1887-43a8-a66b-d1619cb55160 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 7
text | cb20c374-a6ef-4f66-bb42-de64573d34cf |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 84a25962-e9af-4321-8475-5ab58d9b2abe |  | textbox | Description
text | 7239378d-2aa2-4672-828f-c409100335f2 |  | textbox | Company/Person using
text | 1ad9a9cf-2981-4d41-aa91-766937e22407 |  | textbox | Serial Number
text | a62d13c6-c7d2-4b76-8192-d5834380932b |  | textbox | Date of Manufacture
text | 8c24729e-4068-41b2-b5bc-64639d5a8853 |  | textbox | In service Date
button | b98186ee-d3cc-442e-917f-a436bf9d5773 |  | button | Currently certified | Yes, No, N/A
button | f20cee21-aefb-44ea-98ac-c5892dee6507 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | f76bcfef-48a0-46b4-98a6-03b6b478647e |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | ca747ee3-76e8-41d8-bc48-af5ab6024a1b |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | afe5db6d-e2d7-4647-b76f-44d8163d507a |  | button | is webbing in good condition | Yes, No
button | ecbb3e89-e45e-439c-a820-b68917e63231 |  | button | Buckles in good condition | Yes, No
button | ebfde1ab-06eb-49ea-b94f-b1dd43da0745 |  | button | Labels - present and legible | Yes, No
button | 759a4f46-d6b5-47ef-ac50-56c97a78f3d1 |  | button | D - Rings - in good condition | Yes, No
button | 6320a477-94ec-4119-93ac-836a0493dd45 |  | button | Connectors- in good condition | Yes, No
button | 24c4928e-63d8-405a-9d0b-95edbec022bb |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 3dbea205-76b2-4522-90d9-2c067eb6225b |  | textbox | Action/allocated to
button | 1a240234-7210-439a-b866-198d8e32a17b |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 8
text | 55e64e72-c50a-43d8-8f5b-07abe8cbdb86 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | d6df25f9-6603-4264-89f7-083b2acd7dfa |  | textbox | Description
text | 5eaeddc9-11a9-4bf6-bdd4-9b7a73246527 |  | textbox | Company/Person using
text | 4f6095a3-6599-42aa-8ab3-bdc48c5dde11 |  | textbox | Serial Number
text | 44ead6a9-a9a9-46cf-b4da-45367ba74642 |  | textbox | Date of Manufacture
text | 35324340-7dfb-4224-b9b5-027a151255e5 |  | textbox | In service Date
button | 5a5fe7c2-4179-4004-b182-b4013338b5fc |  | button | Currently certified | Yes, No, N/A
button | 1900d29b-a59c-415d-9b91-c319e780a04e |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 350b7ba9-7fff-4a39-86bd-8ca61ecb5aa0 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | d91a6b77-93c0-4646-b6ed-047ff0743769 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 3dfc07d7-b04b-4a20-ada7-df39a1c8d1a9 |  | button | is webbing in good condition | Yes, No
button | ce9a3752-9232-42e0-8bcf-441b72ff1eb0 |  | button | Buckles in good condition | Yes, No
button | f0e9949b-3eff-49cd-b91d-b6b119bf7a3c |  | button | Labels - present and legible | Yes, No
button | 04e8208f-bea1-4b20-80cc-6e6169a822cf |  | button | D - Rings - in good condition | Yes, No
button | d2de664b-0123-4de6-b578-75c760668b90 |  | button | Connectors- in good condition | Yes, No
button | 91d8bf92-0f1e-4c8d-a91e-d5b88fb585be |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | bf89aa89-79fc-42c6-8bf4-b7f049879ea2 |  | textbox | Action/allocated to
button | d19e62b3-6bb3-486c-953a-c3a9234b933b |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 9
text | 601d7c94-52cb-4b0f-ac3d-6e757108f58e |  | textbox | Location Zone /Floor Level /Inside or Outside
text | f32186a4-ee74-440a-b6ba-8532dc94a358 |  | textbox | Description
text | 703c9a2e-1880-4e8e-b91d-62806525d22f |  | textbox | Company/Person using
text | d5b6ae95-ea09-4fc8-a174-6c3071cf4777 |  | textbox | Serial Number
text | ad062c32-58ac-4cb5-9cc8-35b669bed49d |  | textbox | Date of Manufacture
text | e2aac4d9-ec94-47fd-9a43-8efb07100ce1 |  | textbox | In service Date
button | d34dd82b-0050-4114-82c6-aff705154492 |  | button | Currently certified | Yes, No, N/A
button | bbb0e86a-a797-4131-b5b8-ffe2f0ad3a61 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 3816dfd0-d315-4cc2-8b88-8d96bdcc2280 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 1b99561b-0a9f-4ddc-8de3-769430424f01 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 4f005fc1-4985-491e-8662-ce7e41a9d05e |  | button | is webbing in good condition | Yes, No
button | 5a2590be-fbf6-4468-a1e4-2a520aa43274 |  | button | Buckles in good condition | Yes, No
button | 1ef905d3-8b8b-4f8f-877c-0ed34461ea4f |  | button | Labels - present and legible | Yes, No
button | 9a297824-c91f-459c-a076-7dd783f93251 |  | button | D - Rings - in good condition | Yes, No
button | 98e9c0af-ec20-4039-b1be-570c083c9ede |  | button | Connectors- in good condition | Yes, No
button | ac82b76e-9581-4448-ad9f-7b30ddcbda42 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | ec0f46a1-6fa8-4474-97b3-d9faf3711c88 |  | textbox | Action/allocated to
button | 2a085804-342d-42d5-9b22-ee14e3feb195 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 10
text | a1c48e84-a788-42f5-b828-fd544d56197d |  | textbox | Location Zone /Floor Level /Inside or Outside
text | f4d83a9a-4173-4462-b152-7a9abaf04227 |  | textbox | Description
text | f455006c-aa87-4172-8694-8891b9ddb51f |  | textbox | Company/Person using
text | 6d643866-ae41-44d6-a04e-091c969f9c68 |  | textbox | Serial Number
text | 5c94ae90-deb0-4fb2-a8f8-d6b83f8c8c9d |  | textbox | Date of Manufacture
text | 9370440a-9973-46ca-ba41-22259ecc0736 |  | textbox | In service Date
button | cdf046c6-0eb0-415c-be58-c3a6b5f9ede4 |  | button | Currently certified | Yes, No, N/A
button | fdf03c35-b9bf-4c0b-8c14-c89fae6a6b30 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 3e43bd2d-2812-43ca-9ab5-4d3680e51a27 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 2b371ba7-da0e-4f32-b343-fb1627c2ee35 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | c70d681a-fc95-4787-abea-ec75a8b13698 |  | button | is webbing in good condition | Yes, No
button | 991ff743-a1c5-44ea-a089-ede20f5cd75e |  | button | Buckles in good condition | Yes, No
button | c678b1c7-bc47-45b1-b027-b13004a3bd83 |  | button | Labels - present and legible | Yes, No
button | ed1c3979-b81d-4544-ba61-e06443ebd460 |  | button | D - Rings - in good condition | Yes, No
button | e791126c-e61f-43c4-9eee-f98aed568b09 |  | button | Connectors- in good condition | Yes, No
button | 6707387d-0cb7-4088-9597-206e3e0cfe01 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | c7d88e07-9399-49d4-ba20-a701087f6fe6 |  | textbox | Action/allocated to
button | 5e46a7e9-253f-4f74-910f-13442ec63314 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 11
text | 93903a74-3c8e-46fd-8318-0259db414b8c |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 2e6af8fc-d852-4007-aaab-f782032215a2 |  | textbox | Description
text | f804ce1a-bb65-40c2-93fb-77897566c704 |  | textbox | Company/Person using
text | 8f8b82d1-ddbd-4204-8b76-b12207cfd3e1 |  | textbox | Serial Number
text | ffa61021-b9b1-494a-b0b8-ad25fecf008b |  | textbox | Date of Manufacture
text | 5780e2c0-4ed5-4c3c-854d-1e07e39a9610 |  | textbox | In service Date
button | 5a60413b-999d-4cbf-ac47-d5e35aecc437 |  | button | Currently certified | Yes, No, N/A
button | aa875eaf-17cc-4f7d-b2c3-2a5497c5f3f9 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 53caf090-4aec-4f41-8d01-9d7ff7221232 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | a2e1a2ac-82f2-4aa1-bf9d-5de6d81cb01f |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | d772090a-89be-4aa8-9049-8cdb476ef56d |  | button | is webbing in good condition | Yes, No
button | e63aaa87-170e-4197-a772-5551237e985d |  | button | Buckles in good condition | Yes, No
button | b308bf6f-bc6c-41e9-8538-56c05c57580a |  | button | Labels - present and legible | Yes, No
button | ca1a7108-3b02-491b-aeef-fe4b38667336 |  | button | D - Rings - in good condition | Yes, No
button | 7934fac8-9501-43de-87f8-a7a42c376516 |  | button | Connectors- in good condition | Yes, No
button | b55f64b8-fac3-4817-933e-f50424a7fdac |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | ffdcc54c-f35d-401c-b125-3957aaf70062 |  | textbox | Action/allocated to
button | 6fe5c1c1-4ab8-4ff4-8c20-4ed25482b43d |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 12
text | dedb3269-349b-4a83-a197-301449bcbab0 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | fe7374f1-3e6e-4d42-9eb8-fc66f4d72abd |  | textbox | Description
text | e2cf07fc-aac7-426d-8592-9b95bb00a627 |  | textbox | Company/Person using
text | 866c7f34-215c-4391-a858-5bddc0a6d2cc |  | textbox | Serial Number
text | 021d3178-debf-47b1-aa85-afd5f1ba0149 |  | textbox | Date of Manufacture
text | 7caa4a7f-b9df-4772-b4bd-2b0d83144a33 |  | textbox | In service Date
button | 3a768795-6282-4b09-a78b-194e58d1a2bb |  | button | Currently certified | Yes, No, N/A
button | 879c977b-114c-429f-90c3-e2e2e21491a8 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 918e24aa-60de-4609-9251-399340c352f9 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | e8e255df-439d-4c41-b303-6923c289ff7c |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | ad0ad009-d2a1-4676-a1c4-84b46ffef80f |  | button | is webbing in good condition | Yes, No
button | d05bd701-b411-45d0-aa47-c47863514e2d |  | button | Buckles in good condition | Yes, No
button | c12bda1c-945a-4781-a030-af06b21c2f46 |  | button | Labels - present and legible | Yes, No
button | 2a2ab338-92aa-41bb-8fde-fec9fe1a7349 |  | button | D - Rings - in good condition | Yes, No
button | dd86a954-96ee-47a7-a614-2dc8bbc5a0ba |  | button | Connectors- in good condition | Yes, No
button | 0888b2a2-4bd8-47a3-a8c8-dd77f438d81b |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | c105e0b4-26f1-412f-8402-3d253eaef713 |  | textbox | Action/allocated to
button | f1ec3788-62c7-4e41-bf28-ce2391db0097 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 13
text | 97fe8778-c206-4e2d-a9d6-27990af27019 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | d8fbc6dd-6860-4448-846a-b413022cef35 |  | textbox | Description
text | fd1a6840-a1ba-4616-9b4f-fa0894b9398c |  | textbox | Company/Person using
text | 86eb8b4d-7806-481b-b003-ee9618fdeb3c |  | textbox | Serial Number
text | 7bb55e71-a06c-4496-9e26-449e375cc0d7 |  | textbox | Date of Manufacture
text | a5b7e84f-cbfe-4d76-8cce-678d481b9c93 |  | textbox | In service Date
button | d0b2a244-ca27-4f34-8b9b-bc78d540c124 |  | button | Currently certified | Yes, No, N/A
button | cf3140b4-4764-48d2-a6f3-72c11b697233 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 33d9534a-7747-4431-aefa-5f3f3e5832a8 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 705ded6d-81f4-4f57-8b10-1662700b64b4 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 5e8b4e35-ce9c-4581-859b-128707007c9e |  | button | is webbing in good condition | Yes, No
button | 2ea87a1d-1af5-40e9-9db4-8aa212f4462a |  | button | Buckles in good condition | Yes, No
button | 810ad5ee-9dd6-446f-a9dc-bd4d7f1d747a |  | button | Labels - present and legible | Yes, No
button | a299ce50-904c-4b1e-b260-574e2ac14c3b |  | button | D - Rings - in good condition | Yes, No
button | ac2479fb-e51c-4f7f-bf05-4205a1942a1e |  | button | Connectors- in good condition | Yes, No
button | 2ebe45a2-bde0-4620-a809-2ff652f74ea3 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | d2722322-83ea-4444-8964-ac1c4d9966ab |  | textbox | Action/allocated to
button | 19baab56-6fa7-4316-b2c8-09bb16a9a46b |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 14
text | 83509a35-eb0b-4c5b-85de-55f59b517f72 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | b53f3d9d-2577-40e2-8719-afb411ec07b6 |  | textbox | Description
text | 240389f6-698d-4e44-a059-0d5759f8953d |  | textbox | Company/Person using
text | 189c2090-3dae-4764-8d0f-2680df82cbd0 |  | textbox | Serial Number
text | e1e0a5e8-8ca8-48ea-8f3d-967eaf48176b |  | textbox | Date of Manufacture
text | 7963145a-a0b8-48ee-908a-70fbb37fded2 |  | textbox | In service Date
button | 7df025f4-5c49-4f54-8f94-bc7fc57f1ccc |  | button | Currently certified | Yes, No, N/A
button | 203462e7-d735-4406-9819-5d24d0f5f490 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | ceaf3a60-ee96-4cbc-895d-318e98c95706 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 97bd4456-24c8-4043-bf60-470a4cf96eb6 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | eee2ac9b-ddb4-40af-8f50-144a38c2c869 |  | button | is webbing in good condition | Yes, No
button | 93a1b53b-3da4-446c-83d9-98c0505d575a |  | button | Buckles in good condition | Yes, No
button | e280bc1c-1187-496b-a9ef-b860a8eb671b |  | button | Labels - present and legible | Yes, No
button | 313ff0bf-3699-423d-95f6-1f823345e4b4 |  | button | D - Rings - in good condition | Yes, No
button | 648f4d5d-adb4-4c51-8805-4c352ee7f185 |  | button | Connectors- in good condition | Yes, No
button | ed274fe0-6317-43ac-b65d-e321fae21286 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 7b57a2d2-5639-47b6-8e85-debe92dd4711 |  | textbox | Action/allocated to
button | 6b685a14-0d61-4870-aa52-59f20a4ca67a |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 15
text | f74356da-768a-40b6-829d-07d6d4ebb66c |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 6e54da96-766e-4c27-a858-079d57709ea5 |  | textbox | Description
text | db79bed2-5e38-490f-a098-7df1a5bd2962 |  | textbox | Company/Person using
text | 4f69546b-c0ef-4706-9b92-5af88eb1db5a |  | textbox | Serial Number
text | f71b37b4-3627-4444-bd0d-ec60798c83ab |  | textbox | Date of Manufacture
text | 3b4f8b6b-5b7e-49b5-81f2-2da0c68a3961 |  | textbox | In service Date
button | c3f4c4da-99b2-49f2-a0b1-67f4d8468527 |  | button | Currently certified | Yes, No, N/A
button | 59721639-62e8-4897-81da-f50afb0ed7a4 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | b5556e4b-28c4-480d-a978-40fffb52c632 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | d5399626-b82a-4fe8-bac5-9ab35ebe53f4 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 4ba3880a-bfe5-4c53-b0f7-b26e9b31608c |  | button | is webbing in good condition | Yes, No
button | 02c5401e-9eb9-44b9-970e-2c0ddb9eb66c |  | button | Buckles in good condition | Yes, No
button | 7df4a034-8b77-4485-a82e-ad07339f2e80 |  | button | Labels - present and legible | Yes, No
button | ee11e866-c616-4465-afde-6c3f2eaad239 |  | button | D - Rings - in good condition | Yes, No
button | fb0eb5cc-d31b-4675-a7d6-aea63b0dd68b |  | button | Connectors- in good condition | Yes, No
button | db3c215f-d1bc-4444-bd48-b176a20ed244 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 0521b4c2-7f3a-4401-9836-021baf2dd019 |  | textbox | Action/allocated to
button | 7cd8819b-c890-483a-9d5e-dd97523670d2 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 16
text | eafa2a2e-881a-439a-8436-d38cc148cf16 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | dc98baf9-b048-44a9-a860-c72457957126 |  | textbox | Description
text | cde5591b-798f-4eec-aff4-74292410dc7b |  | textbox | Company/Person using
text | a5101972-0c3e-4b60-beff-97ace14c61f1 |  | textbox | Serial Number
text | 67131de2-ba99-493b-8a78-69c9e7786ced |  | textbox | Date of Manufacture
text | 02213480-cdcc-495e-b857-ff812a14e0fe |  | textbox | In service Date
button | 243441a7-9b33-4e77-b9fc-524d4833c3b3 |  | button | Currently certified | Yes, No, N/A
button | f533a89b-4121-42d1-b400-e2e1c1044059 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 74a2da16-a5f7-4c8d-9ee1-d902b9d4193f |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | aaea68ce-ee03-44ad-8a01-d6f237d9dc76 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 15080dd0-4421-454b-87e8-d72604c3202a |  | button | is webbing in good condition | Yes, No
button | 7501205a-3d89-4f17-ab5b-8196d466982d |  | button | Buckles in good condition | Yes, No
button | d2d4c330-3316-4eb0-bfde-2bbadbf0c98f |  | button | Labels - present and legible | Yes, No
button | b24ea2e3-b9e2-4f4e-8ab9-69ffa3407e9b |  | button | D - Rings - in good condition | Yes, No
button | 5a527360-c872-4f41-951c-56cf79837a88 |  | button | Connectors- in good condition | Yes, No
button | 9cfa66e0-3dc9-4145-bb0e-1fac9e515754 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 3e3c92d4-a295-4919-8877-9ab56e5f1b07 |  | textbox | Action/allocated to
button | e2cc9686-d604-4c8a-a03c-66d7e0d8250e |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 17
text | 3aefa035-2ab7-4228-b40d-b092a1875cdf |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 6ca01ef2-25e6-4051-bc2f-993b7cf8581f |  | textbox | Description
text | b8ef821a-231a-4b14-bb4a-6d9510667c24 |  | textbox | Company/Person using
text | 28518da3-9998-41e5-bd94-4111fe12afd1 |  | textbox | Serial Number
text | fc9031ca-1a27-4c1b-9aca-d2bd0338b851 |  | textbox | Date of Manufacture
text | 9990101e-4859-443c-a186-9645cfa5c4cf |  | textbox | In service Date
button | fa2d6f8c-a1f0-4dc5-b152-13b52932f062 |  | button | Currently certified | Yes, No, N/A
button | 7940a005-5c83-4c3b-9790-50fb9d6972c5 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 8bd4c097-e34f-44e6-a68a-4f2dbe326293 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 5505b203-35b7-43e3-9217-3ab084c9aa7b |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | cfa67da2-b26d-4274-b6f0-9b2323acaf04 |  | button | is webbing in good condition | Yes, No
button | 38ffdc97-9c33-4c24-ba21-e1f1e591a159 |  | button | Buckles in good condition | Yes, No
button | 4e56570d-ed5f-4764-b3e1-e0ee50810baf |  | button | Labels - present and legible | Yes, No
button | 7e365f9d-42d0-4853-9c60-004c2a32ee52 |  | button | D - Rings - in good condition | Yes, No
button | 58a432f1-e556-4a54-9521-9b7d660906d7 |  | button | Connectors- in good condition | Yes, No
button | 5a9c928a-606f-48d4-8196-ae1dbfabc016 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 42bc434e-4287-4689-bfa6-3d3f2a768092 |  | textbox | Action/allocated to
button | a99f7980-7505-48ca-a1bc-412ea0889b6f |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 18
text | 989a9b3b-4224-4a19-873b-71d6f0b32ab9 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 931dc939-1e4b-4a0d-a13c-a91aaabafbfd |  | textbox | Description
text | d0615048-8d0e-482e-ad7f-7f4b92ddbf33 |  | textbox | Company/Person using
text | bb95cc8e-be44-4cc3-a40b-23f819ec1c20 |  | textbox | Serial Number
text | a0119bec-6d84-4fba-bd2d-e61f63aa2a04 |  | textbox | Date of Manufacture
text | 457edbd0-4e1a-4f73-8859-7c04cc2847b9 |  | textbox | In service Date
button | 9ea5ee78-40fa-45d1-a8a4-77577f1ae951 |  | button | Currently certified | Yes, No, N/A
button | 93284eca-276c-463d-bad6-2dba7338ef9f |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 7603c091-8075-4d13-b7e3-a28255b401b8 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 8b1efaf8-bc9d-493c-b4b7-7bd2b89fe74d |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 0fca672d-2509-4f12-9fb0-ec3d92316854 |  | button | is webbing in good condition | Yes, No
button | dbae8e85-2a4b-49ba-80ab-cdabd9ac3a3d |  | button | Buckles in good condition | Yes, No
button | 1cc7f94a-156f-460f-a049-bcad52b03072 |  | button | Labels - present and legible | Yes, No
button | 685a325e-d84c-49cd-b6a0-f9a8c226e25d |  | button | D - Rings - in good condition | Yes, No
button | be28b40b-c148-4bdd-ac09-bf1ad50a2e84 |  | button | Connectors- in good condition | Yes, No
button | 200287e5-8fb8-4468-b54d-2cc53d8913ee |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 3948a720-27f1-4eb6-989f-2743a8ccd9e4 |  | textbox | Action/allocated to
button | 68bb4303-03ad-4619-ae98-a412d274ec81 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 19
text | 1a716b22-2f51-4f2e-8b01-8bafdbacf7a1 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | d99f5578-5d40-4947-a64e-50b2344be486 |  | textbox | Description
text | f5ad3e5c-6cc7-43d2-94d7-344bc96e8bda |  | textbox | Company/Person using
text | 70d731dc-f508-4731-a67d-6de937f977f4 |  | textbox | Serial Number
text | 7015301f-4e49-4291-b8d6-e66f5fbd9042 |  | textbox | Date of Manufacture
text | eb5c7321-7d32-494c-899b-6c2e4777679a |  | textbox | In service Date
button | f810c14a-cfb4-4689-bc44-c1ad671ca235 |  | button | Currently certified | Yes, No, N/A
button | ab8ef1a4-241c-4989-a2c5-19d7a972ecc4 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | c6a64ba0-653d-4f51-8bde-792493ccbcdc |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 711023be-dd95-44c1-b66b-163e083efe48 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 62d34303-423b-457d-92ee-5d1f50676bac |  | button | is webbing in good condition | Yes, No
button | d2c22d4d-765b-41ed-822c-0f63359ea0dc |  | button | Buckles in good condition | Yes, No
button | 3e24b09e-0c1c-4dd5-b2ae-b0fe5160c04f |  | button | Labels - present and legible | Yes, No
button | 719d5ebb-4b66-4981-b621-a10c824d0495 |  | button | D - Rings - in good condition | Yes, No
button | 2cecd337-2c1b-42bd-a530-c6316c3f3c75 |  | button | Connectors- in good condition | Yes, No
button | 2af4bb06-8602-4c5c-b4a7-eceace39b331 |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | e7ed799e-4f01-4300-b847-e3916007aa6e |  | textbox | Action/allocated to
button | 454a15c8-cfb2-4663-a623-bade90a6d5a8 |  | button | Action completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Harness check # 20
text | 7bf17eef-5ee8-4764-b9c5-edca751a50ab |  | textbox | Location Zone /Floor Level /Inside or Outside
text | cd448770-a293-4a13-a8f2-8c58f2332a0f |  | textbox | Description
text | 586432e3-9b51-4bbe-8000-9b6767c34fe6 |  | textbox | Company/Person using
text | 5bf6d8f0-c3e1-4eea-9905-2401788facb7 |  | textbox | Serial Number
text | 87110a92-f89a-47d3-9a72-cdd1b4766812 |  | textbox | Date of Manufacture
text | bc79c50c-28fd-4e0f-a3ee-fc4b7afbd3e8 |  | textbox | In service Date
button | c6728e44-2682-46be-94d1-6d57cbcbcba6 |  | button | Currently certified | Yes, No, N/A
button | 73d81577-71b1-4950-9156-fcc91c0ce822 |  | button | Is the harness being use? If so is operator competent | Yes, No, N/A
button | 78369c54-4376-4ff3-99c2-04e4a8432d72 |  | button | Is Correct PPE being used with harness/lanyard | Yes, No, N/A
button | 21d806af-63fb-45d4-94c7-17e20295bb79 |  | button | Impact Indicator( where applicable) in good condition | Yes, No
button | 2db53aa5-58db-4c43-a66c-632192394045 |  | button | is webbing in good condition | Yes, No
button | 3eabf378-b9b9-45ba-9798-3bff69b580c9 |  | button | Buckles in good condition | Yes, No
button | 471b39ba-0dc0-4422-a247-324750fab1e0 |  | button | Labels - present and legible | Yes, No
button | 57b147e3-83a1-4f72-8fc3-f3dbd604dbf1 |  | button | D - Rings - in good condition | Yes, No
button | e128e10d-6554-4682-8da4-f3a3e0438cae |  | button | Connectors- in good condition | Yes, No
button | ae3e06bf-12e6-4ede-8369-ff091cccd34a |  | button | lanyard in good condition ( not broken/cut/frayed/ coming undone/Burned) | Yes, No
text | 2eeca878-e87d-430c-9ab9-82b07c2b1196 |  | textbox | Action/allocated to
button | e59046d4-3f62-467d-aa8d-5615529e5e5b |  | button | Action completed | Yes, No, N/A
checklist-flat |  |  | checklist | Underground Services Install - Comms/Data |  |  |  |  | Yes | Underground Services Install Checklist - Comms/Data - QA | 5c97f748-424c-443b-99cf-b96ee4cff373
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | 7cf5f319-4791-448b-82d1-e79c4e7fe068 |  | textbox | Subcontractor:
text | 2f8f7eaa-1fe6-4600-acdb-b0c121aabb2d |  | textbox | Drawing Reference:
checkpoint-status |  |  | checkpoint | Electrical Works complete
boolean | b84c7abe-d48d-402c-8ad4-af5157c53374 |  | tickbox | Pipes cut clean and square
boolean | 86d7aa1a-fb59-4295-b9ce-e43e7e3706d5 |  | tickbox | Located in the correct location
boolean | db010e9c-7227-443f-8852-5ff1806242d1 |  | tickbox | Pipework protected where required
boolean | 6bbe3f70-9f85-4017-b8ed-65eff897ee4d |  | tickbox | Drainage material under pipe
boolean | c8e33c9a-35f4-47c8-9d5b-8b61ad65f683 |  | tickbox | Levels and inverts correct
boolean | 087648d9-2065-4ecd-bf62-75cb9fe8dd42 |  | tickbox | Pipework to correct falls
checkpoint-status |  |  | checkpoint | Testing to council requirements pass (pass once inspection is completed and approved)
boolean | b7fb2600-5235-4923-82f3-cf7f23557515 |  | tickbox | Councils inspection booked
boolean | 15b4aa16-4583-44d0-aff7-be281a757323 |  | tickbox | Council inspection compete (attached in Council Inspection folder)
checkpoint-status |  |  | checkpoint | Consultant inspection completed & any observations closed out (Inspection attached in Consultants folder)
checklist-sectioned |  |  | checklist | P Walls & Ceiling Preline Checklist |  |  |  |  | Yes | P Walls & Ceiling Preline Checklist | 5cd7b26f-0622-4bdc-82ae-32573be19aed
checkpoint-group |  |  | section | Interior Framing Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area ( sign off when all Complete)
boolean | 3f1c063c-1b8c-53b3-b462-42a36fbfd455 |  | tickbox | Spot checks on frames for square
boolean | 6b9aca3b-2143-5465-a50f-362d1302cf0b |  | tickbox | Spot checks on frame level
boolean | 4a3a9e9d-2df6-51b2-b417-958174a561d7 |  | tickbox | Fixings are correct including seismic requirements
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Plumbing First Fix Walls & Ceilings
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Plumbing install First fix complete - checks done based on current drawings ( attach and pass once all complete)
text | 3e5508f4-a50b-5f48-82b5-9603bdfbefdf |  | textbox | Confirm drawing and revision number
boolean | d034afe4-b6d5-5381-8537-c90601f281d7 |  | tickbox | Pipes size & type
boolean | f75d9152-d2e6-5468-9c78-395924037693 |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | 19917ca3-6d70-5e11-a013-861dd0b23919 |  | tickbox | Correct number of outlets
boolean | dd497697-89e9-5af7-a3eb-9f1e8f29b2c3 |  | tickbox | Any valves/vents installed
boolean | 7a8e6cda-da1f-5827-ae65-888cec501062 |  | tickbox | Pipework protected at holes and notches
boolean | f0dabc62-bf00-5cbb-b066-6770156a65fb |  | tickbox | Heights & positions of pipeworks checked ( above ceiling)
boolean | 15484d13-2d4d-54d0-a55d-6b9360762991 |  | tickbox | All vents installed
boolean | 21ce4a43-cc3f-56d8-bcdc-67ab6f39b891 |  | tickbox | All lagging is inplace
boolean | 15cf1ee6-75c9-58e1-8a0b-4369dce2e5d3 |  | tickbox | All labelling installed for pipework
boolean | 4acaccaf-8d42-5f71-b0d1-2f9e796d43ee |  | tickbox | All required noggs have been added
boolean | 4db524b1-ebee-53d4-a6cc-b67fdd3043f0 |  | tickbox | all pipes cleaned/cleared before testing
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-status |  |  | checkpoint | Engineer has signed off seismic restraints
checkpoint-status |  |  | checkpoint | Protection Provided for floor wastes and ends of unfinished pipes
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Fire Protection Walls & Ceilings (sprinklers & Alarms)First Fix
checkpoint-no-status |  |  | checkpoint | Reference Drawings:
text | bf1cddba-6f9d-582f-92a2-a7bbbad1540a |  | textbox | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
boolean | ab7f105d-8350-5929-873a-5d8d43e5855a |  | tickbox | Pipes checked for damage/corrosion/Scale
boolean | 7d8cb81a-4070-5c9b-95ea-cd80084fb1d3 |  | tickbox | Pipes size correct and type
boolean | bb9dbee9-d1df-55a8-884c-3f8aeecca824 |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | 0c74b561-33f2-5a60-b479-8ac146b1fd4f |  | tickbox | Correct number of outlets/droppers for sprinklers
boolean | db0576ea-547b-5c26-a567-9b4507ead853 |  | tickbox | Heights of pipeworks checked ( above ceiling)
boolean | a81d58f7-daff-59be-b647-e9ef3f004241 |  | tickbox | Any lagging required is in place
boolean | 54966fe9-ded4-5d3d-ab5c-ba610efc3cea |  | tickbox | All required noggs have been added
boolean | fad2cf54-2773-57f4-94ec-b17e56c126ae |  | tickbox | All labelling installed for pipework
boolean | 9407fb8d-e88a-5ea0-89ad-d2f08bf0332f |  | tickbox | Cables are completed and with proper support
boolean | c7c546bc-cc7d-5243-a83d-923ef1aa2d32 |  | tickbox | All wiring labelled/identified
boolean | 7a030ef3-9614-531b-82af-f44908568331 |  | tickbox | All pipes cleaned/cleared before testing
boolean | 867633c5-05ca-5631-a92b-cc2f28857ab2 |  | tickbox | Correct number of connections for dectors
boolean | 504e2d92-59ac-5f98-9230-7749b80a1369 |  | tickbox | All MCP at correct heights & positions
checkpoint-status |  |  | checkpoint | All required 1st fix testing complete
checkpoint-status |  |  | checkpoint | FPIS inspection sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Protection Provided for floor wastes and ends of unfinished pipes
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Mechanical Services Wall & Ceilings First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
text | 7e262d17-5992-5b19-a7d8-0f10c9cb28b6 |  | textbox | Reference drawings ( add drawing numbers & revisions)
boolean | 164e6ff1-7abb-5130-af9e-f19f9c162138 |  | tickbox | Ducts checked for damage/corrosion etc
boolean | 4a85783f-da33-55ae-b3b3-5d2e6cf94d9c |  | tickbox | Ducts size correct and type
boolean | 6cc856be-3dfc-5cbc-adaa-6a59b9f4060c |  | tickbox | Duct supports , anchors and hangers/Clips installed correctly including seismic
boolean | f09259b3-b556-5999-b308-07a2dfc89f44 |  | tickbox | Ducts And pipes insulated and labelled
boolean | 8cbfe978-977d-5e39-9bb3-9e28883b5112 |  | tickbox | Heights of pipeworks checked ( above ceiling)
boolean | 5079412b-c0ae-5b9b-b2ed-f30be040fc47 |  | tickbox | All required labelled/identification done
boolean | c24b237b-c7ab-5423-937f-38c1bb855d23 |  | tickbox | All required noggs have been added
boolean | cd38f1e4-8493-58eb-935f-8fca7fb00f8a |  | tickbox | all ducts cleaned/and ends capped where needed
boolean | b4e16596-06cd-571a-b4fb-179f2f9e9d6b |  | tickbox | Cables are completed and with proper support
boolean | 38c803aa-5959-5d31-9a39-9f8b1a612bd6 |  | tickbox | All equipment , valves and fire dampers, air outlets louvres,grilles and dampers are in place and accessible where required
boolean | 2179408e-7488-5cfd-a585-117daca92267 |  | tickbox | All required first fix testing complete
checkpoint-status |  |  | checkpoint | council Sign Off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Protection of all ends & Cleanup Done
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Electrical Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
text | b84f68b7-986b-55da-b961-f88f8986b121 |  | textbox | Add drawing numbers and revision
boolean | 87e71e57-26aa-5830-8daf-80595086c5c3 |  | tickbox | cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | b1fc5ea7-695c-51d0-a5c6-63fffed3d35a |  | tickbox | distribution boards in correct place
boolean | 077cb833-62f5-5010-971d-6cdc361b61f3 |  | tickbox | All outlets and switches at the correct position & height
boolean | c3f412cb-d804-5835-be22-0ea1e4ee2e98 |  | tickbox | Wiring for ceiling lights in correct position
boolean | 3fc50164-c44a-5bf5-8294-423c23648230 |  | tickbox | Correct number of ceiling lights installed
boolean | 67afb391-3870-558e-99fb-1a9f5c230b85 |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 5914157c-12c6-550a-b442-792ba77e1010 |  | tickbox | Power supplies for roller doors, HWC,Sliding doors,fire ,securty etc installed in correct place
boolean | 295d8efc-8d51-5174-b64d-aa6d5e009c89 |  | tickbox | All wiring labelled/identified
boolean | 258e421a-7db4-5d88-9fd4-054566a9d1da |  | tickbox | all earthing and cables installed
boolean | d2d32781-a5c3-5fda-b68e-3d7c955550ae |  | tickbox | Cables are installed and with proper support
boolean | 30b98aaf-8526-5442-b4f1-f1b18045de63 |  | tickbox | All required additional noggs placed in framing
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Protection /Cleanup Done
checkpoint-status |  |  | checkpoint | any onsite changes documented
checkpoint-group |  |  | section | Data/Security Wall First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 83a45084-5cf7-5c9f-961e-693d662b4b4e |  | tickbox | Setout/straightness checked
boolean | 49d81605-1739-5203-855e-15a4652f36d5 |  | tickbox | All required additional noggs placed in framing
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
boolean | ed42aace-1f67-5438-b848-c82db2721f20 |  | tickbox | cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | c3e213f2-200a-5035-82de-f1c049062100 |  | tickbox | distribution boards in correct place
boolean | 1047a9fc-dcc4-588c-a80a-6b70ec109796 |  | tickbox | All outlets and switches at the correct position & height
boolean | 66d1893a-afb8-5b54-aa5e-e460c1834854 |  | tickbox | Wiring for ceiling lights in correct position
boolean | a5547449-05e3-5b15-bfae-855f45da020e |  | tickbox | Correct number of ceiling lights installed
boolean | beefe724-6596-5e47-bbbd-bf6f167910b0 |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 227ab3eb-c201-5175-98d2-9f91b0cf359f |  | tickbox | Power supplies for roller doors, HWC,Sliding doors,fire ,securty etc installed in correct place
boolean | 895c9710-4fdb-51dc-a31a-ba5be828c7ef |  | tickbox | All wiring labelled/identified
boolean | 1dd47807-b74a-549e-9c3e-525bf27a755d |  | tickbox | all earthing and cables installed
boolean | df8f7d71-1a97-55fa-8560-d0eb9fe35c20 |  | tickbox | Cables are installed and with proper support
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Protection /Cleanup Done
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Passive Fire Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached
checkpoint-status |  |  | checkpoint | All Passive fire elements completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Map for Check photos
checkpoint-status |  |  | checkpoint | Passive Fire Area 1 - hawkins check photos
checkpoint-status |  |  | checkpoint | Passive Fire Area 2 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 3 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 5 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 6 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 7 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 8 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 9 - hawkins check
checkpoint-status |  |  | checkpoint | passive Fire Area 10 - hawkins check
checkpoint-status |  |  | checkpoint | Third party review complete
checkpoint-status |  |  | checkpoint | fire consultant review
checkpoint-status |  |  | checkpoint | council have inspected
checkpoint-group |  |  | section | Insulation Checklist Prior to Lining
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Insulation pre lining works completed, checked & approved
boolean | 0bf606f8-6419-5e2c-a89f-d73db5fd5197 |  | tickbox | correct product & R value as per specification
boolean | 968536a7-1d68-531e-8260-1270f673a239 |  | tickbox | Fitting correctly/Snug
checkpoint-group |  |  | section | Preline Inspection Checklist
checkpoint-status |  |  | checkpoint | All above preline elements checked, correct & approval to line
boolean | fb99d1bb-89ab-552d-a75c-8b3d4493b22c |  | tickbox | Council inspections carried out & attached in council folder
checklist-flat |  |  | checklist | P-Floors Leveling Checklist |  |  |  |  | Yes | P-Floors Leveling Checklist | 5e02e2b8-d9a1-451b-8e81-4cbfb0c3c3b6
checkpoint-status |  |  | checkpoint | Floor prep completed, checked and acceptable
checkpoint-status |  |  | checkpoint | Floor levels checked
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | surface coatings complete & remedials done
checkpoint-status |  |  | checkpoint | Fixtures/fittings Installed
checklist-flat |  |  | checklist | Services Second Fix |  |  |  |  | Yes | TH - Services Second Fix | 612778b9-41a3-4bc2-987e-dc8978d82355
checkpoint-status |  |  | checkpoint | All second fix works complete( pass when all below are complete)
checkpoint-status |  |  | checkpoint | Electrical trade QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Hydraulic QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Fire Protection QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Mechanical QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Wall damage check for linings complete
boolean | c56fce9c-9a05-5a23-9f66-9cc698aca26e |  | tickbox | Damage identified
boolean | e6d73248-3907-5713-b59f-7435aa1c0ccd |  | tickbox | Damage repaired by stopper
boolean | adad1857-11fe-5902-a507-55ce64f6df52 |  | tickbox | Damage repaired by painter
checklist-flat |  |  | checklist | Wall Preline Approval |  |  |  |  | Yes | 2 CONQA - Interior – preline inspection checklist V2 | 61ba5494-4215-4435-b3bf-160ec1ec2191
checkpoint-status |  |  | checkpoint | All above preline elements checked, correct & approval to line
boolean | f3bec0fb-41a3-5122-975d-fa2525d0e462 |  | tickbox | Council inspections carried out & attached in council folder
boolean | de346107-eda5-59eb-8664-ba3154952568 |  | tickbox | Relevant consultant inspections carried out & attached in consultants folder
checklist-flat |  |  | checklist | Daily Site Report - Streetscape/Civil Works: |  |  |  |  | Yes | Daily Site Report - Streetscape/Civil Works | 64baa71a-f05a-409e-978f-271be7b9fc7e
checkpoint-status |  |  | checkpoint | Hours Worked & Weather Conditions Recorded
text | 72b1f775-f7b0-4c2b-85e3-a1959350980b |  | textbox | My Hours Worked (start & finish)
select | 775f7ba3-279a-4d6b-a5bd-393b2933a730 |  | dropdown | Weather Conditions AM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
select | 12fd9b21-a4e3-4368-abe5-6ff908ff5b30 |  | dropdown | Weather Conditions PM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
checkpoint-status |  |  | checkpoint | Visitors to Site (Record name, company & purpose)
checkpoint-status |  |  | checkpoint | Site Instructions Issued (Any relevant site instructions issued are documented here)
checkpoint-status |  |  | checkpoint | Day Works Agreed (Any relevant Day Works issued are documented here)
checkpoint-status |  |  | checkpoint | Subcontractors on site (all recorded area, man power, name)
checklist-sectioned |  |  | checklist | Pour - |  |  |  |  | Yes | Concrete Pour Checklist - Shear & Core Walls - QA | 679f2405-12bf-42e6-9c58-ed8378d88337
checkpoint-group |  |  | section | Pre Pour
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | e36d2e06-5448-4cf6-8a6f-d7eca7b27e29 |  | textbox | Drawing reference:
text | 5758892b-affb-4878-80a1-86e12b7a8262 |  | textbox | Subcontractor:
checkpoint-status |  |  | checkpoint | Shutter Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Penetrations located and checks
checkpoint-status |  |  | checkpoint | Reinforcing Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Reinforcing install completed and reviewed
boolean | 4ee435b1-5831-434f-94a0-c9f57de10adb |  | tickbox | Reinforcing - Size and type correct to specification
boolean | c8cb8b4d-5b33-438a-8c8c-ab1f69a0ee6f |  | tickbox | Reinforcing - spacing and location correct
boolean | 0acc7ea3-cbec-4776-be6b-c6a059b7f16b |  | tickbox | Specified covers checked/correct
boolean | 6bd360d3-5d65-4e76-816c-eb099433cf24 |  | tickbox | Splice laps checked/correct
boolean | be686d18-e1a0-4d8a-9c1f-98b34538c732 |  | tickbox | Any starter bars are installed correctly (location, size and spacing )
boolean | 732ce241-7bd7-494a-bae4-6f0e45db56f5 |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Structural Steel cast in plates installed / checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Waterproofing installed
checkpoint-status |  |  | checkpoint | Bottom of foundation is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | All services completed
checkpoint-status |  |  | checkpoint | Engineer informed of pour, checks completed (see Holmes folder and ensure observations are closed out)
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
checkpoint-status |  |  | checkpoint | Trades Post Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour checks completed and any remedial work closed out
checklist-flat |  |  | checklist | Project Director Site Walk - |  |  |  |  | Yes | Project Director Site Walk Checklist - H&S | 688f366f-37c1-4c66-8606-6ec872f39477
checkpoint-status |  |  | checkpoint | All below items closed out
label | 170c1287-d969-45bd-ab00-1b1bdc196553 |  | note | Project Director or other to "pass" once satisfied all below items have been addressed
checkpoint-status |  |  | checkpoint | Observation 1
text | 6b68f4fb-c990-4279-a488-f97fe6ff5c55 |  | textbox | description
text | 9126832f-6c5e-483c-827e-9b5024b53423 |  | textbox | corrective action required
text | 7c63f840-977d-4a24-bcf9-57e78d447cea |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 2
text | 7eb9ac0b-1b9e-46d4-9827-0ebc8330e6f0 |  | textbox | description
text | 4bcd72e7-9ce6-4f26-ab5f-f02e349e69a4 |  | textbox | corrective action required
text | 183b4b07-f63b-4217-924b-5cbf1ac96648 |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 3
text | bcded733-07fb-4d83-bf7e-e8ce61a466c7 |  | textbox | description
text | 4c3e8ca6-7edc-44c1-be36-dc4acdff8ea9 |  | textbox | corrective action required
text | cd2f59d8-829a-4cb1-9ee5-9c9d69ba955d |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 4
text | f071e36e-5d24-46c2-9800-fc499fbb3783 |  | textbox | description
text | 7bba3133-e9c2-4e98-af01-81ffe0205b60 |  | textbox | corrective action required
text | 351448f3-d0a2-4eaa-89e7-53e1e1ea6caf |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 5
text | 746d9acf-aaf6-4f8c-9621-cff3570946c3 |  | textbox | description
text | 508e8f8a-6d99-414d-9a31-854aec751177 |  | textbox | corrective action required
text | dfb155ee-ade0-4940-8585-5f3211ea8101 |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 6
text | 8dbec071-0524-4ed3-93c0-1caf3b53563e |  | textbox | description
text | ef33a4e1-d951-4f14-8b1e-83d10b99f252 |  | textbox | corrective action required
text | 36ba5fb5-0b58-40a7-aa61-c852980aa77d |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 7
text | 8eadd094-8bf8-4c91-bd63-d3143e1351c8 |  | textbox | description
text | 3b5f4e12-eaab-4389-98ee-a4a1ceaec687 |  | textbox | corrective action required
text | 2882fd70-888c-4af3-8d9c-055b2dc30a70 |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 8
text | 4719dab9-99a3-4a8a-9da0-4cf346fa4691 |  | textbox | description
text | 2e95be2c-8a67-4131-8274-d4506a28ed37 |  | textbox | corrective action required
text | 755bb4e1-0431-4c62-bb72-4bfe665796e7 |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 9
text | c33b37dd-e835-41fb-9fa8-e48057905006 |  | textbox | description
text | 4f12beae-d568-42db-9aaf-49c4dd99d6c8 |  | textbox | corrective action required
text | 272e355d-8aa1-44a4-9444-ec34d034f433 |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 10
text | d031e9a8-1a74-4e23-a2c9-5c9419b8b605 |  | textbox | description
text | 3941ee06-edfa-4cbb-8d5e-3736133d95cc |  | textbox | corrective action required
text | b4567838-78d9-4ce2-9f23-2156385adb4d |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 11
text | fe17b2ab-5a3b-400f-accc-ccf07377b79f |  | textbox | description
text | 6b002ba8-6370-433f-9d0d-eb277de8948c |  | textbox | corrective action required
text | 3476a995-3b3a-489b-9754-61a526065b1a |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 12
text | 0386af52-f612-4eb8-88c3-fd8a29268f2e |  | textbox | description
text | 04238b51-a10b-41f8-b73f-8185f5394e85 |  | textbox | corrective action required
text | a17f83ff-3421-46c6-b345-1afa6f6a2e38 |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 13
text | 2d7cd6eb-9b1c-44e0-8c86-e6899c0f690c |  | textbox | description
text | 9d9ae727-aa50-4295-a437-5616e0b92e7f |  | textbox | corrective action required
text | 24e5920c-9572-4b82-a5df-31125873062e |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 14
text | f4b73371-8136-471f-b02f-0d795743b868 |  | textbox | description
text | 2aab77d3-21d1-4761-b68d-09ba02e488f3 |  | textbox | corrective action required
text | 5ea98240-be3a-4309-bfd3-e1ca412f912b |  | textbox | allocated to
checkpoint-status |  |  | checkpoint | Observation 15
text | ab5fa507-39f1-4708-a315-95f2c6a881f7 |  | textbox | description
text | 0762eab6-a800-4799-b888-b4b0d4cef335 |  | textbox | corrective action required
text | c1333932-273b-4da9-9770-39bf4e84c30c |  | textbox | allocated to
checklist-flat |  |  | checklist | Concrete Floor Level Check |  |  |  |  | Yes | Concrete Floor Level Checklist - QA | 6adf8aa5-40ec-4510-becd-39e6004179e6
checkpoint-status |  |  | checkpoint | Concrete floor level and surface review completed( pass only when the above are completed
boolean | fb272720-e6a8-5349-8764-4535778ca561 |  | tickbox | Concrete surface finish as per specification achieved
boolean | 5e106461-2e2f-5743-9951-dfbd95a298b8 |  | tickbox | Floor level tolerances as per specification achieved
checkpoint-status |  |  | checkpoint | Applied coatings if required completed
checklist-sectioned |  |  | checklist | Pour - |  |  |  |  | Yes | Concrete Pour Checklist - Generic Foundations - QA | 6bca5167-b1da-453c-a2f3-86850058f20d
checkpoint-group |  |  | section | Pre Pour
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | 7caa0b58-d236-4874-af76-babfaf3caa00 |  | textbox | Drawing reference:
text | f51db3fd-7568-4988-be89-b5ff59d05175 |  | textbox | Subcontractor:
checkpoint-status |  |  | checkpoint | Detailed Excavation complete & accurate (Pass before progressing)
checkpoint-status |  |  | checkpoint | underground services complete (Pass before progressing)
checkpoint-status |  |  | checkpoint | Backfilling Complete (Pass before progressing)
checkpoint-status |  |  | checkpoint | Formwork Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Waterproofing Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Penetrations located and checks
checkpoint-status |  |  | checkpoint | Reinforcing Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Reinforcing - Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing - spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Reinforcing Install completed and reviewed
checkpoint-status |  |  | checkpoint | Structural Steel hold down bolts checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Bottom of foundation is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | Any services completed
checkpoint-status |  |  | checkpoint | Engineer informed of pour, checks completed (see Holmes folder and ensure observations are closed out)
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
checkpoint-status |  |  | checkpoint | Trades Post Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour checks completed and any remedial work closed out
checklist-flat |  |  | checklist | TW - Balcony Permit to Unload |  |  |  |  | Yes | TW - Balcony Permit to Unload | 6bdf7ed9-e5cc-4ec3-884a-4422a954a53a
checkpoint-status |  |  | checkpoint | Has the designer specified a permit to unload is required
checkpoint-status |  |  | checkpoint | Have all necessary permanent works for which the temporary works are required for been completed
holdpoint |  |  | signoff | Holdpoint / Request Signoff
checkpoint-status |  |  | checkpoint | Have all necessary permanent works QA documents and hold points been achieved
holdpoint |  |  | signoff | Holdpoint / Request Signoff
checkpoint-status |  |  | checkpoint | Will removal of the temporary works load another structure
checkpoint-status |  |  | checkpoint | Is the structure compete and capable of taking the loads
checkpoint-status |  |  | checkpoint | If required, have any approvals from the Temporary works engineer been granted
checkpoint-status |  |  | checkpoint | If required, have any approval from the permanent works engineer been granted
checkpoint-status |  |  | checkpoint | TWS (Temporary Works Supervisors) given approval to remove
holdpoint |  |  | signoff | Holdpoint / Request Signoff
checkpoint-status |  |  | checkpoint | Have details of any dismantle sequence been communicated to the site foreman?
checklist-sectioned |  |  | checklist | P-Joinery & Kitchen |  |  |  |  | Yes | P-Joinery & Kitchen | 6c5b83bf-1015-4f5f-9f3b-80c05d6daa27
checkpoint-group |  |  | section | Kitchen Install QA
checkpoint-status |  |  | checkpoint | Kitchen cabinetry installation completed and correct
checkpoint-status |  |  | checkpoint | All appliances Installed and commissioned
checkpoint-status |  |  | checkpoint | Kitchen splash backs
boolean | 3080866c-e3df-5d93-b734-b4043b88d9da |  | tickbox | Site measure
boolean | 92cc4f6e-36c1-5ddf-83d8-ad549baf6965 |  | tickbox | Install
checklist-flat |  |  | checklist | Inspection - |  |  |  |  | Yes | Consultant Inspection Checklist | 6d6be2a2-4e88-4613-bbcb-9edc874f2e67
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out
text | fbb5e252-9571-55cc-b293-c8eedd627460 |  | textbox | Date of Inspection:
text | a03258e8-ff50-59a7-9f58-fc78bf912571 |  | textbox | Type of Inspection:
boolean | ff1f9ca2-1963-5225-89d1-a7383bf506cf |  | tickbox | Inspection attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-no-status |  |  | checkpoint | Obeservation 1 (True)
checkpoint-no-status |  |  | checkpoint | Obeservation 2 (True)
checkpoint-no-status |  |  | checkpoint | Obeservation 3 (True)
checkpoint-no-status |  |  | checkpoint | Obeservation 4 (True)
checkpoint-no-status |  |  | checkpoint | Obeservation 5 (True)
checkpoint-no-status |  |  | checkpoint | Obeservation 6 (True)
checkpoint-no-status |  |  | checkpoint | Obeservation 7 (True)
checkpoint-no-status |  |  | checkpoint | Obeservation 8 (True)
checkpoint-no-status |  |  | checkpoint | Obeservation 9 (True)
checkpoint-no-status |  |  | checkpoint | Obeservation 10 (True)
checklist-flat |  |  | checklist | QA Defects List - Intumescent Paint |  |  |  |  | Yes | QA Defects List - Intumescent Paint | 6f56cde0-d59b-4712-b1fb-7777e9205e6e
checkpoint-status |  |  | checkpoint | All below items closed out
text | 2e4462ca-000a-5184-b2f0-4dbf5c71eb03 |  | textbox | Hawkins Team member to "pass " once satisfied all below items have been addressed
text | 86edd473-21d3-51dc-93d9-71c3bd0674d4 |  | textbox | Close out Required By ( add date)
text | 0356fb7b-2211-5c1a-9a8d-fb3e479ac237 |  | textbox | Subcontractor Attached to (Responsible)
text | 57a33f73-56c3-5deb-9156-3c4690257824 |  | textbox | Plan Reference ( Level/Zone)
checkpoint-status |  |  | checkpoint | Observation 1
text | 5a5005c6-412f-58da-b3f1-2501f6473f57 |  | textbox | Zone /Floor Level & Location Description
text | 266f7923-877e-5849-a223-97f88e673e8f |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 2 ( attached photo)
text | 0de22cc8-0858-5336-9427-e6d6ef5f722e |  | textbox | Zone /Floor Level & Location Description
text | 6362618e-7dc8-5776-ad5d-baf0e5843c71 |  | textbox | Corrective Action Required ( Photo to be Attached)
text | 2c991f45-d4eb-564e-b1f1-c06366584a44 |  | textbox | Allocated to
checkpoint-status |  |  | checkpoint | Observation 3
text | df34a245-0938-5403-b4b5-c9947ad311b6 |  | textbox | Zone /Floor Level & Location Description
text | bd8c2a19-5b6a-50a2-ba7b-98bdddd38727 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 4
text | ba512586-0937-521b-87ff-67c283f8b3da |  | textbox | Zone /Floor Level & Location Description
text | 57865a82-7ea2-55b7-886a-d09031405738 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 5
text | 5bf086b4-edb3-5abc-96b5-afd805c9a565 |  | textbox | Zone /Floor Level & Location Description
text | 1fc3b420-48ed-5cdf-a9b5-7c43ca8da102 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 6
text | 533dd2c0-7632-5296-b777-0bf17b19752b |  | textbox | Zone /Floor Level & Location Description
text | 426c7db1-9679-53ac-97d8-2d316b6df04f |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 7
text | 5143e7d4-7c05-537e-897a-e2caeb72abf1 |  | textbox | Zone /Floor Level & Location Description
text | fb5064ba-d58b-5e25-aae5-5f6848ca3398 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 8
text | 9eb0ce4a-8f65-5b3b-878f-5d79ad3d5dbe |  | textbox | Zone /Floor Level & Description
text | 255040c2-ffdc-558d-aa8b-a6e52c6c2443 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 9
text | 6635dfe3-a25d-5761-b80f-42fa141dc4b3 |  | textbox | Zone /Floor Level & Location Description
text | 87c4ca6b-5a3f-58bd-a7b8-a2395322f252 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 10
text | 4c732a8f-a837-559e-a55b-277a2f5a52e4 |  | textbox | Zone /Floor Level & Location Description
text | 53d8665f-6585-5f26-9ec2-843e088b3890 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 11
text | 05c5adde-d7b4-5084-b127-b251bcc7b9e2 |  | textbox | Zone /Floor Level & Location Description
text | 058e9247-ab43-5574-941e-35782a620899 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 12
text | 90f55c94-9d20-571a-84f9-858b3baed0f2 |  | textbox | Zone /Floor Level & Location Description
text | 19944720-7a46-5c86-8f03-be1e7c08e189 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 13
text | fa776270-b736-5c4d-9379-0ce3d69fcef6 |  | textbox | Zone /Floor Level & Location Description
text | 10ef20b1-5bca-500e-a635-c5d58db86154 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 14
text | cac14e16-3574-564f-875b-5f6f6ac5c576 |  | textbox | Zone /Floor Level & Location Description
text | 0091b9d9-7a0e-5632-a83a-aa7225b81c96 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 15
text | 420aba51-767b-5a88-9760-1acdee406e55 |  | textbox | Zone /Floor Level & Description
text | 5390498f-7d63-5263-8d89-9e8028b14815 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 16
text | 239bae7b-10f9-5393-95e4-da86a78d8b20 |  | textbox | Zone /Floor Level & Description
text | 25fd72f0-947b-5ed9-9484-4b1398038808 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 17
text | df672c73-4788-5f2b-8552-c8d88df40181 |  | textbox | Zone /Floor Level & Description
text | 5d2fc4e2-b26b-5cc8-a067-76901ed2c89f |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 18
text | bcb39f9a-3707-58ca-a87c-5c85ce7561e6 |  | textbox | Zone /Floor Level & Description
text | 3f8b0da9-3d9c-5bc1-819f-839c88fe3804 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 19
text | c792c3a3-9ba7-51a4-90f0-b60f8e1a0a46 |  | textbox | Zone /Floor Level & Description
text | 4214cc18-1116-59a5-9ad6-cd738b0c4665 |  | textbox | Corrective Action Required ( Photo to be Attached)
checkpoint-status |  |  | checkpoint | Observation 20
text | e68d9cf6-6cd8-55f8-b204-9e94322c6f81 |  | textbox | Zone /Floor Level & Description
text | fbb8cf20-d2d3-5d2b-9cc0-148898b920c2 |  | textbox | Corrective Action Required ( Photo to be Attached)
checklist-flat |  |  | checklist | Precast - Manufacture |  |  |  |  | Yes | Precast - Manufacture - QA | 6f7d4381-f768-42bb-bb24-99f1dc438f47
checkpoint-status |  |  | checkpoint | Product Details
text | 88bae787-67b2-4eea-9de7-2c102e730c43 |  | textbox | Subcontractor:
text | 07affe7d-8904-4cb1-ba40-34dcff0d1ffb |  | textbox | Location of Plant:
text | cc1554fb-c8e0-4491-a3d9-bcf1f1ced190 |  | textbox | Panel Number:
text | f56c06b2-9f78-4e69-935e-aff913918a05 |  | textbox | Drawing No:
text | 69db4cab-e0de-4c77-a610-4fa65b752d36 |  | textbox | Confirm Mix Design:
text | b25e2c84-1d1c-4192-86d5-a56ba5271360 |  | textbox | Confirm Concrete Strength:
checkpoint-status |  |  | checkpoint | Prepour inspection done and attached
boolean | 19010354-cd07-4061-a8c1-746036d62df7 |  | tickbox | Dimensions
boolean | b331c572-7b9f-4645-a507-bb4c30bec866 |  | tickbox | Lifting Hooks Installed
boolean | 82e586fe-624c-4c8b-b2dd-145a6dadb834 |  | tickbox | Reinforcing as per Drawings
boolean | bb9cbeb1-0695-4d73-8b5c-dee75abb9c4d |  | tickbox | Rebates as per Drawing
boolean | 69c44500-3b1f-4c7f-bf37-be9133d582ff |  | tickbox | Penetrations Located Correctly
boolean | e4ae81dc-5f1d-4040-8369-a93e5310582e |  | tickbox | Formwork Clean
checkpoint-status |  |  | checkpoint | 4 Test cylinders taken
checkpoint-status |  |  | checkpoint | Trade post pour QA received, attached reviewed and approved
checkpoint-status |  |  | checkpoint | Engineer Sign off received
text | fd61d413-0697-4482-b782-4e9f948cd3ab |  | textbox | Curing time required:
text | 611cfab9-c4ee-41e3-b5ba-c393c32fe433 |  | textbox | Due on site
checklist-sectioned |  |  | checklist | Permit to Core Drill (Floor/Wall) |  |  |  |  | Yes | TW - Permit to Core Drill (Floor/Wall) Checklist (V3) | 70fb07e5-f7b2-4b02-b8f5-c1cb947c5e99
checkpoint-group |  |  | section | Permit to Core Drill
checkpoint-status |  |  | checkpoint | Location Information Recorded
label | 03690a8d-f961-4cea-a39e-a7a76d589a9c |  | note | Select "PASS" once all information/photos are recorded
text | 43de1e0c-6c2b-4d1f-828e-0e96c2624929 |  | textbox | Grid Reference
text | 6118d4de-b8ac-4229-9c66-8ae01964ea4c |  | textbox | Drawing Number/Revision
text | c4429d90-0efe-4753-8f83-9bb5ade70742 |  | textbox | Level/Zone
checkpoint-status |  |  | checkpoint | Hole Size
checkpoint-status |  |  | checkpoint | Setout & Reinforcing Checked and "Approval" is given to Drill
label | 4c79a15a-e304-4473-823e-412d1e356e69 |  | note | Select "PASS" when setout & reinforcing has been checked and approval given (if required)
boolean | 0bd43b07-f0da-4313-8d09-29a4490b0ac9 |  | tickbox | Setout Checked
boolean | df63f9b8-d6f9-447d-a39c-74c3f833f0df |  | tickbox | Reinforcing Checked
holdpoint |  |  | signoff | Request Consultants Approval (where required)
checkpoint-group |  |  | section | Core Drilling Prestart / Completion
checkpoint-status |  |  | checkpoint | Area Check Prestart
label | e44f1d18-1eb9-438b-80e0-fd59c2d5cd1e |  | note | Select "PASS" once all information/photos are recorded
text | 631e0d45-12ac-43a3-8348-3ce03b981d40 |  | textbox | Grid Reference
text | 8b81d61c-2e4f-4f9f-b5aa-8deb486ba2c2 |  | textbox | Level /Zone
boolean | 3784c6cc-2079-4d68-a04a-389ed25d0685 |  | tickbox | Area of Works Above & Below Appropriately Cordoned Off
boolean | e6035a98-7bc2-496a-9e84-e49854da853b |  | tickbox | Concrete Drilling Equipment Tag Current
boolean | cee41d1c-d04e-4707-85e9-c1a828a94966 |  | tickbox | Spotter In Place(Below) Prior To Drilling
checkpoint-status |  |  | checkpoint | Area Check on Completion
label | 151ffbd1-bcbf-46e6-98a2-078abc5c3e71 |  | note | Select "PASS" once all information/photos are recorded & area is left clean and slurry free
boolean | c52fc1f0-8fad-4942-83a8-6345faaa2a34 |  | tickbox | Clean-up Complete
boolean | 1cd8b43c-661a-41cb-93f4-196256a688ca |  | tickbox | Penetrations Covered/Sealed (after drilling )
boolean | d9d6a2b7-c12e-49ef-9b5c-7c888f3aedfc |  | tickbox | Hole Registered on Penetration Plan (attach photo of mark up below)
text | 3df9af00-b2a1-47e1-8a63-289393c9c742 |  | textbox | Hole Ref No:
checkpoint-status |  |  | checkpoint | Core Hole Complete
checklist-flat |  |  | checklist | Backfill - Services |  |  |  |  | Yes | Backfill Checklist - Services - QA | 72f2b621-2f68-44ac-bb76-d4e88498d9c8
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct - desired compaction achieved
checklist-sectioned |  |  | checklist | P -Services Second Fix |  |  |  |  | Yes | P -Services Second Fix | 73119616-0fbf-4fec-8e8a-08330ab8f779
checkpoint-group |  |  | section | Electrical 2nd Fix Wall
checkpoint-status |  |  | checkpoint | Electrical Final Fix QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Hawkins checks with Subcontractor
checkpoint-status |  |  | checkpoint | Testing as per deliverable schedule
checkpoint-status |  |  | checkpoint | Second Fix Electrical Completed/Zone sign off
checkpoint-status |  |  | checkpoint | Commissioning as per deliverable schedule
checkpoint-status |  |  | checkpoint | Commissioning completed & witnessed
checkpoint-status |  |  | checkpoint | Final Fix completed and protected where required
checkpoint-group |  |  | section | Plumbing 2nd Fix Wall
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Hawkins checks with Subcontractor
checkpoint-status |  |  | checkpoint | Testing as per deliverable schedule
checkpoint-status |  |  | checkpoint | Second Fix Plumbing Completed/Zone sign off
checkpoint-status |  |  | checkpoint | Commissioning as per deliverable schedule
checkpoint-status |  |  | checkpoint | Commissioning completed & witnessed
checkpoint-status |  |  | checkpoint | Final Fix Completed and protected where required
checkpoint-group |  |  | section | Mechanical 2nd Fix Walls
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Hawkins checks with Subcontractor
checkpoint-status |  |  | checkpoint | Testing as per deliverable schedule
checkpoint-status |  |  | checkpoint | Second Fix Mechanical Completed/Zone sign off
checkpoint-status |  |  | checkpoint | Commissioning as per deliverable schedule
checkpoint-status |  |  | checkpoint | Commissioning completed & witnessed
checkpoint-status |  |  | checkpoint | Final Fix Completed & protected where required
checkpoint-group |  |  | section | Fire Sprinklers & Alarms 2nd Fix Walls
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Hawkins Checks with Subcontractor
checkpoint-status |  |  | checkpoint | Testing as per deliverable schedule
checkpoint-status |  |  | checkpoint | Second Fix Sprinklers & Alarms completed/zone sign off
checkpoint-status |  |  | checkpoint | Commissioning as per deliverable schedule
checkpoint-status |  |  | checkpoint | Commissioning completed & witnessed
checkpoint-status |  |  | checkpoint | Second Fix completed and protected where required
checklist-flat |  |  | checklist | Civil QA Documentation |  |  |  |  | Yes | Civil QA Documentation | 7355c94b-963e-4196-ae3a-e9fb9f19fb0c
checkpoint-status |  |  | checkpoint | Civil QA Uploaded
text | 1bf39e7d-4b2a-5ca5-9030-b70a0c003825 |  | textbox | Add supporting documents/photos attached
select | f78e46ad-5fe1-5252-9224-75c015d83a85 |  | dropdown | Received Via: | Aconex, Email, Other
text | d6fe26f8-64d2-55ae-bb0f-e55508622c9a |  | textbox | Reference Number:
text | 427e2a55-8489-51bf-8af1-bdc7ff5661cb |  | textbox | Reference Date:
checkpoint-status |  |  | checkpoint | QA submitted to client
button | cd344a2a-5e93-5238-bd58-148d856b23ae |  | button | Submission Issued | Yes, No, N/A
text | f495a86b-2ec5-5fe2-811a-f5332b2f98f5 |  | textbox | Reference No:
checkpoint-status |  |  | checkpoint | Add any observations
checklist-flat |  |  | checklist | H&S - EWP Checklist V4 |  |  |  |  | Yes | EWP Checklist V4 - H&S | 79f852c9-3573-4410-a6e2-f0245f37a7cc
checkpoint-status |  |  | checkpoint | All below items closed out
text | 80e32a2f-82e9-5ee8-ac8a-cf52de29e2d7 |  | textbox | Hawkins Team member to "pass " once satisfied all below items have been addressed
checkpoint-status |  |  | checkpoint | EWP check # 1
text | dc559b48-69d8-5d36-a59d-477233d465c2 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 6ab32e2f-f06f-5453-b505-2ab3b71f794c |  | textbox | Machine ID # & Colour
text | e3ccf161-5d26-5098-afc6-2ede13fb2b4e |  | textbox | Hired From
text | 635a86c9-76ae-5c20-8993-258368977a61 |  | textbox | Hired to ( if known)
button | e83f8fe7-0929-54e4-b554-6819f963f4b6 |  | button | Logbook Current | Yes, No
text | 3d79755d-b295-5c2b-9b67-3bba02612363 |  | textbox | Date of last logbook signature
button | 91c8faa1-6778-565d-bf9d-aa307d058c3a |  | button | Machine cert current (six months ) | Yes, No
text | 1f6e3520-d166-593f-8c5c-6b4d9d69872a |  | textbox | Cert Expiry Date
button | 19603e18-a3a6-52b8-8af3-2ef0f71d9814 |  | button | If in use is it being used correctly | Yes, No, NA
button | 19c23fce-b30f-5341-a963-ed33d0d57751 |  | button | If outside is it rated correctly | Yes, No, NA
button | 9aa50363-7d6d-508b-b023-ebf71ee224a2 |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | 08eae78e-ccfb-5228-a6d1-29e94743c257 |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | 8c3da2d3-1958-54ef-ae98-c86eca225496 |  | button | If being used are the operators competent | Yes, No
text | d538815d-957a-5869-a44b-c6baf30c303d |  | textbox | Action/allocated to
button | 09ccc064-5a81-5d77-8413-164ae9299986 |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP check # 2
text | 03aa6754-2954-5260-a6b2-12ef6c33db9f |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 4e6a3091-6d6a-5f78-bf9c-3cd94f0a6179 |  | textbox | Machine ID # & Colour
text | 2d114711-061d-5f8a-82a5-411543ef4f8c |  | textbox | Hired From
text | ec1a5a63-0654-51b4-b430-707188805846 |  | textbox | Hired to ( if known)
button | 605ed9c8-332a-53f7-9d40-f862306bc644 |  | button | Logbook Current | Yes, No
text | 298b9253-e57e-57bd-bcdb-71b8db3f459f |  | textbox | Date of last logbook signature
button | 7ecd1a30-46bc-563b-90fd-0db887e59e65 |  | button | Machine cert current (six months ) | Yes, No
text | 7ccc0d23-f3c6-5ac7-9b52-6f411754f131 |  | textbox | Cert Expiry Date
button | f700262d-e05b-5a83-8c0e-9cbbbc2a7390 |  | button | If in use is it being used correctly | Yes, No, NA
button | 5fb6c974-9873-5938-b735-4cc27763e828 |  | button | If outside is it rated correctly | Yes, No, NA
button | 9a02f065-1e2f-5347-9707-00c8555185a2 |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | 117fd3cf-8c7b-525a-8341-401d31b53b0a |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | adefa031-ef20-5c7a-ab94-43fd882a29db |  | button | If being used are the operators competent | Yes, No
text | 8083ee41-13ff-558b-b0ae-1f5d0ba734b3 |  | textbox | Action/allocated to
button | 1b1c5f51-57ac-5316-b959-6adf08ab376e |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP check # 3
text | cc7bb326-e039-5c74-8158-8489f18249e2 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | c68f59ef-00c3-5786-9dcc-3ed0241df367 |  | textbox | Machine ID # & Colour
text | e15a6894-70d6-592c-9c6f-abefba3789fe |  | textbox | Hired From
text | 0f1d55f5-7b7d-5ad4-8c33-9da40b941781 |  | textbox | Hired to ( if known)
button | f93c5a38-a3d9-5ab4-9480-4147c47b1c1b |  | button | Logbook Current | Yes, No
text | 6d623633-c1fe-5a03-8ebe-ae371ae48d27 |  | textbox | Date of last logbook signature
button | 5207c6fe-67d1-518d-a5d5-04cf275bbb3c |  | button | Machine cert current (six months ) | Yes, No
text | 31094455-5d83-53d4-ad28-6c73ffbd7493 |  | textbox | Cert Expiry Date
button | 9986925a-e282-539f-b6b2-0d7b3f1b8f98 |  | button | If in use is it being used correctly | Yes, No, NA
button | fed6ad8e-9fbe-54bf-bcde-b85f0b4e46c3 |  | button | If outside is it rated correctly | Yes, No, NA
button | ffba3f91-dc8a-5414-b817-d996f123eda6 |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | fdd8dc6a-12ff-570c-930a-2506223f8ce8 |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | 6a1ab48a-461d-5c9b-87c3-1ae63cbde9df |  | button | If being used are the operators competent | Yes, No
text | fd200e1f-11da-5c29-a9ef-195137893cbc |  | textbox | Action/allocated to
button | f2e8e2f9-2fe6-5c60-b930-8fd45b736283 |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP Check # 4
text | 715c01bc-6f5b-5606-bbd9-76c0dc1bab35 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 2d271144-10cb-5e62-af6e-92406eb95f26 |  | textbox | Machine ID # & Colour
text | eeca142b-46a2-5055-bc3b-70c3d6c63b72 |  | textbox | Hired From
text | ae70392f-c5ea-5caf-bfcb-85576faaec42 |  | textbox | Hired to ( if known)
button | a8d5cdeb-ce92-5a57-b5d0-a87b254cd023 |  | button | Logbook Current | Yes, No
text | 4d626b5d-3b4f-5986-aa89-774b9157e8d5 |  | textbox | Date of last logbook signature
button | aa29a58a-d2f5-571b-9c3b-cd8c00b171a6 |  | button | Machine cert current (six months ) | Yes, No
text | 6f899c26-939e-5e5d-9e5e-52784e8e3dca |  | textbox | Cert Expiry Date
button | 42a48c1a-0d29-5f3c-963c-cdfa623d26d5 |  | button | If in use is it being used correctly | Yes, No, NA
button | 66365e5e-ed6b-557b-a8c2-089b3c5a6045 |  | button | If outside is it rated correctly | Yes, No, NA
button | 09ce6c06-a0c8-5804-a473-41def385c84e |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | 04d9158c-45f3-5c3a-b6d5-78d16f2a9b89 |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | 041d599b-e2c9-591e-b7d3-c255f09e6e66 |  | button | If being used are the operators competent | Yes, No
text | 6ed3405e-eeba-5f78-a0ff-e0725a1d4435 |  | textbox | Action/allocated to
button | 10c507ae-91e2-5e4f-b04f-b9e01563f6fa |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP check # 5
text | 93df4e28-467e-5d01-9f6c-fc4b10216a55 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | e324c302-46c9-5b9e-ba88-d38dd564d4f2 |  | textbox | Machine ID # & Colour
text | c04c9745-460d-5baa-b455-e9de59a50d83 |  | textbox | Hired From
text | 7def23a3-5c62-5673-bb83-7119bd275258 |  | textbox | Hired to ( if known)
button | abce0ed1-e094-5a19-9d93-b38bcf226e2c |  | button | Logbook Current | Yes, No
text | 852f3823-5d01-51fa-a84a-b7c576183cf9 |  | textbox | Date of last logbook signature
button | 1d034340-57c7-55e9-a377-b9454b627487 |  | button | Machine cert current (six months ) | Yes, No
text | d7702b4b-7bf9-56e5-8c42-e95c50849e53 |  | textbox | Cert Expiry Date
button | 39ab82cd-6b22-5aa7-af89-8cb7087d3ba4 |  | button | If in use is it being used correctly | Yes, No, NA
button | 6a873dbb-5ae7-56f5-b7c6-eebb65682ad4 |  | button | If outside is it rated correctly | Yes, No, NA
button | c3218450-de48-5f16-93aa-4aa63d8488d4 |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | 14b15171-7137-5aed-a06f-8861d07ed25b |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | 8890d9f3-ffa5-576e-b0c1-4c6efbf51b55 |  | button | If being used are the operators competent | Yes, No
text | 775eb5fe-8ea8-5afd-83c8-285f28318f7a |  | textbox | Action/allocated to
button | fa8ffb38-73c5-5e45-8d7d-d3c9513c6700 |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP check # 6
text | 8d221021-4f6f-5d05-8572-e65c283d1689 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | cb020fe5-2908-5b63-84b1-2384b93199ed |  | textbox | Machine ID # & Colour
text | 6e489175-47d7-5229-94ee-9408b613531f |  | textbox | Hired From
text | ef8f7cfa-7c32-5567-b919-3661dabd7802 |  | textbox | Hired to ( if known)
button | d85cd6f8-84ce-577c-aa31-301be894f40c |  | button | Logbook Current | Yes, No
text | cf645d33-15ac-5fda-aa7a-097074df5514 |  | textbox | Date of last logbook signature
button | 4db4e7b2-2a87-5b5f-a3d4-8f73cfe77bc8 |  | button | Machine cert current (six months ) | Yes, No
text | c3429f64-4893-5b18-9d47-aba12b5cd05f |  | textbox | Cert Expiry Date
button | 5accb01b-b758-55e4-aef8-2f49f8b40921 |  | button | If in use is it being used correctly | Yes, No, NA
button | d5b965f7-8686-564b-9c56-f6aa7bcddf48 |  | button | If outside is it rated correctly | Yes, No, NA
button | 38eafd0a-8fcc-5a5c-9dee-4056d6f71496 |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | fd3877d0-6875-505d-8dad-c71735d69d87 |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | 0d38c4cc-2226-5be0-8e48-a69c88a28cd3 |  | button | If being used are the operators competent | Yes, No
text | 177ea609-4d31-5766-96de-b8b9a260cb3c |  | textbox | Action/allocated to
button | afe90d3e-0c9e-53c7-97bf-b98a62df9237 |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP check # 7
text | dbc90be3-0fde-5733-adf8-e9cd7909f162 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 71147dd3-aefe-5169-b5f1-4631a1afd4c8 |  | textbox | Machine ID # & Colour
text | bb0b954f-ba50-59ec-a072-7b73574c709e |  | textbox | Hired From
text | dab34f5d-199b-53b8-87a9-541e2bb21eea |  | textbox | Hired to ( if known)
button | a0197d5f-9648-55ab-aa27-5466cb769b88 |  | button | Logbook Current | Yes, No
text | 274465ed-93a8-54e4-80db-143d22e3f206 |  | textbox | Date of last logbook signature
button | 2cd05910-afcc-555a-a72e-36c1d0206c63 |  | button | Machine cert current (six months ) | Yes, No
text | 37c3ce7e-0f41-5cf8-9800-8a7e98e9bfd6 |  | textbox | Cert Expiry Date
button | 7194b96b-535a-55ff-96a0-e476f36c3b9b |  | button | If in use is it being used correctly | Yes, No, NA
button | a1af61f7-7565-5ef7-962d-b1b49e490031 |  | button | If outside is it rated correctly | Yes, No, NA
button | 92a52fc3-f946-56f3-a5ea-aefff4566785 |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | 52de926c-cb44-5206-b13a-f5d31be64aed |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | bde94979-3b99-5709-8944-491b623c938e |  | button | If being used are the operators competent | Yes, No
text | 94ac54ba-cc3b-5d73-8e9a-23e328ce3dfd |  | textbox | Action/allocated to
button | 7dc46f6f-9872-5118-b1a6-187d96fa3cab |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP Check # 8
text | dbfcf2e5-8e4d-535c-aa9d-33c469d1ca80 |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 57a72d61-b8a3-5424-94e7-6dbe96f660d9 |  | textbox | Machine ID # & Colour
text | 46750a1c-4f16-5031-9863-cd25f4543d37 |  | textbox | Hired From
text | 380dfe12-4047-510d-9b2d-12ba6675c920 |  | textbox | Hired to ( if known)
button | 380844bb-2669-543d-a7db-d280d2d77f00 |  | button | Logbook Current | Yes, No
text | 2ddecde7-b005-5330-a186-8502af56baed |  | textbox | Date of last logbook signature
button | 48954d12-4ea5-5f70-8105-f4c0b4b8940f |  | button | Machine cert current (six months ) | Yes, No
text | 5d8d4c36-28a7-53a4-add3-3cfde65fcaba |  | textbox | Cert Expiry Date
button | f6e57a30-1931-5ffe-90a0-10aed379fd41 |  | button | If in use is it being used correctly | Yes, No, NA
button | 892180ed-5601-5789-9fb3-5f38b9b6797b |  | button | If outside is it rated correctly | Yes, No, NA
button | 379aca78-be58-55ae-b720-09e97ce724b6 |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | e9b2ee17-2426-56b8-88de-977ea8efd5eb |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | 5808fc02-1a48-5d42-a88b-9646392001b1 |  | button | If being used are the operators competent | Yes, No
text | baeac709-1bb7-5e60-afee-9096a832b91c |  | textbox | Action/allocated to
button | b79451fa-981a-522a-a77e-8491ded6fce9 |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP check # 9
text | 49361b86-5b2c-50f3-b151-0c59be54dbde |  | textbox | Location Zone /Floor Level /Inside or Outside
text | b8cdedcb-bcde-5b1f-8348-fc6759689ff8 |  | textbox | Machine ID # & Colour
text | 71fdfb5b-cf09-50ab-b04a-dea1493e9767 |  | textbox | Hired From
text | 9196165f-388f-5c2d-ba09-2905a4b716a6 |  | textbox | Hired to ( if known)
button | b2884967-6c5e-56fb-a437-4af8e2a8a956 |  | button | Logbook Current | Yes, No
text | 3e184f67-2e13-53fa-8897-10dd898f285b |  | textbox | Date of last logbook signature
button | 41f5af17-525a-5472-ac62-e770af87c35f |  | button | Machine cert current (six months ) | Yes, No
text | f88ecff7-00e7-5043-8c81-825c74d50568 |  | textbox | Cert Expiry Date
button | 90de6517-aeff-519b-801f-90e1e43c557d |  | button | If in use is it being used correctly | Yes, No, NA
button | 870afe29-ea66-5cf3-8da6-fbcd24692e33 |  | button | If outside is it rated correctly | Yes, No, NA
button | 61d04742-0cbe-5419-9ac7-cb24c792be6a |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | 0e55a8a3-4c79-5872-9952-c8cf2968fda0 |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | d3b14912-8eed-5d85-8a67-7b0f27dc181f |  | button | If being used are the operators competent | Yes, No
text | f50fe13c-51a2-5e34-ab23-bc95c6df90fe |  | textbox | Action/allocated to
button | 1a257950-b870-57c9-be02-1c4d072a6c75 |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP Check # 10
text | 5270581f-b6ce-557e-ae66-76c6f4adfa7b |  | textbox | Location Zone /Floor Level /Inside or Outside
text | 2532e99f-6174-5699-885c-52c1a21f3ee6 |  | textbox | Machine ID # & Colour
text | 12238e97-acf6-5e8a-8a0f-58d7813dee10 |  | textbox | Hired From
text | c9a7339c-9371-5b08-9f44-b849a8df0245 |  | textbox | Hired to ( if known)
button | 2cc7cbb7-8e6d-545c-9cc9-8a243d71a78b |  | button | Logbook Current | Yes, No
text | 657b5fdf-e859-5b49-a996-7c6fcd432aaf |  | textbox | Date of last logbook signature
button | c1ec3b1f-5d74-5a11-a516-8681b9b47187 |  | button | Machine cert current (six months ) | Yes, No
text | 8fa8aa66-284a-5e98-a7cf-e46192a376a7 |  | textbox | Cert Expiry Date
button | acd29453-2c11-5ab0-8e7b-aa207a22b561 |  | button | If in use is it being used correctly | Yes, No, NA
button | 2d0bb84f-7bf7-59cb-a3b0-300f9c93d96b |  | button | If outside is it rated correctly | Yes, No, NA
button | 38833ae9-d05a-5cf0-9b1d-a811616b20eb |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | 3af7959b-5d2d-5671-9865-95014a9145cd |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | 4525f362-f150-5f54-9747-1142b794191f |  | button | If being used are the operators competent | Yes, No
text | 60044949-8a7e-50c4-b2f9-417d77fd1ca7 |  | textbox | Action/allocated to
button | 37e428fe-9d64-5f12-a016-3bb9e560e2f1 |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP Check # 11
text | 209be7e9-0f7b-5982-a698-e460e0aff3af |  | textbox | Location Zone /Floor Level /Inside or Outside
text | ba62dfbe-4641-56a3-8649-ab1c1f908954 |  | textbox | Machine ID # & Colour
text | 60595685-f4da-5089-a59a-980688a88d3c |  | textbox | Hired From
text | 87680b93-795e-50bc-847a-faf49746fe2d |  | textbox | Hired to ( if known)
button | 4e212932-5b12-56b5-8825-b19929352b0b |  | button | Logbook Current | Yes, No
text | 62e2d637-5889-587a-9543-66349070f6a8 |  | textbox | Date of last logbook signature
button | f356aa69-b4c6-53cc-b196-90b32d8e8a98 |  | button | Machine cert current (six months ) | Yes, No
text | 0bee1fff-84a4-5204-adf2-f033dc5769ce |  | textbox | Cert Expiry Date
button | b0a5aebb-af62-5909-bcb0-741a5c798cbb |  | button | If in use is it being used correctly | Yes, No, NA
button | 08836a75-699d-5dd7-8fa8-d83d203a8446 |  | button | If outside is it rated correctly | Yes, No, NA
button | d028ef3e-8798-536e-af06-2b56ec26dd48 |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | 375b14aa-e5e8-5ec7-9a39-86f3ccc01702 |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | 855b3d77-c8a3-550f-8f37-1feca304258e |  | button | If being used are the operators competent | Yes, No
text | f8938dd9-ea2b-5007-b98f-489a09b327b4 |  | textbox | Action/allocated to
button | 63858a60-cef9-5420-b995-11244c4f7877 |  | button | Action completed | Yes, No, NA
checkpoint-status |  |  | checkpoint | EWP Check # 12
text | 88d567dd-d702-50de-8207-d77900b49ccf |  | textbox | Location Zone /Floor Level /Inside or Outside
text | f62672bb-9022-5b20-8da6-a8ff209add10 |  | textbox | Machine ID # & Colour
text | 92d0c88f-9dc1-56b7-b2fb-501c47ff105f |  | textbox | Hired From
text | d0b08104-a994-57fd-a151-c23b8359d378 |  | textbox | Hired to ( if known)
button | be3bbbfb-d6e9-5582-8f5f-79a4b563e76d |  | button | Logbook Current | Yes, No
text | 7464ea0b-a744-5d5d-954e-435224f98732 |  | textbox | Date of last logbook signature
button | 9db7f733-ed3c-5054-a8eb-0845ae885e65 |  | button | Machine cert current (six months ) | Yes, No
text | 6dd4c1c3-c254-5dac-a86e-1ca8ced51008 |  | textbox | Cert Expiry Date
button | ef23284e-ef52-5f3a-9840-56f4de296ebf |  | button | If in use is it being used correctly | Yes, No, NA
button | f1f8f261-2d43-5511-b5a5-a998b2653436 |  | button | If outside is it rated correctly | Yes, No, NA
button | 7dbf802c-5524-5f58-be16-f5770db8b610 |  | button | Is Correct PPE being used/harness/lanyard | Yes, No, NA
button | 58c8af3d-cc24-562f-83be-486e0d0c5056 |  | button | Is harness/lanyard current & in good condition | Yes, No, NA
button | 9fbaadfa-c15d-56ea-8e12-5520c60fb8d2 |  | button | If being used are the operators competent | Yes, No
text | e783b6d0-ef97-5afc-9fec-2bdc8b53ff42 |  | textbox | Action/allocated to
button | 309979d3-7133-54db-bb77-aef11a2049a4 |  | button | Action completed | Yes, No, NA
checklist-flat |  |  | checklist | Temporary Work - |  |  |  |  | Yes | TW – Request to Inspect | 7d1d7f3d-b3ee-40ea-a2ed-ad7a3e8d3837
checkpoint-status |  |  | checkpoint | Temporary Work - Details inputted below
text | 096c08ef-6850-4d23-bb69-b4240ff496e8 |  | textbox | Location
text | b28a9008-5aa1-455a-a1cd-949a4df72400 |  | textbox | Reference drawings ( and revision No) eg (HEB)
text | 0cea9a32-4270-4195-92d3-d18de13da19e |  | textbox | Description of Inspection
checkpoint-status |  |  | checkpoint | General Photos
checkpoint-status |  |  | checkpoint | Scaffold as per Design
text | bd0c9e35-f614-420b-9d59-a9a164f92b97 |  | textbox | TWS (Temporary Works Supervisor) Inspection comments
checkpoint-status |  |  | checkpoint | Props have been loaded/wound up read for final inspection
checkpoint-status |  |  | checkpoint | Additional Comments/photos
checkpoint-status |  |  | checkpoint | OK to proceed
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Scaffolding Inspections |  |  |  |  | Yes | Scaffolding Inspections (V2) - QA | 7f62ca05-2990-4b9e-9928-faa938ce8ea6
checkpoint-no-status |  |  | checkpoint | Scaffolding Inspection Details
text | 3e5afb9b-f5fb-4165-8b11-281e4c5b0709 |  | textbox | Date & Time
text | aa8c2fd6-be1e-459a-b855-9feaa7bda05e |  | textbox | Inspected by
text | 35b4aea6-cbbd-49cb-96b1-872f2eaee7f5 |  | textbox | Area Inspected
checkpoint-status |  |  | checkpoint | Items Inspected ( pass when all checked)
button | 076691c3-4c15-47b8-b1d5-0a2163d06a73 |  | button | Scaffold tag current | Pass, Fail, N/A
button | 59a8d8ee-dcc1-41ee-bb88-a1ad92302006 |  | button | Ties in place and secured | Pass, Fail, N/A
button | 5f68e34b-446d-4208-8542-9b90413cf2aa |  | button | Toe boards in place and secured | Pass, Fail, N/A
button | 328a16d4-2521-4573-a5b4-f0a530e93348 |  | button | Mid rails in place where required and secured | Pass, Fail, N/A
button | dc973d73-37eb-4e14-9372-260dff3d9bde |  | button | Planks secure | Pass, Fail, N/A
button | e91385fe-09c7-4eb3-b2c7-3a9ead8d32cf |  | button | Drop protection in between the building & scaffold where required | Pass, Fail, N/A
button | 658b4d52-df24-4c52-b434-4bb32050088f |  | button | Shrink wrap/netting intact & in good condition | Pass, Fail, N/A
button | cd7d65a8-edb3-4b2d-a0e2-82f79d462a55 |  | button | Foudations no undetermined | Pass, Fail, N/A
button | 958c97d2-1e34-4d59-aacf-e6cb6c6c3dc6 |  | button | Housekeepiing (scaffolding clean and clear) | Pass, Fail, N/A
checklist-flat |  |  | checklist | Flooring |  |  |  |  | Yes | Floors Carpark & Service areas (V1) - QA | 7fa4acba-ba7c-45aa-92f8-e586b614f6a5
checkpoint-status |  |  | checkpoint | Floor prep completed, checked and acceptable
checkpoint-status |  |  | checkpoint | Floor levels checked
checkpoint-status |  |  | checkpoint | surface coatings complete
checkpoint-status |  |  | checkpoint | Hardware installed
boolean | f404f691-796a-4830-8d68-eba1e9dd4944 |  | tickbox | bollards
boolean | 2a105f63-21f3-4b38-a6cd-3651c2c26968 |  | tickbox | Wheel stops
boolean | 1b10193d-724d-4bf8-88bd-15adc4610737 |  | tickbox | Line marking
checklist-flat |  |  | checklist | Underground Services (Civil) - |  |  |  |  | Yes | Underground Services Install Checklist - Civil - QA | 7fc06e6d-7e62-4c8e-9f8d-19759babd46a
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | 3485eb62-9346-4c5a-a1c2-214bfdaa7b4e |  | textbox | Subcontractor:
text | 7439a5cf-1f19-45f2-9147-b9de9fc03e12 |  | textbox | Drawing Reference:
checkpoint-status |  |  | checkpoint | Material complies with spec
checkpoint-status |  |  | checkpoint | Civil works completed
boolean | 66919c12-4f86-4e48-b486-9d285e02228c |  | tickbox | Pipes cut clean and square
boolean | ab9b0d60-dac1-42dc-b54a-bc0ebec2d37f |  | tickbox | Pipework protected where required
boolean | 15707d00-5763-43ae-b2d1-ca4bc34d91d9 |  | tickbox | Drainage material under pipe
boolean | a23dd97d-fb20-4f54-9b04-451441678f88 |  | tickbox | Levels and inverst correct
boolean | c1541f53-0fa3-4e92-8d28-a6ecd09c7ac4 |  | tickbox | Pipework to correct falls
checkpoint-status |  |  | checkpoint | Testing to council requirements pass (pass once inspection is completed and approved)
boolean | 5bea5168-1d74-4fda-b617-d1bc1e8e8829 |  | tickbox | Councils inspection booked
boolean | 84a874c5-36d2-4e04-bbca-fb3da2b609b2 |  | tickbox | Council inspection compete (attached in Council Inspection folder)
checkpoint-status |  |  | checkpoint | Consultant inspection completed & any observations closed out (Inspection attached in Consultants folder)
checklist-sectioned |  |  | checklist | Fitout / Finishing Checklist |  |  |  |  | Yes | TH - Fitout / Finishing Checklist | 81ae224b-c027-419d-b17a-19b3e3286638
checkpoint-group |  |  | section | Fitout / Finishing
checkpoint-status |  |  | checkpoint | Floor prep completed, checked and acceptable (approval to lay flooring)
checkpoint-status |  |  | checkpoint | Timber Flooring completed & correct
checkpoint-status |  |  | checkpoint | Carpet flooring completed & correct
checkpoint-status |  |  | checkpoint | Wardrobes Install Completed, checked and approved
boolean | 4bea0f37-4854-5674-b275-5986c0e2bf84 |  | tickbox | Onsite measure
boolean | 217834ad-510d-5cb5-b0e5-bb1fb9aba5a5 |  | tickbox | Installation
checkpoint-status |  |  | checkpoint | Second fix door hardware installed and approved
checkpoint-group |  |  | section | Wall Linings Check
checkpoint-status |  |  | checkpoint | Wall Lining Check - complete
boolean | f6f8b4f4-b76a-5e66-a785-0f7d2aaa1f1c |  | tickbox | Damage identified
boolean | aadd4138-ff91-5e91-9899-330e3fe97fda |  | tickbox | Damage repaired by stopper
boolean | 9bddcaf8-9625-5a33-95a8-adae674d5bfe |  | tickbox | Damage repaired by painter
checkpoint-status |  |  | checkpoint | Final Clean Completed & Area ready for handover
checkpoint-status |  |  | checkpoint | All above QA items completed
checklist-sectioned |  |  | checklist | P-Fitout / Finishing Checklist |  |  |  |  | Yes | P-Fitout / Finishing Checklist | 835248d1-1949-45a6-97f8-a07b8cc32b78
checkpoint-group |  |  | section | Wall & Ceiling Linings Check
checkpoint-status |  |  | checkpoint | Damage check for linings complete
boolean | f1754f46-7e9d-5933-a9ec-4b38bdb8b153 |  | tickbox | Damage identified
boolean | 9f5f04e3-c977-5e2b-a0fd-b6fd3a441a86 |  | tickbox | Damage repaired by stopper
boolean | 899cb964-c17c-58b8-a3c8-ec14577471eb |  | tickbox | Damage repaired by painter
checklist-sectioned |  |  | checklist | Services Second Fix |  |  |  |  | Yes | T1&2 Fitout (New) - Services Second Fix | 84124f05-e826-4eb3-b485-b87b75221468
checkpoint-group |  |  | section | Electrical Final Fix Wall (including Data & Security)
checkpoint-status |  |  | checkpoint | Electrical Final Fix QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Hawkins checks with Subcontractor
checkpoint-status |  |  | checkpoint | Testing as per deliverable schedule
checkpoint-status |  |  | checkpoint | Second Fix Electrical Completed/Zone sign off
checkpoint-status |  |  | checkpoint | Commissioning as per deliverable schedule
checkpoint-status |  |  | checkpoint | Commissioning completed & witnessed
checkpoint-status |  |  | checkpoint | Final Fix completed and protected where required
checkpoint-group |  |  | section | Plumbing Final Fix Wall
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Hawkins checks with Subcontractor
checkpoint-status |  |  | checkpoint | Testing as per deliverable schedule
checkpoint-status |  |  | checkpoint | Second Fix Plumbing Completed/Zone sign off
checkpoint-status |  |  | checkpoint | Commissioning as per deliverable schedule
checkpoint-status |  |  | checkpoint | Commissioning completed & witnessed
checkpoint-status |  |  | checkpoint | Final Fix Completed and protected where required
checkpoint-group |  |  | section | Mechanical Final Fix Walls
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Hawkins checks with Subcontractor
checkpoint-status |  |  | checkpoint | Testing as per deliverable schedule
checkpoint-status |  |  | checkpoint | Second Fix Mechanical Completed/Zone sign off
checkpoint-status |  |  | checkpoint | Commissioning as per deliverable schedule
checkpoint-status |  |  | checkpoint | Commissioning completed & witnessed
checkpoint-status |  |  | checkpoint | Final Fix Completed & protected where required
checkpoint-group |  |  | section | Fire Sprinklers & Alarms Final Fix Walls
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Hawkins Checks with Subcontractor
checkpoint-status |  |  | checkpoint | Testing as per deliverable schedule
checkpoint-status |  |  | checkpoint | Second Fix Sprinklers & Alarms completed/zone sign off
checkpoint-status |  |  | checkpoint | Commissioning as per deliverable schedule
checkpoint-status |  |  | checkpoint | Commissioning completed & witnessed
checkpoint-status |  |  | checkpoint | Second Fix completed and protected where required
checkpoint-group |  |  | section | Wall & Ceiling Linings Check
checkpoint-status |  |  | checkpoint | Damage check for linings complete
boolean | fec3ddc5-0259-530f-8579-93056731b947 |  | tickbox | Damage identified
boolean | 84d21518-7ae0-504f-ba4f-8d3390353700 |  | tickbox | Damage repaired by stopper
boolean | 718758df-f07f-5992-a975-ad16baa0d0d2 |  | tickbox | Damage repaired by painter
checklist-sectioned |  |  | checklist | Doors / Finishing Lines & Trims |  |  |  |  | Yes | T1&2 Fitout (New) - Doors / Finishing Lines & Trims | 8c1545bf-270c-4313-b44e-4499ac43a8a5
checkpoint-group |  |  | section | Finishing Lines Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Finishing lines spot checks complete
boolean | c2796f18-f77f-5380-83ef-b8b666d959e1 |  | tickbox | Correct product and size
boolean | 206b12a6-ebbd-5863-a735-b04390b8b65b |  | tickbox | Correct fixings and jointing
checkpoint-group |  |  | section | Door Install Checklist
checkpoint-status |  |  | checkpoint | All pre start requirements completed and acceptable, approval given to commence
checkpoint-status |  |  | checkpoint | Door fitted correctly as per specification (product, size, location, level, swing, fixings etc.)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Door install completed, checked, correct and approved
checkpoint-status |  |  | checkpoint | Door Hardware installed
checklist-sectioned |  |  | checklist | Crane Briefing Plan (V8) |  |  |  |  | Yes | Crane Briefing Plan (V8) | 8f895410-bbcc-4385-a7ba-94c682314d0a
checkpoint-group |  |  | section | Attendance
checkpoint-status |  |  | checkpoint | Attendance Information (pass once all inputted)
text | baf2782e-3ed0-5028-be24-2439461718e1 |  | textbox | Hawkins Crane Manager
text | 8ea8bedc-0a26-51ca-824c-91e6a7dff622 |  | textbox | Crane Co-ordinator
text | 57d5f745-2de7-51aa-8c9f-a49ba1054179 |  | textbox | Cranage Lead
text | 377db168-599e-5307-bebb-f5d8704bcccc |  | textbox | Crane #1 Staff
text | 818e11e4-cabf-526f-a41a-5d7a89c414bb |  | textbox | Crane #2 Staff
text | e54ec291-20a3-57ca-be80-c6a654b42302 |  | textbox | Crane #3 Staff
text | 8c812ee8-b94c-554c-9823-bb17661a13c4 |  | textbox | Crane #4 Staff
checkpoint-group |  |  | section | Critical Risks/Daily lifting schedule
checkpoint-status |  |  | checkpoint | Daily Lifting Schedule :Mobile 1
boolean | 562a5c0f-d38a-5b8a-b3e6-58b90d8391e0 |  | tickbox | Structural steel
boolean | f3f9d71a-93c9-500a-8537-e2493f95f356 |  | tickbox | Scaffold moving
boolean | 8af9cfc8-debf-5e25-8c7c-693ff03fe9b7 |  | tickbox | Steel stud
boolean | 63bd3a30-305c-55c7-89e9-3aac2732d452 |  | tickbox | Gib board
boolean | d25ce27b-5238-5353-90fb-2d5cf20cab23 |  | tickbox | Joinery Items
boolean | d79ed7fa-5f39-580b-9fee-54ab93b52f85 |  | tickbox | Waste bins
boolean | ab98db5e-3add-515d-861c-2a398e1bf166 |  | tickbox | Mancage
boolean | e352acc0-364f-5506-bb0e-a23c04c75844 |  | tickbox | SWL checked
text | 0701a9af-0ea6-5269-a53d-ee9e85fbe78d |  | textbox | If other, specify:
checkpoint-status |  |  | checkpoint | Daily Lifting Schedule : Mobile 2
boolean | 855a8f9d-0e4b-5fe0-add8-7cdf1429ac0f |  | tickbox | Structural steel
boolean | 13f85449-63ff-5f11-b50c-c1e3259db0cd |  | tickbox | Scaffold moving
boolean | c7743a95-c1b9-5115-b4fb-97d1700d75bc |  | tickbox | Steel stud
boolean | 1af0c679-fb95-5442-b55a-d5e3340a5478 |  | tickbox | Gib board
boolean | 0e699f63-f2ea-55fb-9c41-d27719a81fbc |  | tickbox | Joinery Items
boolean | b833aeb2-db74-5c5a-ad44-d173ffb9d079 |  | tickbox | Waste bins
boolean | c0654677-34ac-5f3e-9c2c-aa01aafdc4f3 |  | tickbox | Mancage
boolean | 72212467-659a-5f52-8e3e-54080624730a |  | tickbox | SWL checked
text | 971d6d3c-15a0-5405-bd7c-950ba8044fed |  | textbox | If other, specify:
checkpoint-status |  |  | checkpoint | Photos/Additional Comments
checkpoint-status |  |  | checkpoint | Radius chart or lift plan attached (Pass once attached)
checkpoint-group |  |  | section | Health & Safety controls for lifting
checkpoint-status |  |  | checkpoint | Crane operators /Dogman ticketed
checkpoint-status |  |  | checkpoint | Towercrane /Equipment have current certificate
checkpoint-status |  |  | checkpoint | New Hazards/risk/control
text | 9e14966c-724a-5bab-8cbc-29839fe55aa9 |  | textbox | Hazard One:
text | 6bb437fa-37ab-5e71-926c-43365b25eec7 |  | textbox | Hazard Two:
checkpoint-group |  |  | section | Weather Conditions
checkpoint-status |  |  | checkpoint | Conditions (Pass once recorded)
boolean | 77bb2029-ca77-5309-8cf7-efa23ab70f7a |  | tickbox | Rain forecast
boolean | 85af22ea-e05e-5348-9342-c93aefeda3cd |  | tickbox | Wind plus 35 km/h
text | bfbcacd4-8d11-528c-a783-51b3090cd0bf |  | textbox | If other, specify:
checkpoint-group |  |  | section | Lifting Gear/Hazard check For today
checkpoint-status |  |  | checkpoint | Lifting Gear/Hazard Check complete
boolean | 762c9c4a-be97-5f52-9111-cb1d2674b287 |  | tickbox | Taglines ok
boolean | 5b2d18ba-2ba2-57d0-b3af-ac96395f4b97 |  | tickbox | Lifting gear ok
boolean | 060b2ff2-e695-5d13-8c6b-c5b6dd07dea2 |  | tickbox | Crane operation ok
boolean | 28bb01e3-7a34-5c78-ae51-5415675eaae0 |  | tickbox | Anti-clash working ok
boolean | 9a0b1670-41a5-5ad7-b99a-cd0fe42cf674 |  | tickbox | Hook camera woking ok
boolean | 6513387c-993d-51f4-aac6-0972ea1ac19f |  | tickbox | Rigging methodology discussed
boolean | a5e1dcdc-52fc-5018-9fe7-b8e840cbdd50 |  | tickbox | Operator quick check complete
boolean | 5b1b048d-014e-5621-9e05-9faa1ceac2b3 |  | tickbox | Radio working ok
checkpoint-status |  |  | checkpoint | Photos/Additional Comments
checkpoint-group |  |  | section | Complex Lifts Today
checkpoint-status |  |  | checkpoint | Complex Lifts Today (Pass once relevant complex lifts are selected and any planning by engineer are done-to be attached)
boolean | ae56bedf-d67d-524a-872e-7d4636aa6a94 |  | tickbox | Irregular loads or loads with unusual weight distribution (centre of gravity)
boolean | 6c7d71a4-7ce3-5937-8c92-965e09c4411a |  | tickbox | Using one or more cranes(winches)
boolean | 0552093e-4596-5195-aa86-cef5e515aec0 |  | tickbox | A lift with less than the recommended multicrane safety factors
boolean | 13ac6837-e06d-5ca4-b7f9-6ca69e940d6c |  | tickbox | A lift out of view of the crane operator
boolean | 9d721019-9b09-57bb-9989-a85e4c61bbeb |  | tickbox | Technically difficult rigging
boolean | 1ad87d4b-b85b-56b9-aaf2-5dc818cd318f |  | tickbox | Lifting personnel
boolean | 40bbfdfc-09ad-5bfa-8de7-a5ad0dccb22b |  | tickbox | Lifting hazardous materials
boolean | 09bef386-31b0-5b9d-8b25-e81be42ad3b8 |  | tickbox | Lifting submerged loads
boolean | b2c77063-d85b-54b9-af0e-acd478ff5752 |  | tickbox | Lift with no or partial outrigger
boolean | 9070e212-9dfe-5fbe-a585-1d5e30831354 |  | tickbox | lifting on rubber
boolean | 94e253ab-b754-5ae3-936f-8438e0ff3b0a |  | tickbox | Lift weights if required
boolean | 93a048c2-9d49-5ec2-a4c9-d2fce11ca06c |  | tickbox | Or any lift the crane operator feels should be classed as such
checkpoint-group |  |  | section | Crane Operations Audit
checkpoint-status |  |  | checkpoint | Crane Operations Audit
checkpoint-status |  |  | checkpoint | Is a crane operations audit required today? If not required, select N/A above
text | a0c72676-f9a3-55e3-a072-d3d9da48f45e |  | textbox | Date and time of audit:
text | 88fc6436-1bec-5b9c-9bd0-343c65010968 |  | textbox | Audit completed by:
boolean | 6e20b90d-a913-59a7-b4a4-d8cd09149727 |  | tickbox | Anti-clash tests completed
boolean | 5c6e49ae-9ca6-5bc0-8bef-b3c68ce333bb |  | tickbox | Quik checks completed
boolean | 52927af1-4e8b-500d-a48e-254def275996 |  | tickbox | Training and certification current
boolean | 4863d570-2608-5c33-9a66-5264be7a09c9 |  | tickbox | Weather conditions monitored
boolean | a0c79e71-631b-5317-983b-7745becd3256 |  | tickbox | Daily lifting schedules
boolean | 2db15a49-670d-5fdb-9f90-203fc9916189 |  | tickbox | Lifting gear and equipment current
boolean | 46a36f02-03e6-50a0-b932-e433d590647b |  | tickbox | Anti-clash agreement current
checklist-sectioned |  |  | checklist | Walls & Ceiling Preline Checklist |  |  |  |  | Yes | T1&2 Fitout (New) - Walls & Ceiling Preline Checklist | 9295f763-34b1-4efc-a5ce-675f3eb64024
checkpoint-group |  |  | section | Interior Framing Checklist (including IT)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area ( sign off when all Complete)
boolean | 1ef069ae-e4c5-5ce8-ae3f-89e206b4d598 |  | tickbox | Spot checks on frames for square
boolean | 5f778ca1-d982-572d-aa1c-5a8f5dedef99 |  | tickbox | Spot checks on frame level
boolean | def121f5-e828-588d-8cdb-20016471087d |  | tickbox | Fixings are correct including seismic requirements
checkpoint-group |  |  | section | Plumbing First Fix Walls & Ceilings
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Plumbing install First fix complete - checks done based on current drawings ( attach and pass once all complete)
text | 18ebecd9-136f-511e-a4c7-244d1f878502 |  | textbox | Confirm drawing and revision number
boolean | 854701a2-4770-5b82-a7d4-3b329a92fe48 |  | tickbox | Pipes size & type
boolean | 4e503a16-431f-5b4b-9f77-252e7956f45b |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | 9a525540-62f9-5f58-8d7c-61e980c23f50 |  | tickbox | Correct number of outlets
boolean | 9af3adf7-35d7-588d-b6ef-a83248a1e2c5 |  | tickbox | Any valves/vents installed
boolean | 7489fd0c-6e72-57a3-bc78-e92a1c7f7e01 |  | tickbox | Pipework protected at holes and notches
boolean | 6f89ba0b-2193-5569-ac63-b140e90eca0e |  | tickbox | Heights & positions of pipeworks checked ( above ceiling)
boolean | ec7b2383-3391-59b5-a7eb-b41c44689e33 |  | tickbox | All vents installed
boolean | c025ffb3-47eb-5d4d-b988-8ffca634582e |  | tickbox | All lagging is inplace
boolean | b5208875-f6c8-54cb-9417-16e0cd9234a4 |  | tickbox | All labelling installed for pipework
boolean | 9f5f4954-4009-5f75-9286-e3ec8f972330 |  | tickbox | All noggs added in where needed
boolean | fef6209c-811b-5da3-8064-29ad9b4c32d3 |  | tickbox | All pipes cleaned/cleared before testing
checkpoint-status |  |  | checkpoint | Protection Provided for floor wastes
checkpoint-group |  |  | section | Fire Protection Walls & Ceilings (sprinklers & Alarms)First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
boolean | 66cad6a4-b8dd-5b17-8fc1-13f49c42e407 |  | tickbox | Pipes checked for damage/corrosion/Scale
boolean | ca4f48d6-75cd-5a88-9172-d94fad2dfd23 |  | tickbox | Pipes size correct and type
boolean | c0cd2589-9e4d-5813-93a3-4d0ba345c38d |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | 5106f6e5-7a08-505e-b58f-522f16b0e67c |  | tickbox | Correct number of outlets/droppers for sprinklers
boolean | 7c8bbe1b-eae9-5b08-b8a0-7b90574b6805 |  | tickbox | Heights of pipeworks checked ( above ceiling)
boolean | 39b3496a-76c6-5959-8f83-cc98593a842d |  | tickbox | Any lagging required is in place
boolean | e7c4f134-0dbb-5b76-823a-28bc9c282f70 |  | tickbox | All labelling installed for pipework
boolean | b5c6b17e-62ee-57e1-b000-bdb71397645a |  | tickbox | Cables are completed and with proper support
boolean | edd59635-637c-5ec3-9114-841ec874d24a |  | tickbox | All wiring labelled/identified
boolean | 5a087fa5-7245-508e-b456-49ca93b6251b |  | tickbox | All pipes cleaned/cleared before testing
boolean | b02cd06a-925e-52e5-b1a0-66a22643c9de |  | tickbox | Correct number of connections for dectors
boolean | 83a30ed0-0440-561b-b604-5a809bbe7231 |  | tickbox | All MCP at correct heights & positions
checkpoint-group |  |  | section | Mechanical Services Wall & Ceilings First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
text | 4b40ece1-d339-518a-b33a-8c9f9caaa353 |  | textbox | Reference drawings ( add drawing numbers & revisions)
boolean | 4909817d-84c4-5cfe-b1d0-ef5323e10b56 |  | tickbox | Ducts checked for damage/corrosion etc
boolean | a51f184f-06aa-5a9f-a163-604265dd4691 |  | tickbox | Ducts size correct and type
boolean | f379687e-96fd-59d3-b1ef-297babc50bd4 |  | tickbox | Duct supports , anchors and hangers/Clips installed correctly including seismic
boolean | b38201a9-73fd-55c4-9815-f741eb37dd9b |  | tickbox | Ducts And pipes insulated and labelled
boolean | 7bb248f2-0970-5012-b0ce-14ef0f2a221d |  | tickbox | Heights of pipeworks checked ( above ceiling)
boolean | 761597a9-58f6-5ee8-88b5-275cecdca355 |  | tickbox | All required labelled/identification done
boolean | 2fb4c6b5-18a2-5980-af53-4fbef62dee89 |  | tickbox | All ducts cleaned/and ends capped where needed
boolean | c56618e9-f50e-51ab-bac4-9e5ce40fc5c7 |  | tickbox | Cables are completed and with proper support
boolean | 4aa6d270-64df-5cd5-bd21-bab773e33cd0 |  | tickbox | All equipment , valves and fire dampers, air outlets louvres,grilles and dampers are in place and accessible where required
boolean | 7e74c98b-e3ba-5906-8e17-a3816c203c0c |  | tickbox | All required first fix testing complete
checkpoint-group |  |  | section | Electrical Wall First Fix (including Data & Security)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
text | a49b4d6e-72ef-52aa-a0ff-7c3f9948bc22 |  | textbox | Add drawing numbers and revision
boolean | 36d7efb6-36ef-56ac-877f-a79eb060c07f |  | tickbox | Cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | fad374b4-5887-53ba-aa06-4440055d0c46 |  | tickbox | Distribution boards in correct place
boolean | e4c98853-93c9-557a-bcd6-3edbb35d989c |  | tickbox | All outlets and switches at the correct position & height
boolean | d331f993-fef0-5bd6-b5b1-f340dd339639 |  | tickbox | Wiring for ceiling lights in correct postion
boolean | 5c4ef6d9-32b7-5715-b5b2-ee63ba52dc40 |  | tickbox | Correct number of ceiling lights installed
boolean | ac7bb8c3-03f9-5f51-b4fc-5a7ec467be15 |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | d6ecc72d-a93c-5349-ba83-9e9862581820 |  | tickbox | Power supplies for roller doors, HWC,Sliding doors,fire ,security etc installed in correct place
boolean | c28b8bc3-a5b1-5066-8951-7818f65ece3f |  | tickbox | All wiring labelled/identified
boolean | 2f0db063-a6bc-5427-83c0-48b9d4d85218 |  | tickbox | All earthing and cables installed
boolean | 516598a8-1505-51b2-a7db-36c8bc1260be |  | tickbox | Cables are installed and with proper support
boolean | 91d4464f-486f-5bd3-950f-a8f501e81589 |  | tickbox | All required additional noggs placed in framing
checkpoint-group |  |  | section | Passive Fire Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached
checkpoint-status |  |  | checkpoint | All Passive fire elements completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Third party review complete
checkpoint-group |  |  | section | Insulation Checklist Prior to Lining
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Insulation pre lining works completed, checked & approved
boolean | b83b97e3-9d06-5f9c-a489-056b8a67ce35 |  | tickbox | Correct product & R value as per specification
boolean | a496ae48-7747-568a-8d73-c9e3a681e121 |  | tickbox | Fitting correctly/Snug
checkpoint-group |  |  | section | Preline Inspection Checklist
checkpoint-status |  |  | checkpoint | All above preline elements checked, correct & approval to line
checkpoint-status |  |  | checkpoint | Council inspection complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-status |  |  | checkpoint | FPIS inspection sign off
checkpoint-status |  |  | checkpoint | Aon inspection sign off
checkpoint-group |  |  | section | Ceiling Batten Installation
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Works completed, checked & approved
checklist-flat |  |  | checklist | Precast: Delivery Inspection |  |  |  |  | Yes | Precast - Delivery Inspection - QA | 944e762c-7a59-41d2-b9ff-cd39dfd5d592
checkpoint-status |  |  | checkpoint | Product Information
text | 6d5b8dc5-e8f0-487b-8509-866831bc0e52 |  | textbox | Material Description:
text | 0e704ca8-72ae-4f41-b543-2d5ca3f74afd |  | textbox | Manufacturer:
text | ba67efeb-a44c-4d54-8364-8575fbebbbe4 |  | textbox | Unit No:
text | 3dd131a9-b7e5-490b-84d0-39f7afa02822 |  | textbox | Date & Time received:
checkpoint-status |  |  | checkpoint | Documents received with delivery:
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Pre lifting checks completed and approval to unload
boolean | 2fe300aa-d68a-4618-a7f1-13f18d664b5f |  | tickbox | Appropriate manufacture QA received
boolean | 2122becb-2211-4ebd-b50f-065aea08114e |  | tickbox | Visual check
boolean | c622cf5b-32dd-491f-86ad-ca6312de6e87 |  | tickbox | Lifting gear tagged
text | 5608e4da-f8ff-4149-809f-ff618c24e90a |  | textbox | Damage noted (Unit No & Type):
checklist-sectioned |  |  | checklist | Cavity System |  |  |  |  | Yes | Facade - Cavity System (V1) | 96e546ec-ec49-4a74-a38e-20c3ff6b80e7
checkpoint-group |  |  | section | RAB
checkpoint-status |  |  | checkpoint | RAB board installed & complete
boolean | 82f146ce-8e62-519e-bdc8-2a5a3934519d |  | tickbox | Correct fixings type & patterns/Spacing
boolean | 70ffade1-63ec-5fb9-b150-93f97d0d5dc6 |  | tickbox | Flashings installed checked and correct
boolean | b071f044-02f5-53e3-8350-d49d4574db12 |  | tickbox | All joints/penetrations/openings taped as per specs
boolean | 5d5502e2-3186-5c59-bf9b-7dd41d6a2c80 |  | tickbox | Services checked, type and location
checkpoint-status |  |  | checkpoint | RAB Board critical lines checklist completed
text | 3e563633-4d77-5c28-804f-565df93b47d9 |  | textbox | Critical line number/location & elevation
checkpoint-status |  |  | checkpoint | Inter-Story Junction
boolean | 7adfca2e-0efa-57e1-9989-50a286fa4734 |  | tickbox | Inter-story 20mm Horizontal join
boolean | c75a3260-4654-5718-a6d5-29edd5caed6a |  | tickbox | Inter-story flashing tapes
boolean | 08c9a6d3-a392-5f5a-ac54-c3bf97a6edd1 |  | tickbox | Vertical 12mm joins between bulkheads
boolean | c1d30c62-edfd-5c42-afa9-7bb786455abb |  | tickbox | Tapes over 12mm vertical join
boolean | 8528818c-5691-530e-8663-f0c936ceb248 |  | tickbox | Under balconies flashing tape bulge
boolean | b271bc7e-fc3f-5721-bd28-4838686e94dd |  | tickbox | Under balconies metal flashing over flashing tape
checkpoint-status |  |  | checkpoint | RAB QA received, reviewed, attached and approved
holdpoint |  |  | signoff | RAB Request inspection by Façade Engineer/ Architect/Council
checkpoint-status |  |  | checkpoint | RAB inspections
boolean | 95c851c7-26ec-5e5b-ac71-db6c02392c3e |  | tickbox | RAB Façade engineers remedials done and signed off
boolean | af44f01f-2403-509d-8c91-ef75e87b9ee6 |  | tickbox | RAB Architects remedials done and signed off
boolean | b496e006-ded0-5b89-a004-e17326f0a019 |  | tickbox | RAB Council inspections carried out any remedials done
checkpoint-group |  |  | section | Building Wrap & Flashing Tape Installed
checkpoint-status |  |  | checkpoint | RAB board installed and signed off
checkpoint-status |  |  | checkpoint | Building wrap and flashing tape installed
boolean | 41f7b96f-0711-5669-ae7d-f9a6ae3270a7 |  | tickbox | Correct fixing types & Pattern/Spacing
boolean | 0837be3a-e546-5aad-9ded-fbfe8d0a5743 |  | tickbox | Flashings installed checked and correct
boolean | 248e75a7-55cd-5ccf-8253-333e6c97852f |  | tickbox | All joints/penetrations/openings taped as per specs
boolean | 5c4ee1df-5ba0-5057-baac-bd1d5bb11046 |  | tickbox | Services checked, type and location
checkpoint-status |  |  | checkpoint | Powder coated Saddle flashings in and taped
checkpoint-status |  |  | checkpoint | Building Wrap QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Inspection by façade engineer /Council and Architect
checkpoint-status |  |  | checkpoint | Building Wrap Inspections
boolean | 1529b671-f131-549a-b23a-b8f891329d51 |  | tickbox | Building Warp -Architect remedials completed and signed off
boolean | c6ac2abe-8317-5753-8238-830a1828eb84 |  | tickbox | Building Wrap - Façade engineers remedials done and signed off
boolean | f5f197e5-7023-55f2-8956-ecf257b0e611 |  | tickbox | Building Wrap - Council inspection carried out and any remedials complete
checkpoint-group |  |  | section | Cavity Batten
checkpoint-status |  |  | checkpoint | Building wrap and flashing tape installed and signed off
checkpoint-status |  |  | checkpoint | Cavity installation completed, checked and approval to clad
boolean | 46ec9ddb-40f9-596a-bad2-cc76599a79ae |  | tickbox | Appropriate fixings for cavity (as per design)
boolean | 90616a3a-8e5a-5b57-a318-b13041777890 |  | tickbox | service penetrations complete
checkpoint-status |  |  | checkpoint | Critical lines checklist completed
text | a5988eb4-ee8c-5a5f-8ec7-29f83ef1e30d |  | textbox | Critical line number/location & elevation
checkpoint-status |  |  | checkpoint | Cavity Batten QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Cavity Batten - Request inspection
checkpoint-status |  |  | checkpoint | Cavity Batten - Inspection
boolean | 39bf051d-dff0-51fa-8fba-e602d01de9d7 |  | tickbox | Cavity Batten - Façade remedials complete and signed off
boolean | 444c8b97-a6c9-5e19-8e35-27b447ac4ad0 |  | tickbox | Cavity Batten - Architects remedials done and signed off
boolean | 885d504d-c5ed-5a57-9515-0f016f35e043 |  | tickbox | Cavity Batten - council remedials complete and signed off
checkpoint-group |  |  | section | Cavity Flashings
checkpoint-status |  |  | checkpoint | Cavity battens installed and signed off
boolean | dd72a12b-a515-5c1a-acf9-1de0036cedff |  | tickbox | Correct material ordered
boolean | 17f23b6d-4283-52d3-a46c-442ef7e7183e |  | tickbox | Arrived onsite and protected
checkpoint-status |  |  | checkpoint | Flashings Critical Lines
text | 36372a37-aca3-5b53-a19f-4a8437819532 |  | textbox | Number, Location, Elevation
checkpoint-status |  |  | checkpoint | Critical lines checklist completed
text | 2bb5b281-de4a-5904-9884-06cfcc82acef |  | textbox | Critical line number/location & elevation
checkpoint-status |  |  | checkpoint | Cavity flashings QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Cavity flashings Ssot check with Subcontractor -Installed/fixed in correct place
holdpoint |  |  | signoff | Cavity flashings request signoff -Architect /Façade engineer
checkpoint-status |  |  | checkpoint | Cavity Flashings Architect /Façade Engineer Sign oof
boolean | 1f073e42-89df-5735-bf65-fbb27fb6136a |  | tickbox | Façade engineers remedials done and signed off
boolean | d668d90c-79e8-5f84-b426-c48de641c2bb |  | tickbox | Architect remedials completed and signed off
checkpoint-group |  |  | section | Firetherm Rainbar
checkpoint-status |  |  | checkpoint | Firetherm Rainbar
checkpoint-status |  |  | checkpoint | Consultant Signoff
checkpoint-status |  |  | checkpoint | Fire Engineer Signoff
checklist-flat |  |  | checklist | Safety & Environmental Checklist - |  |  |  |  | Yes | Safety & Environmental Checklist - Full - H&S | 96ef9a52-f203-46ab-866f-617bb028c482
checkpoint-status |  |  | checkpoint | Safety & Environmental Inspection Details
text | 17e3d953-715d-42bc-9545-436b4458e459 |  | textbox | Safety and Environmental Supervisor:
text | 59aaf737-5c47-4fb5-9ef1-1a1c7f63ba38 |  | textbox | Inspection by:
checkpoint-status |  |  | checkpoint | Site Control
boolean | ec89709a-4bad-4ab8-bafa-4dd2f355907c |  | tickbox | Hazard ID up to date
boolean | 4bf95dda-61ad-49d9-bd14-be2c3a9187d6 |  | tickbox | Environmental Plan current – List any issues
boolean | 984d4d89-31a2-4be5-9fac-cbed75362508 |  | tickbox | Date of last safety and Environmental toolbox meeting
boolean | 28f6b95f-5966-492f-9b0c-1a7134bc8d98 |  | tickbox | Safety and Environmental Inductions being completed
boolean | 42c43287-7383-444b-9d7b-ee82132fd77b |  | tickbox | Safety and Environment Notice Board current
checkpoint-status |  |  | checkpoint | Traffic Management
boolean | 41a655d7-8c43-4cd0-98c2-53b343dbe4c8 |  | tickbox | Temporary Traffic Management Plan (TMP) in place
boolean | dfd26187-8661-466f-9fb9-7cf1f46d455f |  | tickbox | TMP approved by the road controlling authority
boolean | f9df1282-e6b1-4184-a45c-8ae36492e701 |  | tickbox | Traffic management measures set up in accordance with the TMP
boolean | b89db185-5830-4183-9a38-5d3178b64f6a |  | tickbox | TMP supervised by a qualified STMS
boolean | 82f6bb56-3742-403c-a508-0a698a15222c |  | tickbox | Traffic controller on site
checkpoint-status |  |  | checkpoint | Sediment and Erosion Control
boolean | c51f3b39-b493-4bbc-b9bc-386f2af9524e |  | tickbox | Silt control Plan in place
boolean | 4617deb8-ccbc-4fa7-a2e4-d04cc1569f89 |  | tickbox | Bare areas being stabilized
boolean | b8edaafa-16b5-46b0-a14d-721c45732034 |  | tickbox | Sediment control measures (e.g. sediment ponds, silt fences installed and maintained
boolean | 48a12c26-fdde-4e1a-ae4a-bab5919406b9 |  | tickbox | Dirty water from dewatering or pumping operations being controlled and treated prior to discharge
boolean | 17c0577e-d7a3-47f1-b708-a476f6ac2fd1 |  | tickbox | Spoil being managed and disposed correctly
boolean | 159a0a25-aeec-4e13-9252-d27713659a26 |  | tickbox | Onsite stockpiles being controlled/ Managed
boolean | fe1433c6-0824-4b1d-a3a1-228fc7e8d2bb |  | tickbox | Stabilised construction entrances in place and maintained
boolean | f2ff788e-2dc7-40c3-9e9a-ca85cbc6eabc |  | tickbox | Carriageways clean or being swept on a regular basis
boolean | 6998dc17-4d80-4cf4-81a7-7fdc372830fb |  | tickbox | On site wheel wash facilities installed and used as required
boolean | 3d18c148-be2c-43f3-b770-d2ad83a5b35d |  | tickbox | Dust controlled
boolean | 2204f351-201e-4bc3-9f74-3798a3379ab0 |  | tickbox | Construction noise being monitored
checkpoint-status |  |  | checkpoint | Hygiene
boolean | cbe688ef-b060-4d6e-8a93-303fdcaa8a53 |  | tickbox | Clean offices
boolean | 378e727d-de29-4844-b4d5-0b182df6f51e |  | tickbox | Clean smoko sheds
boolean | 5ffcefaf-3efc-4446-aefa-da8af424bfd2 |  | tickbox | Clean toilets
checkpoint-status |  |  | checkpoint | General Site Tidiness
boolean | 9036d970-4973-4f07-a90a-ddc03fe13412 |  | tickbox | Clear, safe access to work areas
boolean | be79bec6-f334-4556-b1e4-749a61d4a69b |  | tickbox | Stairways clear
boolean | df0a8ae7-fb82-46ee-a095-1871191aa1e2 |  | tickbox | Hoardings/perimeter fence and gates secure
checkpoint-status |  |  | checkpoint | Personal Safety Equipment
boolean | 541c2188-fc89-4a25-9eaa-6cf188314a87 |  | tickbox | Signage displayed and legible
boolean | f7120d8b-0272-4470-ad3b-674fb51d432a |  | tickbox | Hardhats being worn
boolean | ad6bf6d0-b45d-4f82-9275-db010da0b716 |  | tickbox | Correct footwear being worn
boolean | 8bbbd3d2-2c38-45ee-b0bf-d08c6bab7d50 |  | tickbox | PPE being used (glasses/ear muffs/ vests/masks)
checkpoint-status |  |  | checkpoint | First Aid/Fire Prevention
boolean | a2d42e6c-8c5d-498d-a2f7-f77e7b996257 |  | tickbox | First aid box checked (Available, clean & sufficient supplies)
boolean | d17b611d-911c-479d-b53e-031232e34c54 |  | tickbox | Accident Register Checked & Photographed (Available & Check Usage)
boolean | 565b7131-783e-45ac-8e98-f3f71c39d25e |  | tickbox | Fire Extinguishers (Available, Up to date & Sufficient number
boolean | aa01ab60-48af-4cf8-9f95-f7b211e75f62 |  | tickbox | Evacuation procedure in place, and current
checkpoint-status |  |  | checkpoint | Sun Exposure
boolean | a3b113b5-4257-4f86-9fa0-c7464f85173e |  | tickbox | Shade cover or screens available
boolean | 4658508a-05af-45a7-8d78-4e831582e191 |  | tickbox | Employees wearing clothing to prevent sun exposure
boolean | 70d6531d-0b84-41f5-a43d-5c566024c0b4 |  | tickbox | Broad spectrum sun screen available on site (SPF 30 or more)
boolean | a5806baf-a94a-4e0e-825d-2e6b66199c35 |  | tickbox | Are workers applying sun screen
checkpoint-status |  |  | checkpoint | Cranes/Hoist/Lifting equipment
boolean | 8d866bf0-b701-4296-b193-f43d5e2a7fe3 |  | tickbox | Certification up to date
boolean | fe9a5bb5-ac80-45d6-a721-3e2a4af1c761 |  | tickbox | Slings/chains certified
boolean | c9f87701-4c2e-4c04-b7db-878c4cb0072e |  | tickbox | Operator procedures in place
boolean | 14361908-cfd5-46b8-82fd-0d9d4e042372 |  | tickbox | Inspections being done
boolean | 8dd7de4c-be05-402b-8225-32161f4f0cc7 |  | tickbox | Log books being completed for MEWP’s
boolean | 980010a2-7aa4-4f3b-adba-1e1cf0482f92 |  | tickbox | Man cage available
boolean | f56838d4-ad3e-4a99-b9ce-90f8dacf3866 |  | tickbox | Emergency plan in place
checkpoint-status |  |  | checkpoint | Compressed Air Equipment
boolean | 9ab6cdb5-6fb1-40e5-8001-06e115ff6cff |  | tickbox | In good condition
boolean | 47261f3a-df63-41cc-b538-666ef7cb1a91 |  | tickbox | Appropriate guards fitted
boolean | 28c741e6-a37d-4585-a031-7a5580881713 |  | tickbox | Trained user
checkpoint-status |  |  | checkpoint | Excavation
boolean | 0cd2d98e-2a31-4be9-abea-509db25fdcec |  | tickbox | Correctly shored
checkpoint-status |  |  | checkpoint | Welding/Gas Cutting
boolean | f1ab6081-8abe-4a16-ab70-4ff327d1cf04 |  | tickbox | Hot works permits being issued
boolean | 7cdf0c46-b5da-4573-9186-75d5aca2aabb |  | tickbox | Fire extinguishers on hand
boolean | dadc3db2-501f-4fc0-adb0-494de0b125c7 |  | tickbox | Operators using PPE
checkpoint-status |  |  | checkpoint | Electrical Equipment
boolean | 667ba79c-8c5f-4b04-bf03-4b33c643f421 |  | tickbox | Leads safely placed
boolean | 0f159f19-82a0-416b-a010-fb09497014fe |  | tickbox | Leads tagged and current
boolean | acc50205-9e49-41b1-b051-48f45002a8b2 |  | tickbox | Tools tagged and current
boolean | 3b9f8430-2f68-4773-9ed4-4ff897a56a3f |  | tickbox | Lifeguards certified and current
boolean | 09b5ead5-1da8-45a4-a96c-a3eb34206240 |  | tickbox | Equipment in good condition
boolean | 03cc0608-5cc6-4c9a-abe1-b4c9d609c134 |  | tickbox | Appropriate guards on equipment
boolean | 7bc81a9c-aec9-4fa8-b311-0c11959a0b12 |  | tickbox | Temporary/Festoon lighting tagged
boolean | d9675217-6db3-4af5-b79b-4cbd26f50fdc |  | tickbox | Register up to date
checkpoint-status |  |  | checkpoint | Chemicals
boolean | 3e0b321d-77c3-4b3b-9534-f17dd3d12b10 |  | tickbox | Correctly stored
boolean | d473da5c-9148-422f-bf06-6b754667ccbd |  | tickbox | SDS available
boolean | 5f8980a9-c0f1-42af-b6e8-550568d7d86e |  | tickbox | Operators using PPE
boolean | c6ba43f9-c0ad-4c63-8648-f2622ed600e7 |  | tickbox | Spill kit available
checkpoint-status |  |  | checkpoint | Tools
boolean | 22ac8d44-e0c0-41ce-bc68-75e41fce6edd |  | tickbox | Ramset WOF current
boolean | 94289c75-9cc0-41dd-bd99-a24da2be0953 |  | tickbox | Tools being used correctly
boolean | bdac829c-fb8e-4319-9221-77fc9010e9ef |  | tickbox | Staff trained in tool use
boolean | dbec7be3-5b2f-4df2-8d0f-ec304590cee5 |  | tickbox | Tools in good condition
checkpoint-status |  |  | checkpoint | Harnesses
boolean | c1e444e3-e7ed-4bce-a682-718d28eb574d |  | tickbox | Being worn
boolean | d2d28c19-cec5-4533-83e9-9fc6d44a21c6 |  | tickbox | In good condition
boolean | 96b7c48f-d918-41ce-add6-5c4c174dc15b |  | tickbox | Fixing/anchor points adequate
boolean | a3827708-3410-471d-82bc-5eb68ed23638 |  | tickbox | Personnel trained on correct use
boolean | 1bcf4032-861b-490a-95a2-d20fe277e692 |  | tickbox | Emergency plan in place
checkpoint-status |  |  | checkpoint | Scaffolding
boolean | c851ead1-5881-40f6-b0cc-31588cda0d5f |  | tickbox | Register complete/updated weekly
boolean | d303ce2c-8e67-4099-a69a-c3754626e481 |  | tickbox | Handrails/mid-rails
boolean | e3dcb1aa-8aed-4331-a11b-946b15d808a5 |  | tickbox | Toe boards
boolean | a8f3cb4d-518b-42ad-a09d-36df5b72aeae |  | tickbox | Platforms
boolean | ce927e9f-97db-4274-9353-2f9ee4fa7840 |  | tickbox | Ladders
boolean | 2a215d21-010a-48f1-acba-15dbb596999c |  | tickbox | Base sound
boolean | 4c389aad-dda7-4309-913b-c6373231f2e1 |  | tickbox | Work platforms clear
boolean | 8d8ea702-bede-4e32-940b-d137d211e628 |  | tickbox | Platforms free of trip hazards (check plank overlaps)
boolean | c0c72bb3-46bd-43d0-92b2-5ebe15f4a6ae |  | tickbox | Planks tied down
boolean | 742f08dd-5be8-4278-8399-ea776a427474 |  | tickbox | Headroom clear
boolean | 0839ba4c-50d6-429e-9a67-2aa46a4a6f78 |  | tickbox | Ties/bracing adequate
checkpoint-status |  |  | checkpoint | Access
boolean | 25741c40-efab-43de-b0b4-16e0b913b5ea |  | tickbox | Ladders (Good condition, Top tied, Base secure, Stays to step ladders
checkpoint-status |  |  | checkpoint | Fall Hazards
boolean | 848fbd68-f324-43ff-bdf5-92693eede40f |  | tickbox | Floor edges (Handrails, Toe boards, Covered)
boolean | dd15cbe6-8b56-4cd2-ae42-a7e512f2d0bd |  | tickbox | Lift shafts (Handrails, Toe boards, Covered)
boolean | 910c6dea-3a2a-432a-acfb-7fb4b2654067 |  | tickbox | Floor openings (Handrails, Toe boards, Covered)
boolean | 3904f293-10eb-4129-afa5-faa1c15ecb1b |  | tickbox | Excavations (Handrails, Toe boards, Covered)
boolean | 6f1080e8-bf3d-4685-8281-7aa52bdb8774 |  | tickbox | Stairs (Handrails, Toe boards, Covered)
checkpoint-status |  |  | checkpoint | Safety / Environment Completion/Signoff
text | 60384865-647a-4bb2-80ef-8413f7a0724c |  | textbox | Safety & Environmental Supervisor
checklist-flat |  |  | checklist | Underground Services Install - Mechanical |  |  |  |  | Yes | Underground Services Install Checklist - Mechanical - QA | 9952764a-c874-4b2e-ab80-2e8ea2e3c87b
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | b7db1934-34e1-4480-9f18-6f9eb8f652ea |  | textbox | Subcontractor:
text | 866db633-62ce-4c6a-9ba6-0e92ecd0e3b4 |  | textbox | Drawing Reference:
checkpoint-status |  |  | checkpoint | Electrical Works complete
boolean | d8e68327-4295-4ffc-9f28-290bec290d1e |  | tickbox | Pipes cut clean and square
boolean | b8c63792-0317-4644-8770-2c508fa5e5f5 |  | tickbox | Located in the correct location
boolean | 0266d276-70ff-495b-81f7-c35656651a6b |  | tickbox | Pipework protected where required
boolean | 7f2ef8cd-2ce1-40be-9571-5875ae7d7754 |  | tickbox | Drainage material under pipe
boolean | 833d333b-3769-4e9d-b1e1-b695d131c462 |  | tickbox | Levels and inverts correct
boolean | 3166187e-6a30-4f2f-8600-de1024f1ae2b |  | tickbox | Pipework to correct falls
checkpoint-status |  |  | checkpoint | Testing to council requirements pass (pass once inspection is completed and approved)
boolean | 8d7f9c98-08eb-420b-a6ca-331cc381c89c |  | tickbox | Councils inspection booked
boolean | bc0f1694-f109-4fb2-b028-7fce00ab6efa |  | tickbox | Council inspection compete (attached in Council Inspection folder)
checkpoint-status |  |  | checkpoint | Consultant inspection completed & any observations closed out (Inspection attached in Consultants folder)
checklist-flat |  |  | checklist | Blockwork - |  |  |  |  | Yes | Blockwork Checklist - QA | 9995d82a-878d-4dde-9703-33b3853f5280
checkpoint-status |  |  | checkpoint | Area Clean and ready to start
checkpoint-status |  |  | checkpoint | Mortar and Grout mix received and achieved
checkpoint-status |  |  | checkpoint | Delivered material correct
checkpoint-status |  |  | checkpoint | Area of works completed
boolean | 782acb47-013c-4791-9eb6-b8d76d7aa05e |  | tickbox | Vertical joints correctly installed
boolean | 1162ee31-7a91-4c5e-a45f-1e96be680694 |  | tickbox | Correct alinement and plumb
boolean | 190cfeec-fe8b-43da-afde-dda99d43d24e |  | tickbox | Starters Drilled /expoxied in correct place
boolean | 6893e5a6-b493-4f2c-9e0c-faa830bd36b5 |  | tickbox | Reinforcing installed as specification and drawings
boolean | caaa377f-fb7b-4ca3-9199-d49ca519fbec |  | tickbox | Door and window openings in correct location
checkpoint-status |  |  | checkpoint | Inspected by council and signed off
checkpoint-status |  |  | checkpoint | inspected by engineer and signed off
checkpoint-status |  |  | checkpoint | Wall correctly grouted
text | fc167238-3ca4-4fe7-af3a-c3b9c1607198 |  | textbox | Cure time
checklist-sectioned |  |  | checklist | Wall & Ceiling Lining Checklist |  |  |  |  | Yes | TH - Wall & Ceiling Lining Checklist | 9ad550cc-2739-470b-949e-e78b0dfe080d
checkpoint-group |  |  | section | Gib Lining Checklist Ceilings
checkpoint-status |  |  | checkpoint | Gib lining QA received, reviewed, attached and approved pass when all below done
boolean | 9b519da6-7edf-5c57-a604-9a2b0e5943d8 |  | tickbox | All preline services completed and approval given to line
text | 0d9fb6e4-8659-5500-8d21-4238440292f3 |  | textbox | moisture content checked, recorded and acceptable
checkpoint-status |  |  | checkpoint | Lining installed ( pass when all below ticked)
boolean | 790f0a5a-0bc3-5ac8-8014-e8dc43f27b84 |  | tickbox | Correct lining type (Checked and approved)
boolean | ef553379-7363-5795-8038-aeb0b3c0dffa |  | tickbox | Correct fixings used and installed at correct centers
boolean | 01b327d8-7e31-5ef4-b40a-0b27453a4175 |  | tickbox | Any bracing elements completed to design specification
boolean | 9e946351-c025-541f-87ee-617face7729e |  | tickbox | where required 2nd layer installed
checkpoint-status |  |  | checkpoint | Council inspection complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Walls & Ceilings Gib Stopping Checklist
checkpoint-status |  |  | checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint-status |  |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status |  |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status |  |  | checkpoint | Adequate drying time between applications & No visible bubbling
checkpoint-status |  |  | checkpoint | Gib stopping QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All stopping completed and specified level of finish achieved
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checklist-sectioned |  |  | checklist | Scaffolding Tiles |  |  |  |  | Yes | Scaffolding Tiles Checklist | 9b220e59-7c66-46dc-b063-6fdfddebd3e9
checkpoint-group |  |  | section | Tower One - Ties (Attach photos, locations & any comments)
checkpoint-status |  |  | checkpoint | Tie One (Attach photos, locations & any comments)
label | 8b4702bb-228a-5673-a9b2-620866b8b35a |  | note | General note at top of document - Only two compression ties per level per tower can be removed at any one time. Maximum two levels at a time
text | 32e1a283-df30-5271-9649-9eb382281757 |  | textbox | Level:
text | 053b67c9-4b5b-5e2e-83bf-6d73d391ba8a |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Tie Two (Attach photos, locations & any comments) Pass once reinstated
text | 3d788e8a-8ea0-57ad-b4b6-6fd99b2fa6a1 |  | textbox | Level:
text | 3e88c49b-cb47-50b4-bc9a-ed9367d514da |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Tie Three (Attach photos, locations & any comments) Pass once reinstated
text | 983f08ee-aac9-545e-a5d1-014bd9756fd4 |  | textbox | Level:
text | 74c1237d-b815-505e-86e1-5f40229ef6f8 |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Tie Four (Attach photos, locations & any comments) Pass once reinstated
text | 3879e738-ec2d-5f72-bd01-735ecf321625 |  | textbox | Level:
text | 01e269da-e7c9-5342-94a4-3dbbf6262a7a |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Additional Ties - Have enough ties been reinstated before removing additional ties?
checkpoint-status |  |  | checkpoint | Tie Five (Attach photos, locations & any comments) Pass once reinstated
text | ab4b1d71-b9e0-5503-9539-be4304c58d37 |  | textbox | Level:
text | f00ab16e-dfdc-564f-b6ea-221b88327bb5 |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Tie Six (Attach photos, locations & any comments) Pass once reinstated
text | 21f32342-b571-58fc-978c-ed049f1db5d9 |  | textbox | Level:
text | 3e3659cf-0ae5-57bb-98a5-5e1caf3b2a0a |  | textbox | Elevation:
checkpoint-group |  |  | section | Tower Two - Ties (Attach photos, locations & any comments)
checkpoint-status |  |  | checkpoint | Tie One (Attach photos, locations & any comments)
label | 1ad8942b-e86b-5957-b769-59869c7ade02 |  | note | General note at top of document - Only two compression ties per level per tower can be removed at any one time. Maximum two levels at a time
text | de57d8d6-b5ba-5892-bec7-5b6f248b23e8 |  | textbox | Level:
text | dd93e29c-b911-5522-80cd-0c4707db663b |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Tie Two (Attach photos, locations & any comments) Pass once reinstated
text | 75ad413c-2ca9-5c0e-be0a-89a25bb55823 |  | textbox | Level:
text | a7fbe521-118e-53c6-bd2b-8ad8a258a1f2 |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Tie Three (Attach photos, locations & any comments) Pass once reinstated
text | 4ff8f2fc-ec74-572b-ab0d-79a53f989cfd |  | textbox | Level:
text | 682f0379-15b9-569d-8737-202205a5dd38 |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Tie Four (Attach photos, locations & any comments) Pass once reinstated
text | d4dab953-6b73-52f6-8ec1-bfd0abf22eab |  | textbox | Level:
text | c5332b00-7b15-558f-8ce8-b77255de598b |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Additional Ties - Have enough ties been reinstated before removing additional ties?
checkpoint-status |  |  | checkpoint | Tie Five (Attach photos, locations & any comments) Pass once reinstated
text | 32c3ea8d-1a2c-5f13-a0ff-5db0b629d0b9 |  | textbox | Level:
text | 3de7c4eb-e22a-5d71-9d8a-164882339c1d |  | textbox | Elevation:
checkpoint-status |  |  | checkpoint | Tie Six (Attach photos, locations & any comments) Pass once reinstated
text | 1dee9644-29a5-5272-8e24-e6007211fec0 |  | textbox | Level:
text | efa6a695-4c18-5567-8c42-7420a716a2e6 |  | textbox | Elevation:
checklist-flat |  |  | checklist | Reinforcing Mill Certificates - |  |  |  |  | Yes | Reinforcing Mill Certificates Checklist - H&S | a3ae503b-4945-4613-bdb7-3cf681422fcf
checkpoint-status |  |  | checkpoint | Reinforcing Mill Certificates attached, checked and acceptable
holdpoint |  |  | signoff | Request Documentation / Signoff
checklist-flat |  |  | checklist | P Floors checklist plant room |  |  |  |  | Yes | P Floors checklist plant room | a3ed1c25-01fc-4756-8c39-f3e3259538ce
checkpoint-status |  |  | checkpoint | Product checked and correct as per specification
checkpoint-status |  |  | checkpoint | All prestart checks completed and approval given to install
checkpoint-status |  |  | checkpoint | Mat installed as per product specification
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint-status |  |  | checkpoint | Tanking to area completed, checked and approved as per specifications
checkpoint-status |  |  | checkpoint | Initial testing complete
checkpoint-status |  |  | checkpoint | Any remedials completed
holdpoint |  |  | signoff | Request Sign Off from façade engineer
checkpoint-no-status |  |  | checkpoint | Request Sign Off from architect
holdpoint |  |  | signoff | Request Sign Off from architect
checkpoint-no-status |  |  | checkpoint | Request Sign Off from Manufacturer
holdpoint |  |  | signoff | Request Sign Off from Manufacturer
checklist-flat |  |  | checklist | Daily Site Report - Townhouse Works: |  |  |  |  | Yes | Daily Site Report - Townhouse Works | ab45f8aa-3fd0-4215-ba01-1b859af1bd2a
checkpoint-status |  |  | checkpoint | Hours Worked & Weather Conditions Recorded
text | 38d99b90-0987-52d1-af4f-ad545dd971a4 |  | textbox | My Hours Worked (start & finish)
select | 4c7dacde-3c2d-59bc-9926-aed43ae9dbe3 |  | dropdown | Weather Conditions AM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
select | bcd2e628-d945-5daa-a4c2-93588f47c1be |  | dropdown | Weather Conditions PM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
checkpoint-status |  |  | checkpoint | Visitors to Site (Record name, company & purpose)
checkpoint-status |  |  | checkpoint | Site Instructions Issued (Any relevant site instructions issued are documented here)
checkpoint-status |  |  | checkpoint | Day Works Agreed (Any relevant Day Works issued are documented here)
checkpoint-status |  |  | checkpoint | Subcontractors on site (all recorded area, man power, name)
button | 306b4eb5-6bac-5aa5-b65c-6a6d44b79f0c |  | button | Eireann - Area & Man Power | Yes, No
text | eb1ddb82-2301-5945-a946-fc13dc6274d0 |  | textbox | Area Working (Eireann)
text | 559e5ca9-3078-567d-9c59-8b9bcf911e79 |  | textbox | Manpower (Eireann)
button | 5795ad0b-4898-5042-a4df-0848b64898b2 |  | button | Toyle - Area & Man Power | Yes, No
text | 8015bce9-5166-551f-a12d-ae0708be6b68 |  | textbox | Area Working (Toyle)
text | cae5d41f-0194-57a7-ae46-0a8b1a2c0352 |  | textbox | Manpower (Toyle)
button | e76e582e-4fc1-5a9e-854b-a21e218ecc0e |  | button | Zero Fire - Area & Man Power | Yes, No
text | c4c43f71-8672-5bad-8cc8-c954b65423a1 |  | textbox | Area Working (Zero Fire)
text | e45ce16c-6b96-58dd-9ac7-5ebed986db07 |  | textbox | Man Power (Zero Fire)
button | 513ce02f-4497-5f2c-893e-c3c0fae5e6ce |  | button | Jensens - Structure - Area & Man Power | Yes, No
text | 465110ba-290e-5bd1-8758-6f149b33681f |  | textbox | Area Working (Jensens - Structure)
text | fb7be795-e263-5f1d-ab6b-33945cbde087 |  | textbox | Manpower (Jensens - Structure)
button | f42c8af0-7ec6-5c66-b0c6-546bc226034d |  | button | Turfrey - Area & Man Power | Yes, No
text | 35fc6e86-4b57-5357-b70c-feab15b4d1b0 |  | textbox | Area Working (Turfrey)
text | 7d0d9436-5020-5658-bea5-3ecde33dc9c7 |  | textbox | Manpower (Turfrey)
button | e0829595-3bde-563c-b0cc-3be3c09a6795 |  | button | The Insulator - Area & Man Power | Yes, No
text | f5e0f691-54b7-5380-b723-dd4730e30cb8 |  | textbox | Area Working (The Insulator)
text | d2fe8c24-8953-58ce-bb23-b63c8393bbf3 |  | textbox | Manpower (The Insulator)
button | 7f674d2e-ad0f-53c6-b2ec-1cd447a3eeda |  | button | Westaco - Area & Man Power | Yes, No
text | 6c9b5959-d18c-582c-abf9-795879666328 |  | textbox | Area Working (Westaco)
text | 08e093db-2ab5-5f2f-9e84-8238b1ff6d84 |  | textbox | Manpower (Westaco)
button | 46b79542-2007-5642-927b-e78ee4590b57 |  | button | Tempest - Area & Man Power | Yes, No
text | 692bf947-8c32-59e1-bd2b-358d9be022f3 |  | textbox | Area Working (Tempest)
text | 0693283d-6778-5fc7-ad96-9d9d842b7dd2 |  | textbox | Man Power (Tempest)
button | 980c283b-2574-5b27-a366-ada8ded78fd1 |  | button | Fabworx - Area & Man Power | Yes, No
text | 63bd2e85-c016-528d-8175-01b33bb91c9a |  | textbox | Area Working (Fabworx)
text | 4adbe9b2-c9f2-5498-b8b7-aa7b99fa0e71 |  | textbox | Man Power (Fabworx)
button | 627abe8d-8636-5d7b-87bc-0d7e830e77df |  | button | Total Access - Area & Man Power | Yes, No
text | 69e4a57a-da48-565e-a3ab-bc584b45c379 |  | textbox | Area Working (Total Access)
text | ac9760c5-fe0c-5192-80a3-b294d7a02586 |  | textbox | Man Power (Total Access)
button | 28f582a1-ba49-5eba-a2dd-bd969dfbce87 |  | button | Trade - Area & Man Power | Yes, No
text | b2c2bd6d-5238-50b0-b085-24ecb5f4793c |  | textbox | Area working (Trade)
text | 208ee17b-4a33-5f18-b87d-c24298377f87 |  | textbox | Manpower (Trade)
button | f41b993c-d171-5aea-8805-8eab03960ee9 |  | button | Trade - Area & Man Power | Yes, No
text | 7fe5d468-9a5b-55ed-b2ad-d96e4203a0ac |  | textbox | Area working (Trade)
text | 04ac7b47-1998-5237-8ec5-83112129e40f |  | textbox | Manpower (Trade)
button | d2c4e6d3-d49b-59b8-8130-2c1e49ca6d51 |  | button | Trade - Area & Man Power | Yes, No
text | db6dcad9-bd2e-5265-9f3c-11f133e2534c |  | textbox | Area working (Trade)
text | 75f5ec67-e9b5-5d46-8a6a-25abf2134fa6 |  | textbox | Manpower (Trade)
button | 3ac982ce-ba61-5503-9c64-54b7a04751c8 |  | button | Trade - Area & Man Power | Yes, No
text | d46633d2-9f0c-56cc-bd42-32c1cfbdf166 |  | textbox | Area working (Trade)
text | ca85ec3a-c8cf-5eb5-982d-1cd64f8b6713 |  | textbox | Manpower (Trade)
button | c90a0bac-9ba0-5613-a4b4-a79714a5c6f9 |  | button | Trade - Area & Man Power | Yes, No
text | d8cb2d75-87c4-5740-b5be-a973a6eca591 |  | textbox | Area working (Trade)
text | d44b60b7-1a99-5d03-8690-7cb0d85a6027 |  | textbox | Manpower (Trade)
checkpoint-status |  |  | checkpoint | Subcontractors contacted today (document name & date trade is required / conversation details)
checkpoint-status |  |  | checkpoint | Progress (quantities & location) - include photos
checkpoint-status |  |  | checkpoint | Unsatisfactory Progress - include photos (Fail if of serious concern - Pass once resolved)
checkpoint-status |  |  | checkpoint | Subcontractor/Supplier -Items delaying progress (Fail if of serious concern - Pass once resolved)
checkpoint-status |  |  | checkpoint | Design - items delaying progress
checkpoint-status |  |  | checkpoint | Disruption /Mitigation (subcontractor / design)
checklist-sectioned |  |  | checklist | Tower Structural Elements |  |  |  |  | Yes | Tower Structural Elements Checklist (Level 2 onward) - QA | add8e567-c7f2-4678-a31d-3b9ffd456ca0
checkpoint-group |  |  | section | Precast: Delivery Inspection
checkpoint-status |  |  | checkpoint | Product Information
text | d5bf2490-0385-4b84-bcf7-90fd904594d4 |  | textbox | Material Description:
text | 26c7829e-6c45-4f21-a700-3bb60d9f3668 |  | textbox | Manufacturer:
text | a26ab98e-66a9-43ae-ac29-0542ffa71d99 |  | textbox | Unit No:
text | c72ac9a6-b858-4751-bca4-31192258cbeb |  | textbox | Date & Time Received:
checkpoint-status |  |  | checkpoint | Documents Received With Delivery & Attached:
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Pre Lifting Checks Completed & Approval to Unload
boolean | b52c7dfd-335c-4c89-9b0c-d303cb95f52c |  | tickbox | Appropriate Manufacture QA Received
boolean | 23f297f2-a43c-4e3c-9d59-bcb9bc5a9359 |  | tickbox | Visual Check
boolean | 0e3d9d6e-af50-44ea-8862-0d6ce5372022 |  | tickbox | Lifting Gear Tagged
text | bf4bfcb5-4d0b-4e03-8222-cf5328235c0b |  | textbox | Damage Noted (Unit No & Type):
checkpoint-group |  |  | section | Precast Checklist: Installation
checkpoint-status |  |  | checkpoint | Product Information
text | 85d9851d-a043-47aa-8c35-c54948b19101 |  | textbox | Material Description:
text | ae2f79f2-3173-4821-8400-dcb0e48befbd |  | textbox | Manufacturer:
text | 041c348b-e2ac-4aab-a2cc-d77603124161 |  | textbox | Unit No:
checkpoint-status |  |  | checkpoint | Temporary Support Installed & Approved
boolean | 1e7286c1-9aeb-4bef-af29-80410aeb16c6 |  | tickbox | RL's Checked & Levels Correct
boolean | 7e1595fd-4302-4d6d-abfd-a11b44638f2d |  | tickbox | All Setout Completed Correctly & Approved
checkpoint-status |  |  | checkpoint | General Photos/Comments During Stair Install
checkpoint-status |  |  | checkpoint | Damage Report
boolean | a87a99a3-523a-4037-997e-eb39a2301af3 |  | tickbox | No Damage
text | 306f6025-5367-44fc-b294-2e7aa8c22b62 |  | textbox | Remedials Required (Unit & Type of Damage):
checkpoint-status |  |  | checkpoint | Remedials Completed & Approved
checkpoint-status |  |  | checkpoint | Approved Propping Installed Inspected
checkpoint-status |  |  | checkpoint | Heights, Orientation & Position Approved( once in place)
checkpoint-status |  |  | checkpoint | Precast Unit Completed, Correct, Approved & Reviewed (as per design)
checkpoint-status |  |  | checkpoint | Bearing Strip Installed
checkpoint-status |  |  | checkpoint | Seating Correct - Min 65mm
checkpoint-status |  |  | checkpoint | Props to Height (as per design)
checkpoint-status |  |  | checkpoint | Handrail Installed Approved
checkpoint-group |  |  | section | Concrete Pre Pour Checklist - Floors
checkpoint-status |  |  | checkpoint | Pre Pour Checklist
text | 760e06d1-1ecb-4e2f-b59c-ae32742268d8 |  | textbox | Drawing reference:
text | c5e9bf72-c38d-4493-a91e-8b3726ee82cf |  | textbox | Subcontractor:
checkpoint-status |  |  | checkpoint | Formwork Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Penetrations located/boxed & approved
checkpoint-status |  |  | checkpoint | Reinforcing Install completed and reviewed
boolean | c31d4abd-d055-4c2e-a49e-bb89d0aba614 |  | tickbox | Reinforcing - Size and type correct to specification
boolean | 0fdd9f5d-1a9b-4853-a6e3-bdf27304eb2b |  | tickbox | Reinforcing - spacing and location correct
boolean | ec657cae-60ac-4727-8ffa-750f001efdf9 |  | tickbox | Specified covers checked/correct
boolean | 9ad11ddf-cb51-4f87-949a-90be3afa224b |  | tickbox | Splice laps checked/correct
boolean | 3eaf2485-d19e-4855-a6b6-18e7f1524d5f |  | tickbox | Any starter bars are installed correctly (location, size and spacing )
boolean | e7ee44b6-8c9e-4018-9799-a682b5f6172c |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Structural Steel cast in plates installed/ checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Bottom of foundation is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | All services completed
checkpoint-status |  |  | checkpoint | Engineer informed of pour, checks completed (see Holmes folder and ensure observations are closed out)
checkpoint-group |  |  | section | Concrete Post Pour Checklist - Floors
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc.)
checkpoint-status |  |  | checkpoint | Trades Post Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour checks completed and any remedial work closed out
checkpoint-group |  |  | section | Concrete Pre Pour Checklist - Shear & Core Walls
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | 5891bda3-9357-4809-b4b3-bcd9011cd708 |  | textbox | Drawing reference:
text | 47fbb9ce-2d07-42e0-9d9d-c89f5bb3e738 |  | textbox | Subcontractor:
checkpoint-status |  |  | checkpoint | Shutter Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Penetrations located and checks
checkpoint-status |  |  | checkpoint | Reinforcing Trades Pre Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Reinforcing install completed and reviewed
boolean | 89f3e0a5-06c8-44de-8a5d-876385e90378 |  | tickbox | Reinforcing - Size and type correct to specification
boolean | 86738ffa-471a-4c27-8dbb-75b855699848 |  | tickbox | Reinforcing - spacing and location correct
boolean | d4baec24-6f21-43e6-9e5e-2e2932eafd38 |  | tickbox | Specified covers checked/correct
boolean | 866d947b-67af-4b57-8f27-723b2f002c79 |  | tickbox | Splice laps checked/correct
boolean | 90b031fc-73c0-4c3a-9709-afd694feda7e |  | tickbox | Any starter bars are installed correctly (location, size and spacing )
boolean | 513f4a1a-842b-40b0-a861-3cf29184fed3 |  | tickbox | Any additional items installed/ completed (trimmer bars etc.) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Structural Steel cast in plates installed/ checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Waterproofing installed
checkpoint-status |  |  | checkpoint | Bottom of foundation is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | All services completed
checkpoint-status |  |  | checkpoint | Engineer informed of pour, checks completed (see Holmes folder and ensure observations are closed out)
checkpoint-group |  |  | section | Concrete Pre Pour Checklist - Shear & Core Walls
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc.)
checkpoint-status |  |  | checkpoint | Trades Post Pour QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour checks completed and any remedial work closed out
checkpoint-group |  |  | section | Intumescent Painting
checkpoint-status |  |  | checkpoint | Product Details
text | b01995c8-fcfb-488f-8836-61fc5c101787 |  | textbox | Subcontractor:
text | e013da68-0c55-451d-9552-c531955bfb5f |  | textbox | Drawing Revision Number:
text | 57ec8da3-ce08-4091-b931-b30c69f77cf7 |  | textbox | Product Details
checkpoint-status |  |  | checkpoint | Approval Given to Apply Intumescent Paint to Completed Steel
checkpoint-status |  |  | checkpoint | Paint Specifications/ Product Checked
checkpoint-status |  |  | checkpoint | Correct Exclusion Zones & Health & Safety Requirements (Approved/Installed)
checkpoint-status |  |  | checkpoint | Paint Applied Using Correct Methodology
checkpoint-status |  |  | checkpoint | General Photos, Comments and Observations During Paint Application
checkpoint-status |  |  | checkpoint | Trades QA , reviewed and approved
checkpoint-status |  |  | checkpoint | Inspection Report Received by Consultants
checkpoint-status |  |  | checkpoint | Area Inspected by Manufacturer and Report Received
checkpoint-status |  |  | checkpoint | Remedials Competed and Signed Off
checklist-sectioned |  |  | checklist | Safety & Environmental Checklist - Split Site Team |  |  |  |  | Yes | Safety & Environmental Checklist - Split Site Team Rev 2 | b67b9cb5-5e10-4c08-a104-bf99718223e6
checkpoint-group |  |  | section | Safety / Environment Inspection Towers Fitout
checkpoint-status |  |  | checkpoint | Safety / Environment Inspection Towers fitout ( all observations/actions to be listed to the bottom of section)
text | 33d6c2a5-bfcc-5699-a9da-82704d1cb7d0 |  | textbox | Inspection today Carried out by:
checkpoint-status |  |  | checkpoint | Stairwells are clear
checkpoint-status |  |  | checkpoint | Clear work faces
checkpoint-status |  |  | checkpoint | Material stored away from edge and secured
checkpoint-status |  |  | checkpoint | Signage displayed and legible
checkpoint-status |  |  | checkpoint | PPE being used (glasses/ear muffs/ vests/masks/Hard hat/ Boots/Gloves)
checkpoint-status |  |  | checkpoint | Fire Extinguishers Sufficient numbers & Up to Date
checkpoint-status |  |  | checkpoint | Hot works permits issued, fire extinguishers / PPE
checkpoint-status |  |  | checkpoint | Lifeguards tagged
checkpoint-status |  |  | checkpoint | Tools in good condition, guards working
checkpoint-status |  |  | checkpoint | Sufficient lighting
checkpoint-status |  |  | checkpoint | Tools and equipment secured (tool bags, tethers, lanyards)
checkpoint-status |  |  | checkpoint | Handrails in place and secured
checkpoint-status |  |  | checkpoint | Penetrations in place, appropriately labeled and secured
checkpoint-status |  |  | checkpoint | Safety / Environment Completion/Sign Off
text | 3d5b2f9c-46aa-5682-9989-be9a06859c70 |  | textbox | Checklist Signed Off By:
checkpoint-group |  |  | section | Safety / Environment Inspection Towers Façade
checkpoint-status |  |  | checkpoint | Safety / Environment Inspection Tower Facade( all observations/actions to be listed to the bottom of section)
text | 82366e4c-e820-59d3-aa34-fb02c7ef5887 |  | textbox | Inspection today Carried out by:
checkpoint-status |  |  | checkpoint | Stairwells are clear
checkpoint-status |  |  | checkpoint | Clear work faces
checkpoint-status |  |  | checkpoint | Material stored away from edge and secured
checkpoint-status |  |  | checkpoint | Signage displayed and legible
checkpoint-status |  |  | checkpoint | PPE being used (glasses/ear muffs/ vests/masks/Hard hat/ Boots/Gloves)
checkpoint-status |  |  | checkpoint | Fire Extinguishers Sufficient numbers & Up to Date
checkpoint-status |  |  | checkpoint | Hot works permits issued, fire extinguishers / PPE
checkpoint-status |  |  | checkpoint | Lifeguards tagged
checkpoint-status |  |  | checkpoint | Tools in good condition, guards working
checkpoint-status |  |  | checkpoint | Sufficient lighting
checkpoint-status |  |  | checkpoint | Tools and equipment secured (tool bags, tethers, lanyards)
checkpoint-status |  |  | checkpoint | Handrails in place and secured
checkpoint-status |  |  | checkpoint | Penetrations in place, appropriately labeled and secured
checkpoint-status |  |  | checkpoint | Safety / Environment Completion/Sign Off
text | e395197f-76ca-57ff-9a54-212a293726e4 |  | textbox | Checklist Signed Off By:
checkpoint-group |  |  | section | Safety / Environment Inspection Podium & Townhouses Fitout
checkpoint-status |  |  | checkpoint | Safety / Environment Inspection Podium & Townhouses( all observations/actions to be listed to the bottom of section)
text | b543e48d-0574-58c9-a5af-8237520204e8 |  | textbox | Inspection today Carried out by:
checkpoint-status |  |  | checkpoint | Clear, safe access to work areas
checkpoint-status |  |  | checkpoint | Material stored away from edge, secured & covered
checkpoint-status |  |  | checkpoint | Signage displayed and legible
checkpoint-status |  |  | checkpoint | PPE being used (glasses/ear muffs/ vests/masks/Hard hat/ Boots/Gloves)
checkpoint-status |  |  | checkpoint | Hot works permits being issued, PPE and fire extinguishers
checkpoint-status |  |  | checkpoint | Lifeguards certified and current
checkpoint-status |  |  | checkpoint | Tools in good condition, guards working correctly.
checkpoint-status |  |  | checkpoint | Sufficient lighting
checkpoint-status |  |  | checkpoint | Tools and equipment secured (tool bags, tethers, lanyards)
checkpoint-status |  |  | checkpoint | Handrails in place and secured
checkpoint-status |  |  | checkpoint | Penetrations in place, appropriately labeled and secured
checkpoint-status |  |  | checkpoint | MEWP’s, Logbook completed, Check 6-month cert.
checkpoint-status |  |  | checkpoint | Traffic management measures set in accordance with the TMP
checkpoint-status |  |  | checkpoint | Sediment control measures (e.g. sediment ponds, silt fences, drain protection installed and maintained
checkpoint-status |  |  | checkpoint | Clean offices, break sheds, Toilets
checkpoint-status |  |  | checkpoint | Clear access in & around perimeter
checkpoint-status |  |  | checkpoint | Site secure
checkpoint-status |  |  | checkpoint | Safety / Environment Completion/Sign Off
text | 8ffc72e3-ab30-5291-94de-ba43f53f8234 |  | textbox | Checklist Signed Off By:
checkpoint-group |  |  | section | Safety / Environment Inspection Podium & Townhouses Façade
checkpoint-status |  |  | checkpoint | Safety / Environment Inspection Podium & Townhouses( all observations/actions to be listed to the bottom of section)
text | 6aa488eb-6e35-5e08-b11e-667156b9137f |  | textbox | Inspection today Carried out by:
checkpoint-status |  |  | checkpoint | Clear, safe access to work areas
checkpoint-status |  |  | checkpoint | Material stored away from edge, secured & covered
checkpoint-status |  |  | checkpoint | Signage displayed and legible
checkpoint-status |  |  | checkpoint | PPE being used (glasses/ear muffs/ vests/masks/Hard hat/ Boots/Gloves)
checkpoint-status |  |  | checkpoint | Hot works permits being issued, PPE and fire extinguishers
checkpoint-status |  |  | checkpoint | Lifeguards certified and current
checkpoint-status |  |  | checkpoint | Tools in good condition, guards working correctly.
checkpoint-status |  |  | checkpoint | Sufficient lighting
checkpoint-status |  |  | checkpoint | Tools and equipment secured (tool bags, tethers, lanyards)
checkpoint-status |  |  | checkpoint | Handrails in place and secured
checkpoint-status |  |  | checkpoint | Penetrations in place, appropriately labeled and secured
checkpoint-status |  |  | checkpoint | MEWP’s, Logbook completed, Check 6-month cert.
checkpoint-status |  |  | checkpoint | Traffic management measures set in accordance with the TMP
checkpoint-status |  |  | checkpoint | Sediment control measures (e.g. sediment ponds, silt fences, drain protection installed and maintained
checkpoint-status |  |  | checkpoint | Clean offices, break sheds, Toilets
checkpoint-status |  |  | checkpoint | Clear access in & around perimeter
checkpoint-status |  |  | checkpoint | Site secure
checkpoint-status |  |  | checkpoint | Safety / Environment Completion/Sign Off
text | 343885f8-dec7-59ce-a024-f9ab2d57c870 |  | textbox | Checklist Signed Off By:
checklist-flat |  |  | checklist | Exterior balconies & Tiling |  |  |  |  | Yes | Exterior balconies & Tiling (short version) | b754981b-a6ba-4d86-bd01-de80ff870b0a
checkpoint-status |  |  | checkpoint | Waterproofing completed and water tested
checkpoint-status |  |  | checkpoint | Correct jacks being used as per specification
checkpoint-status |  |  | checkpoint | Correct tiles ( type/colour ) confirmed
checkpoint-status |  |  | checkpoint | All tiles have been installed and deck finished
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Architects inspection complete
checklist-sectioned |  |  | checklist | Ceiling Preline |  |  |  |  | Yes | 3CONQA - Ceiling Preline Checklist V2 | b8417341-7f48-4e52-9a4a-a2d314569b71
checkpoint-group |  |  | section | Plumbing Ceiling First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Plumbing Ceiling QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | pipework checks with Plumber - tick when all below are checked and complete
boolean | bbcf5e29-a4de-589f-b179-3cef796e3d76 |  | tickbox | Pipes size correct and type
boolean | 24184125-cb42-5c7f-997b-41fd483a9eb7 |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | 90a4a358-9b01-5a0c-a3d3-bbd4024ccd03 |  | tickbox | Correct number of outlets /valves
boolean | e7f96b57-0cd6-58d9-840c-102bee810c4d |  | tickbox | Pipework protected at holes and notches
boolean | a9586e02-1671-5705-9457-e0b5f17e54a6 |  | tickbox | Heights of pipework checked ( above ceiling)
boolean | 9a7c2cae-cae5-5bae-9fd6-cb79258f1f75 |  | tickbox | All lagging is in place
boolean | d3d1ae2c-3ff6-53dd-9423-afd74efc0db2 |  | tickbox | All labelling installed
boolean | 8ba3f3a7-f2d8-5300-b2c5-402eb0f2ff6b |  | tickbox | All pipes cleaned/cleared before testing
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Service Engineer Beca - inspection requested
checkpoint-status |  |  | checkpoint | Protection installed for all ends
checkpoint-group |  |  | section | Fire Protection Ceiling (Sprinklers & Alarms)First Fix
checkpoint-status |  |  | checkpoint | Reference drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Sprinklers & alarms ceiling QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First fix checks with subcontractor - tick when all below are checked and complete
boolean | 90e0140c-8858-5b25-b5de-3b16066788fb |  | tickbox | Pipes checked for damage/corrosion
boolean | 67e27a83-5271-5dc5-89dd-02f6bb30bae2 |  | tickbox | Pipes size correct and type
boolean | 6a0e9960-4411-5ca1-834d-eb7ca6356724 |  | tickbox | Pipe supports , anchors and hangers/clips installed correctly including seismic
boolean | fdf4dbb6-2dc5-5e89-b9c2-01ae96b39c40 |  | tickbox | Correct number of outlets/droppers for sprinklers
boolean | 075fe5b3-a31c-5a9c-a986-935ce0e59b66 |  | tickbox | Heights of pipework checked ( above ceiling)
boolean | 3d344e51-d160-593c-a6f8-4193daa9f2dd |  | tickbox | Any lagging required is in place
boolean | 2860cbd1-452b-5747-acaa-6ea32aa6f9cb |  | tickbox | All labelling installed for pipework
boolean | 7ed7b5ce-76d9-5f41-a7d9-fd0c4c704e88 |  | tickbox | All wiring labeled/identified
boolean | 8fd6e5c2-3b45-55ad-98de-ca3d7d5fe769 |  | tickbox | All droppers for ceiling are installed
boolean | 48847fa2-61a5-5254-a3f6-4291db5050bd |  | tickbox | All pipes cleaned/cleared before testing
boolean | cb79b183-1815-5135-ba59-b30eb85a6c05 |  | tickbox | Cables are completed and with proper support
boolean | 78ce92da-6670-52b6-8824-c83f32cc9580 |  | tickbox | Correct number of connections for detectors
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | FPIS inspection sign off
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Service Engineer Beca - inspection requested
checkpoint-status |  |  | checkpoint | Protection- all amends covered
checkpoint-status |  |  | checkpoint | Any onsite changes documented(copy attached)
checkpoint-group |  |  | section | Mechanical Services Ceiling First Fix
checkpoint-status |  |  | checkpoint | Mechanical Services Ceiling First Fix
text | dd71a4d0-3cb3-54bd-a79d-84106875a151 |  | textbox | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Mechanical ceiling QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First fix spot checks with subcontractor - tick when all below spot checks are complete
boolean | 2cb83b41-c8f3-557f-92ab-01e80c8302b3 |  | tickbox | Pipes checked for damage/corrosion/Scale
boolean | f8b98c6e-88a5-53cc-a6f1-b2de2247a9ab |  | tickbox | Ducts size correct and type
boolean | 80654bef-35a1-5e73-85d6-7c4cdd4a66e2 |  | tickbox | Duct supports , anchors and hangers/Clips installed correctly including seismic
boolean | 5d4b082f-d24c-59ed-af83-5803edf530b8 |  | tickbox | Thermal ducts and pipes insulated and labelled
boolean | b0efb106-9b49-57b8-a603-112ad7d1c222 |  | tickbox | Heights of pipework checked ( above ceiling)
boolean | 27208de4-d9c2-5556-8eeb-ec8e493a9d0a |  | tickbox | All labelling installed
boolean | 727afa41-43a0-5174-8638-73bb7f64d1fa |  | tickbox | All wiring labeled/identified
boolean | f5d1597c-585b-59d9-a9bc-51495491d45d |  | tickbox | all ducts cleaned/and ends capped where needed
boolean | f81b92ac-153a-5bf7-95ee-bf1409891927 |  | tickbox | Cables are completed and with proper support
boolean | 708d92f2-9ca7-5344-89cf-586c90ea6d3a |  | tickbox | All equipment , valves and fire dampers, air outlets louvres, grilles and dampers are in place and accessible where required
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Service Engineers Beca - Inspection requested
checkpoint-status |  |  | checkpoint | All ends covered/protected to reduce debris
checkpoint-status |  |  | checkpoint | Any onsite changes documented(add a copy)
checkpoint-group |  |  | section | Electrical First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 6d3da883-76f7-510b-b558-a0f0b416a8b7 |  | tickbox | Setout/straightness checked
boolean | ce6243db-7b94-5ffd-8bf8-dd8154c9823f |  | tickbox | All required noggs placed in framing
text | 0d613412-7fa9-591e-bfaa-1ab9a9f09c24 |  | textbox | Reference drawings (add drawing numbers & revisions)
checkpoint-status |  |  | checkpoint | Electrical QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First fix checks with subcontractor - tick when all below are checked and complete
boolean | 25af368a-aba7-5d88-98fd-45bd467b483a |  | tickbox | Cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | 5a7e5117-88e1-58ea-af86-9082f08599d8 |  | tickbox | All outlets and switches at the correct position & height
boolean | 0cc47d61-2269-566f-973c-667bf7c50a84 |  | tickbox | Wiring for ceiling lights in correct position
boolean | 1a920b5b-ebbf-5e31-9519-3e2360e5b5b7 |  | tickbox | Correct number of ceiling lights installed
boolean | 6f1dce5f-3e32-5ab6-b0a0-8f600cd78d9b |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | af69c623-4777-5814-89e6-18c1f9f16301 |  | tickbox | Power supplies for roller doors, HWC,Sliding doors, fire ,security etc. installed in correct place
boolean | 385854dc-5524-5766-9241-3acab311904c |  | tickbox | All wiring labeled/identified
boolean | 5c432752-53a6-55d9-8000-6915421cca41 |  | tickbox | All earthing and cables installed
boolean | e167441c-e1cb-5bb3-9b26-a309a09f6a0f |  | tickbox | Cables are completed and with proper support
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | All ends covered/protected to reduce debris
checkpoint-status |  |  | checkpoint | Any onsite changes documented( add a copy)
checkpoint-group |  |  | section | Data/Security First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | 642b5587-3471-59c9-9451-e3bbaef01803 |  | tickbox | Setout/straightness checked
boolean | e429f7d0-f4b5-54ef-9d6c-a84570dd09f3 |  | tickbox | All required noggs placed in framing
text | e8dbe82f-9819-5892-ba98-f234035394bb |  | textbox | Reference drawings (add drawing numbers & revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
boolean | dbff30f7-df9f-5e2c-96b9-4698240946a9 |  | tickbox | Cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | 131d3f98-805c-5352-96bf-c229db5bc5f8 |  | tickbox | All outlets and switches at the correct position & height
boolean | 923c05ea-f000-54a5-9dcd-f00d064a6bb3 |  | tickbox | Wiring for ceiling lights in correct position
boolean | cfdc1b34-6937-5b89-9035-2f2639b316c1 |  | tickbox | Correct number of ceiling lights installed
boolean | 17ffa536-18e2-5f9b-b1ef-1c1128267556 |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 2c1a0490-e78b-557d-b91d-bdc0b95859e9 |  | tickbox | Power supplies for roller doors, HWC,Sliding doors, fire ,security etc. installed in correct place
boolean | ed8c86cd-6d5d-5426-8e2d-81549a15896c |  | tickbox | All wiring labeled/identified
boolean | d3b03c58-2a25-5241-95b4-f71c24709538 |  | tickbox | All earthing and cables installed
boolean | af11fa9f-c603-5367-b4c0-be8bafdce686 |  | tickbox | Cables are completed and with proper support
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Services Engineer - Beca - inspection requested
checkpoint-status |  |  | checkpoint | All ends covered/protected to reduce debris
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Passive Fire
checkpoint-status |  |  | checkpoint | Passive Fire QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All Passive fire elements completed, reviewed and approved
checkpoint-status |  |  | checkpoint | All penetrations through the floors and passive elements are completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Consultant/Council Inspections
boolean | 0cc2c463-92aa-5fc4-94e2-f0dce041c6c8 |  | tickbox | Third party review complete
boolean | edb21679-89a1-5092-a57a-8db331f1f249 |  | tickbox | Fire consultant review
boolean | 4f9ff1eb-52b6-5cb6-9692-f513dcbabf66 |  | tickbox | Council inspection complete
checkpoint-group |  |  | section | Rondo Ceiling Grid Installation
checkpoint-status |  |  | checkpoint | Service mark out completed, checked and acceptable (clashes considered)
checkpoint-status |  |  | checkpoint | Ceiling grid ( pass when all below ticked)
boolean | ce1622ab-7611-5ab9-987f-bdfc3ec1305a |  | tickbox | Ceiling height confirmed
boolean | 7a9c5904-3750-55aa-a214-69d701273f4f |  | tickbox | Appropriate fixings used and installed as per required specification
boolean | 7548d1c2-c315-50cd-8345-19c72c25030f |  | tickbox | Appropriate spacings for respective grid elements
boolean | 3e55f151-40f6-5002-9e0e-9efdaa509a32 |  | tickbox | Battens level confirmed
boolean | 1dfef629-8fd0-5929-957b-9d29f6a7e8e4 |  | tickbox | Perimeter channel/angle installed correctly
boolean | e9fb991d-a242-547b-afd3-5a4d94f41455 |  | tickbox | All strong backs installed where required to meet specification
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Seismic restraints installed and signed off by engineer
checkpoint-group |  |  | section | Insulation/Acoustic Ceiling prior to lining
checkpoint-status |  |  | checkpoint | Insulation & Acoustic QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Insulation pre lining works completed, spot checks done
boolean | 60b8f1b9-cce2-5dbb-ba01-be2f6dfbf67b |  | tickbox | Correct product & R value
boolean | 7534be87-3a3e-5e49-b0d4-9c104c3e9ea2 |  | tickbox | Fitting correctly
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Preline Final Ceiling Inspection
checkpoint-status |  |  | checkpoint | All above preline elements checked, correct & approval to line
boolean | 1823451a-938d-596d-9f8d-e68ca280d26a |  | tickbox | Council inspections carried out & attached in council folder
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checklist-flat |  |  | checklist | Safety & Environmental Checklist Streetscape |  |  |  |  | Yes | Safety & Environmental Checklist Streetscape - H&S | b97f66c3-9ea5-4ecd-8f49-4f177c4c278c
checkpoint-status |  |  | checkpoint | Safety & Environmental Inspection Details
text | 7ccd173b-843d-5ab1-ae4f-22fc368ee2b5 |  | textbox | Safety and Environmental Supervisor:
text | d29f64f8-5556-52ed-8022-73fbe093808c |  | textbox | Inspection by:
checkpoint-status |  |  | checkpoint | Site Access is in place (Pass once all is inputted)
boolean | 7699ed4c-45e2-5e6c-ae37-2d3a2ed6cf1c |  | tickbox | Shore Loading is Correctly Installed
boolean | 4d55338d-0bae-595e-a483-b815fd655ae5 |  | tickbox | Fencing is Located Securely Around all Work Areas/Holes
boolean | 1a9750f7-9817-5825-b73a-5398873773ff |  | tickbox | Ladders are Secured In Place
boolean | b3a83e04-6df0-5315-9797-d967b15d7c80 |  | tickbox | Emergency Plan in Place
checkpoint-status |  |  | checkpoint | Site Control
boolean | c8155765-0d09-512f-bb7f-5420c211d41f |  | tickbox | Hazard ID up to date
boolean | 03e38f86-b1b8-5db9-b558-dcb6d0828b96 |  | tickbox | Environmental Plan Current – List any issues
boolean | ecc496dd-3a6b-521c-9830-951c1c1b0d2e |  | tickbox | Date of Last Safety & Environmental Toolbox Meeting
boolean | 8be155c2-195d-531d-ac01-2a31e6d9527c |  | tickbox | Safety and Environmental Inductions Being Completed
boolean | d154c122-2dea-5605-b45e-8dcd3aec52e0 |  | tickbox | Safety and Environment Notice Board Visible & Current
checkpoint-status |  |  | checkpoint | Traffic Management
boolean | fb51bac9-2ec4-5fc5-ac14-b7f96d8dc4cd |  | tickbox | Temporary Traffic Management Plan (TMP) in place
boolean | 0a8399f9-d702-5a8c-8948-dbde1b098546 |  | tickbox | Traffic Management Measures Are In Accordance With The TMP
boolean | be63289e-4606-5901-92b3-cbadcc7f4d94 |  | tickbox | TMP Supervised by a Qualified STMS
boolean | 3dbd8560-fd4e-55a1-9882-65272824d3fd |  | tickbox | Traffic Controller on Site
checkpoint-status |  |  | checkpoint | Sediment & Erosion Control
boolean | bbb585df-67a3-541e-90e6-89448330e294 |  | tickbox | Silt Control Plan in Place
boolean | e4499a16-91b1-58ef-aaac-c8bf5e6843ab |  | tickbox | Sediment Control Measures (e.g. Sediment ponds, silt fences) Installed & Being Maintained
boolean | e634e9e5-6a26-59d8-ae85-66f3cc347ef1 |  | tickbox | Dust/Noise Controlled
boolean | b6957425-37a5-537e-a41c-848f0bfebb58 |  | tickbox | Roads Clean or Being Regularly Swept
boolean | a7c67b69-89a4-5d6e-9c8b-8cafe4e25b30 |  | tickbox | Footpath Clean or Being Regularly Swept
boolean | f3430d9a-84d5-5f1f-859b-c4c7df24f02c |  | tickbox | Construction Noise Being Monitored
checkpoint-status |  |  | checkpoint | General Site Tidiness
boolean | 1cdad438-c308-5bc8-8736-c57dfbeadc85 |  | tickbox | Clear, Safe access to Work Areas
boolean | f20a57d7-7adf-55dd-8392-121afb3cd071 |  | tickbox | Ladders /Stairs Access Points Clear
boolean | 436a8693-920f-545f-900f-3d03ae2aab09 |  | tickbox | Hoardings/Perimeter Fence & Gates Secure
checkpoint-status |  |  | checkpoint | Personal Safety Equipment
boolean | 1be6b8b6-3642-5e6f-b47a-9fb6bfebcc53 |  | tickbox | Signage Displayed & Legible
boolean | 74a19ec3-1b92-5c41-a42f-0d06d8c12e8f |  | tickbox | Hi Vis & Correct Footwear Being Worn
boolean | 296272ff-5eb2-5654-937a-c73e6d8ebb78 |  | tickbox | Long longs/Glasses & Gloves Being Worn
boolean | 533e0b6c-c7d3-5fc1-b3e0-6bdd5f851da1 |  | tickbox | Where Required Ear Protection/ Masks Being Worn
checkpoint-status |  |  | checkpoint | First Aid/Fire Prevention
boolean | ad4d28d5-e10b-5952-9e2f-399e113de1e7 |  | tickbox | First Aid Box Checked & Available
boolean | 3e5fedaa-9784-582a-973d-7cc4ad5d7217 |  | tickbox | Accident Register Checked & Photographed
boolean | d51e4790-67c1-5f38-bea5-5bc8adeeea5c |  | tickbox | Fire Extinguishers (Available , In Sufficient Number & Current)
boolean | 2306b9d9-0951-5db1-97ef-6aeb11762dbe |  | tickbox | Evacuation Procedure In Place & Current
checkpoint-status |  |  | checkpoint | Sun Exposure
boolean | db23dfb4-8a58-5f10-ac1d-41cead1af68d |  | tickbox | Employees Wearing Clothing to Prevent Sun Exposure
boolean | 5bbc7243-c192-5cff-a2ce-f3634ae043bd |  | tickbox | Broad Spectrum Sun Screen Available On Site (SPF 30 or more)
checkpoint-status |  |  | checkpoint | Machinery/Lifting equipment
boolean | 2f12f2bc-65b0-5e83-b22e-14abb7ee6c38 |  | tickbox | Lifting Equipment Checked
boolean | e310e7c7-49ab-53ae-b1c9-e126dd6d6ba7 |  | tickbox | Lifting Equipment Certification Current
boolean | 11bfc16d-13f4-52f7-abd4-330613053a0a |  | tickbox | Slings/Chains Certified
checkpoint-status |  |  | checkpoint | Machinery
boolean | 992b6f9f-3a6e-57bd-87c7-b7da5fd5c2df |  | tickbox | Daily Prestart on Machinery in Use Being Completed
boolean | 41060cc8-a6e1-532b-9b9c-f6700dd14fd5 |  | tickbox | Machine Operation Trained /Competent
boolean | f4c0b43a-1772-5a22-b2f4-18d9eb6cf7ea |  | tickbox | Hot permits(Welding & Cutting) In Place( Fire Extinguisher Within Arms Reach)
boolean | 1d80d16e-364c-5509-8622-5a3f8af7a18e |  | tickbox | Welder Trained/Competent and has Correct PPE
checkpoint-status |  |  | checkpoint | Chemicals
boolean | 369d8c18-a628-5561-868d-1bedfc4fa615 |  | tickbox | Correctly Stored
boolean | 6574958a-7ed8-5cc4-958d-81d57f904244 |  | tickbox | SDS Available
boolean | e66c8c4d-e4de-5862-bb83-ddf51e326ab7 |  | tickbox | Operators Using PPE
boolean | b3db8bb4-f2bf-5c48-800a-c621ef9ce06b |  | tickbox | Spill Kit Available
checkpoint-status |  |  | checkpoint | Safety / Environment Completion/Signoff
text | 0eb52b79-eabd-50ac-949b-456d7bd89f2b |  | textbox | Safety & Environmental Supervisor ( Add Name)
checklist-flat |  |  | checklist | Work Progress - Observations |  |  |  |  | Yes | Work Progress - Observations | bc99d4de-dff6-4665-8c60-a4d56efbc6b6
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 1 (True)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 2 (True)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 3 (True)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 4 (True)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 5 (True)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 6 (True)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 7 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 8 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 9 (True)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 10 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 11 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 12 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 13(true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 14(true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 15 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 16 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 17 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 18 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 19 (true)
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Observation 20 (true)
checklist-sectioned |  |  | checklist | Ceiling Preline |  |  |  |  | Yes | Ceiling Preline checklist (V1) - QA | bd5ab3f9-ee7c-4050-bb0c-095dd6fec0c7
checkpoint-group |  |  | section | Plumbing Ceiling First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Pipework's checks with Plumber - tick when all below are checked and complete
boolean | 2177c922-2c14-4d7c-8ad6-afc1b34cd528 |  | tickbox | Pipes size correct and type
boolean | ee6df848-4f16-4624-a774-cb6f70a58154 |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | 882c7008-8454-49d9-a6fa-a93104485c80 |  | tickbox | Correct number of outlets /valves
boolean | 858ad25b-0abb-4c25-af1c-fbf25c447f7b |  | tickbox | Pipework protected at holes and notches
boolean | 9d5b4e77-179f-483f-b90a-4ac9e33550f3 |  | tickbox | Heights of pipework's checked ( above ceiling)
boolean | 9bb40d33-2aff-499c-b1eb-3cb1a980a784 |  | tickbox | All lagging is in place
boolean | fc4ffc0a-2381-420e-9181-c2d0e4b6315a |  | tickbox | all labelling installed
boolean | 04981a6c-070b-4c8e-bd80-542d87b3e699 |  | tickbox | all pipes cleaned/cleared before testing
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Protection installed for all ends
checkpoint-group |  |  | section | Fire Protection Ceiling (Sprinklers & Alarms)First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
boolean | b0426ee7-b76f-4005-863e-44f2a9dac3a9 |  | tickbox | Pipes checked for damage/corrosion
boolean | d41810ac-258c-491a-917a-4d1e185a982e |  | tickbox | Pipes size correct and type
boolean | b98bcd57-01cc-49bc-9316-c879c6d958ae |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | a1ebb393-0b3b-4643-b6a6-54b1998e841d |  | tickbox | Correct number of outlets/droppers for sprinklers
boolean | 19a1db87-f3e8-4a97-af36-db97e80b37a4 |  | tickbox | Heights of pipework's checked ( above ceiling)
boolean | 9816ff2f-3f51-43a1-81c0-ac46cd54096b |  | tickbox | Any lagging required is in place
boolean | 6d041b0a-a024-409a-8729-12f13f9c31dd |  | tickbox | all labelling installed for pipework
boolean | 5fe5925a-ae87-4603-b89c-22a0eaba3512 |  | tickbox | All wiring labeled/identified
boolean | 5f0354c1-1f0d-4525-afc7-f9bcfe8bc992 |  | tickbox | all pipes cleaned/cleared before testing
boolean | 4a9ea6af-9e57-4518-b54b-79b8659335df |  | tickbox | Cables are completed and with proper support
boolean | d5f0ec08-82ac-49ae-8d2d-a83f1a87c241 |  | tickbox | Correct number of connections for detectors
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | FPIS inspection sign off
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Protection- all amends covered
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Mechanical Services Ceiling First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | First Fix spot checks with Subcontractor - tick when all below spot checks are complete
boolean | 34b37701-2ce2-4f01-ab5b-df7d91c9b7dd |  | tickbox | Pipes checked for damage/corrosion/Scale
boolean | a4f3dfec-5df4-4355-a2f7-0bdc02add789 |  | tickbox | Ducts size correct and type
boolean | 73c2abc0-f293-4fc8-8dbd-d06fa117a8fc |  | tickbox | Duct supports , anchors and hangers/Clips installed correctly including seismic
boolean | 405f4a5f-6efc-42eb-89ad-acbfaa81e7c6 |  | tickbox | Thermal Ducts And pipes insulated and labelled
boolean | f3766ce0-4bf5-4a10-b99f-966c34268c89 |  | tickbox | Heights of pipework's checked ( above ceiling)
boolean | ab0748ae-7358-4e12-a5f8-9b37853c6e12 |  | tickbox | all labelling installed
boolean | f02b7513-5563-47e7-bfaa-f50b0c4b3e61 |  | tickbox | all ducts cleaned/and ends capped where needed
boolean | ad8ae374-9c08-49bf-a29a-26f99c85aad7 |  | tickbox | Cables are completed and with proper support
boolean | 4ca359d3-a275-41bc-82a3-dcc5296c7128 |  | tickbox | All equipment , valves and fire dampers, air outlets louvres, grilles and dampers are in place and accessible where required
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | All ends covered/protected to reduce debris
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Electrical/Data/Security First fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | a38ffd50-cdca-42c6-8f5b-a7dfba604143 |  | tickbox | Setout/straightness checked
boolean | 2edac539-3d8d-4961-9019-c391fbf8d403 |  | tickbox | All required noggs placed in framing
text | 0449c302-4e0a-4690-9daf-592acad29244 |  | textbox | Reference drawings (add drawing numbers & revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
boolean | 8e5fbd74-a026-4d12-9e03-682628a1d72f |  | tickbox | Cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | 6d28a0d2-cad0-44ec-9441-531f81c149e8 |  | tickbox | All outlets and switches at the correct position & height
boolean | d1837b7c-b881-4d70-8879-d40cca88f184 |  | tickbox | Wiring for ceiling lights in correct position
boolean | f3273b7d-26e0-4b8b-9b73-235708b97cf6 |  | tickbox | Correct number of ceiling lights installed
boolean | 45aa13dd-dcda-4a17-a56f-c1321f032bbc |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 34172190-5b1e-4aea-b5d6-f108d985ad70 |  | tickbox | power supplies for roller doors, HWC,Sliding doors, fire ,security etc. installed in correct place
boolean | 44c8d4d3-bf77-4d9a-8cb2-4f17d06718c1 |  | tickbox | all earthing and cables installed
boolean | fd9aef72-1cc1-420e-bf1d-f25618b61e71 |  | tickbox | Cables are completed and with proper support
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | All ends covered/protected to reduce debris
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Rondo Ceiling Grid Installation
checkpoint-status |  |  | checkpoint | Service mark out completed, checked and acceptable (clashes considered)
checkpoint-status |  |  | checkpoint | Ceiling Grid ( pass when all below ticked)
boolean | 01198e9a-a297-46ec-bc1b-cefd8f4a08bd |  | tickbox | Ceiling Height confirmed
boolean | 38a2004d-e684-4aa5-97ee-d3ebb955f881 |  | tickbox | Appropriate fixings used and installed as per required specification
boolean | fd1fbcad-0935-4ceb-ae87-59a1a824373d |  | tickbox | Appropriate spacings for respective grid elements
boolean | 92b2b64f-98c6-43cb-8dcc-a822c15d4025 |  | tickbox | Battens Level
boolean | b08b66e3-a397-4688-93da-45732951e6bb |  | tickbox | Perimeter channel/angle installed correctly
boolean | 98eeeb8e-2deb-49eb-8a44-1a53cbab7b32 |  | tickbox | All strong backs installed where required to meet specification
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Insulation Checklist prior to lining
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Insulation pre lining works completed, checked & approved
boolean | 6b2d4d00-51a4-4ba0-8a6b-e2408ef63bb9 |  | tickbox | correct product & R value as per specification
boolean | 7e337cd1-e170-4eb1-87a4-a4135980b0ac |  | tickbox | Fitting Snug
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Preline Inspection Checklist
checkpoint-status |  |  | checkpoint | All above preline elements checked, correct & approval to line
boolean | 6b031ecd-f694-4a77-94f9-c5a2d2b2022b |  | tickbox | Council inspections carried out & attached in council folder
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checklist-flat |  |  | checklist | Precast: Installation |  |  |  |  | Yes | Precast - Installation - QA | c36c0d2d-bd15-4b5a-a878-31508811826b
checkpoint-status |  |  | checkpoint | Product information
text | e01d74c6-6165-417b-b0f7-b045ca7a39d5 |  | textbox | Material Description:
text | e4d02494-9ad9-4468-bbd2-b9893bfbdf52 |  | textbox | Manufacturer:
text | 472c2e64-3b07-44ae-b6ff-d4f727aa6df6 |  | textbox | Unit No:
checkpoint-status |  |  | checkpoint | Temporary support installed and approved
boolean | 5c06cfd7-7b1d-4c05-9317-90f274480311 |  | tickbox | RL's checked and levels correct
boolean | 181ad081-1345-4659-a430-9f08993cec09 |  | tickbox | All setout completed correctly and approved
checkpoint-status |  |  | checkpoint | General photos/comments during stair install
checkpoint-status |  |  | checkpoint | Damage Report
boolean | d2cb5d05-9aee-4d9b-b3a1-d2a9cbceb096 |  | tickbox | No Damage
text | 62a5b8b0-933f-47f1-b242-66e3b62f1f0f |  | textbox | Remedials required (unit and type of damage):
checkpoint-status |  |  | checkpoint | Remedials completed & Approved
checkpoint-status |  |  | checkpoint | Approved propping installed and inspected
checkpoint-status |  |  | checkpoint | Heights, orientation and position approved once in place
checkpoint-status |  |  | checkpoint | Precast unit completed, correct, approved and reviewed as per design
checkpoint-status |  |  | checkpoint | Bearing strip installed
checkpoint-status |  |  | checkpoint | Seating is correct - min 65mm
checkpoint-status |  |  | checkpoint | props wound up to height as per design
checkpoint-status |  |  | checkpoint | Handrail in area installed and approved
checklist-sectioned |  |  | checklist | Soffits |  |  |  |  | Yes | Soffits | c4509fa1-e104-4843-9089-55eeb7c7fc3a
checkpoint-group |  |  | section | Soffit Install
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Soffits complete,
boolean | 35106523-57a7-5682-94f2-203e1ef1b739 |  | tickbox | Soffit Framing completed, checked and accurate including sheet joins/blocking
boolean | e3dd4704-71a3-5f92-84d4-896155689998 |  | tickbox | Relevant services first fix and nogging completed
boolean | 8d5e4653-9bb3-5145-879f-463057a7a39c |  | tickbox | Lining product checked and correct, all pre checks completed & approval to line
boolean | 8bd5160b-10f6-52c7-bc4e-86bdfab45105 |  | tickbox | Joints all neat and correct
checkpoint-status |  |  | checkpoint | General photos, comments and observations during installation
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Consultant Inspections requested
checkpoint-status |  |  | checkpoint | Inspections completed
checkpoint-group |  |  | section | Soffit Painting
checkpoint-status |  |  | checkpoint | First coat/ sealant coat completed
checkpoint-status |  |  | checkpoint | General comments and photos of additional paint application
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Final coat completed, no overpainting, finish acceptable as per specification
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Design team inspections completed
checklist-flat |  |  | checklist | P- Painting Checklist |  |  |  |  | Yes | P- Painting Checklist | c7d4f0d4-9c20-4162-a373-1455be7c22a3
checkpoint-status |  |  | checkpoint | Area / substrates acceptable
checkpoint-status |  |  | checkpoint | Paint specifications and colour checked & correct to specification
checkpoint-status |  |  | checkpoint | First coat/ sealant coat completed( attached trade QA )
checkpoint-status |  |  | checkpoint | Light inspection completed & remedials complete
checkpoint-status |  |  | checkpoint | first coat -General comments and photos of additional paint application
checkpoint-status |  |  | checkpoint | Final coat completed,( trade Qa attached)
checkpoint-status |  |  | checkpoint | Final coat -General comments and photos of additional paint application
checklist-flat |  |  | checklist | Council Inspection - |  |  |  |  | Yes | Council Inspection Checklist | c844ef84-0320-490b-90ea-ded37f902088
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of Inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Type of Inspection:
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council inspection attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | Passive Fire Works |  |  |  |  | Yes | Facade - Passive Fire Works | cc8fa5ba-8f18-4f94-aa23-14ce61dd8bb7
checkpoint-status |  |  | checkpoint | Firetherm Rainbar
checkpoint-status |  |  | checkpoint | Hilti in Sto Projections
checkpoint-status |  |  | checkpoint | Timber to Balcony edge installed
checkpoint-status |  |  | checkpoint | Intubatt to balcony edge installed
checkpoint-status |  |  | checkpoint | Architect& Fire Engineer signoff
checklist-flat |  |  | checklist | Underground Services Install - Fire Services |  |  |  |  | Yes | Underground Services Install Checklist - Fire Services - QA | d11cb925-dd34-40d9-a0d8-8a526d8b5214
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | eb9a3e59-80e1-4f1b-a6f1-2772a2292c2b |  | textbox | Subcontractor:
text | 88a57b66-39c8-45b0-8d2b-12627554d5b8 |  | textbox | Drawing Reference:
checkpoint-status |  |  | checkpoint | Electrical Works complete
boolean | 25a71cc4-27b4-4bfc-a680-3b46bfa74edd |  | tickbox | Pipes cut clean and square
boolean | 4861b4fa-0827-454f-b51f-5e0827401b78 |  | tickbox | Located in the correct location
boolean | 0cfcbdf3-bcfb-4457-889a-640d4da68845 |  | tickbox | Pipework protected where required
boolean | a5ead9dd-3504-44c3-a75b-f6900bce492d |  | tickbox | Drainage material under pipe
boolean | eae18db0-fd88-417e-98fe-6b6e32ccc8db |  | tickbox | Levels and inverts correct
boolean | 0bbcd476-ea1b-440d-9c6f-1c58fbb8d8c5 |  | tickbox | Pipework to correct falls
checkpoint-status |  |  | checkpoint | Testing to council requirements pass (pass once inspection is completed and approved)
boolean | 06924057-5a17-4b16-844f-b1f240534b4b |  | tickbox | Councils inspection booked
boolean | a7eb349f-10f8-4ae0-bde1-f38f26969f7b |  | tickbox | Council inspection compete (attached in Council Inspection folder)
checkpoint-status |  |  | checkpoint | Consultant inspection completed & any observations closed out (Inspection attached in Consultants folder)
checklist-flat |  |  | checklist | Daily Site Report - Fitout Works: |  |  |  |  | Yes | Daily Site Report - Fitout Works | d615a008-a63c-4c2d-97c2-e0c414632fde
checkpoint-status |  |  | checkpoint | Hours Worked & Weather Conditions Recorded
text | d05f7522-1b02-45a4-90b2-1c458ce47bd8 |  | textbox | My Hours Worked (start & finish)
select | 9fa5715f-afda-4fd4-a2f7-db8fbc6409e6 |  | dropdown | Weather Conditions AM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
select | 132cf610-a61c-4f07-a489-70466f1503bd |  | dropdown | Weather Conditions PM | Fine w Light Wind, Fine w Strong Wind, Light Rain w Light Wind, Light Rain w Strong Wind, Heavy Rain w Light Wind, Heavy Rain w Strong Wind
checkpoint-status |  |  | checkpoint | Visitors to Site (Record name, company & purpose)
checkpoint-status |  |  | checkpoint | Site Instructions Issued (Any relevant site instructions issued are documented here)
checkpoint-status |  |  | checkpoint | Day Works Agreed (Any relevant Day Works issued are documented here)
checkpoint-status |  |  | checkpoint | Subcontractors on site (all recorded area, man power, name)
button | 2e8c89f3-6f2f-46c9-b26e-8e84ec00e072 |  | button | Certified Bricklayer - Area & Manpower | yes, no
text | 36764b1a-ae0e-4e54-9299-daf759a72017 |  | textbox | Area Working ( Certified Block layers)
text | 2c1c5b50-0602-47c1-9bac-35e845e5ebd1 |  | textbox | Manpower (Certified Block layers)
text | 4b3de616-9e06-4633-be2d-e9e2d675dc85 |  | textbox | Area Working ( GHD)
text | 25f90ccf-4adb-4a4c-8865-76fd2ee9bfdc |  | textbox | Manpower (GHD)
button | 570cdfe4-2fa0-4d7d-8be2-e123c1ad7209 |  | button | Ceilings Unlimited - Area & Manpower | yes, no
text | 3555a199-27c4-44fb-8667-bd514c433ad8 |  | textbox | Area working (Ceilings unlimited)
text | 913a55e1-96ff-4dec-a9bf-ef24f30f7a05 |  | textbox | Manpower (Ceilings Unlimited)
button | 62645ae8-ea2d-49ca-b935-be7248d04c15 |  | button | Zero Fire (Fire Protection) Area & Manpower | yes, no
text | 17d45812-efc5-4726-b37d-14b7a624f4a7 |  | textbox | Area Working (Zero Fire)
text | d2beef71-6e80-47a0-9c7a-03d86c09dbbe |  | textbox | Man Power (Zone)
button | 2cc244d7-ac12-44c7-969f-733bd0afb410 |  | button | Aotea - Area & Manpower | yes, no
text | c9bd31d1-e3f8-4c30-ac81-57c525b50620 |  | textbox | Area Working (Aotea)
text | aa9d26d0-6e0f-4780-bb84-b9a2ec1df39d |  | textbox | Manpower (Aotea)
button | 4a8ace9a-0276-4149-a67e-94a469ce4e89 |  | button | Tempest - Area & Manpower | yes, no
text | 1c7deeab-fb1d-42f4-8fc0-8fbe96a2afec |  | textbox | Area Working (Tempest)
text | 9b299b9a-d648-41d6-8248-507f0a0145a8 |  | textbox | Manpower (Tempest)
button | ce2c638b-3db9-4490-9d4c-05c0bac73caa |  | button | Toyle- Main structure- Area & Manpower | yes, no
text | 1edcfd77-5057-4971-b073-cb1e5923415a |  | textbox | Area Working ( Toyle)
text | ea200e78-1750-4e44-a8a8-105925c6b237 |  | textbox | Manpower (Toyle )
text | 5d9b55b4-5b2b-4c73-969f-031c0ff3ac1b |  | textbox | Area Wokking( Arid)
text | 2db7ace2-8140-40a6-9593-4cecc23db715 |  | textbox | Manpower (Arid)
button | 78761643-ea57-45d3-a1cd-41b3d5d0ca15 |  | button | Cake remedials ( Intumescent) Area & Manpower | yes, no
text | ff839275-5e04-4c56-b348-1a777c5bca2a |  | textbox | Area Working ( Cake)
text | a6cef4f0-74ad-4521-b004-c2740b90f49c |  | textbox | Manpower (Cake remedials)
button | 077d83be-f5db-4d08-b361-dfe8263db926 |  | button | Fabworx - Metalworks Area & Manpower | yes, no
text | 7727a969-ae39-4d82-ad11-c76dc5c94630 |  | textbox | Area Working ( Fabworx)
text | cf6afc36-66a1-4d6e-8407-a8aa946031fd |  | textbox | Manpower (Cake remedials)
button | cb49b666-4522-4457-94a9-f8b1dad45536 |  | button | Hawkins carpentry- Area & Manpower | yes, no
text | d3f9488c-f64a-477e-bad0-f51b9d12f7f4 |  | textbox | Area Working (Hawkins Carpentry )
text | e4dff7a0-268c-4256-94de-94abb8263996 |  | textbox | Manpower (Cake remedials)
button | dfa66770-3934-430a-b203-ac313fd23d24 |  | button | Trade - Name, Area & Manpower | yes, no
text | df6a13c6-95b0-438a-8257-1a6f849e470a |  | textbox | Company
text | 26c1aa58-dc36-46c9-8351-d472c3383338 |  | textbox | Area Working
text | 586c3a6a-e8cf-47cb-b5c9-c6582fd62751 |  | textbox | Manpower
button | 27a5fce0-4782-4aa5-80da-e44fa9603eb6 |  | button | Trade - Name, Area & Man power | yes, no
text | 97647bdf-641e-4c05-95e0-c4f5a6c341c8 |  | textbox | Company
text | 2f6c8e13-8317-4ea7-ba1a-374baaad34ea |  | textbox | Area Working
text | 947ce050-acb6-495d-aab9-d88453b86fda |  | textbox | Manpower
button | ea4c1d12-05ea-4cd5-ac3f-c22186ddf73d |  | button | Trade- Name, Area & Man power | yes,no
text | 8710ed66-a62a-487a-ab6d-b3e4905c2dcc |  | textbox | Company
text | 79e50797-e756-4ce3-afac-ff17afe3c187 |  | textbox | Area Working
text | 2a0e3afe-1920-41ea-860c-45e731c2ff45 |  | textbox | Manpower
checkpoint-status |  |  | checkpoint | Subcontractors contacted today (document name & date trade is required / conversation details)
checkpoint-status |  |  | checkpoint | Progress (quantities & location) - include photos
checkpoint-status |  |  | checkpoint | Unsatisfactory Progress - include photos (Fail if of serious concern - Pass once resolved)
checkpoint-status |  |  | checkpoint | Subcontractor/Supplier -Items delaying progress (Fail if of serious concern - Pass once resolved)
checkpoint-status |  |  | checkpoint | Design - items delaying progress
checkpoint-status |  |  | checkpoint | Disruption /Mitigation (subcontractor / design)
checklist-sectioned |  |  | checklist | Joinery & Bathrooms |  |  |  |  | Yes | TH - Joinery & Bathrooms | d65eabcd-a838-4cdd-a1b4-54962d7fe983
checkpoint-group |  |  | section | Kitchen Install QA
checkpoint-status |  |  | checkpoint | Kitchen cabinetry installation completed and correct
checkpoint-status |  |  | checkpoint | All appliances Installed and commissioned
checkpoint-status |  |  | checkpoint | Kitchen splash backs
boolean | 3b2d8283-51fe-591d-b983-463bc98bb07c |  | tickbox | Site measure
boolean | bbc0817f-7baf-59df-865e-7e636341e7e5 |  | tickbox | Install
checkpoint-group |  |  | section | Bathrooms
checkpoint-status |  |  | checkpoint | Waterproofing completed and correct
checkpoint-status |  |  | checkpoint | Under Floor Heating completed and correct
checkpoint-status |  |  | checkpoint | Floor tiles installed and acceptable
checkpoint-status |  |  | checkpoint | Grout installed and finish acceptable
checkpoint-status |  |  | checkpoint | Silicone installed and finish acceptable
checkpoint-status |  |  | checkpoint | Shower door installation completed and approved
checkpoint-status |  |  | checkpoint | Bathroom cabinetry installed checked and correct
checkpoint-status |  |  | checkpoint | Hardware second fix completed and approved
checkpoint-status |  |  | checkpoint | Shower tray QA received, reviewed and attached
checklist-sectioned |  |  | checklist | Fitout / Finishing Checklist |  |  |  |  | Yes | T1&2 Fitout (New) - Fitout / Finishing Checklist | d784ac44-5e1c-4c51-9336-38662cce211c
checkpoint-group |  |  | section | General QA
checkpoint-status |  |  | checkpoint | Floor prep completed, checked and acceptable (approval to lay flooring)
checkpoint-status |  |  | checkpoint | Timber Flooring completed & correct
checkpoint-status |  |  | checkpoint | Carpet flooring completed & correct
checkpoint-status |  |  | checkpoint | Wardrobes Install Completed, checked and approved
boolean | 347a75ed-29bc-5ccc-ba05-518d8044c15f |  | tickbox | Onsite measure
boolean | 94357d62-6867-57b7-884c-21ac73309100 |  | tickbox | Installation
checkpoint-status |  |  | checkpoint | Second fix door hardware installed and approved
checkpoint-group |  |  | section | Kitchen Install QA
checkpoint-status |  |  | checkpoint | Kitchen cabinetry installation completed and correct
checkpoint-status |  |  | checkpoint | Bench top install completed
boolean | 3382ebc3-b4e1-5e6c-a9c9-b3697afd34ff |  | tickbox | Measure
boolean | 514fe4af-838f-5b9b-b7ab-bed047d7fe46 |  | tickbox | Install
checkpoint-status |  |  | checkpoint | All appliances Installed and commissioned
boolean | 11b59397-1918-5495-b132-0f7375aceac6 |  | tickbox | Range hood
boolean | 6b776f80-16d6-53ac-a08a-e434b2a17af5 |  | tickbox | Oven
boolean | 5c292bcf-2b84-5b07-ab2c-ede0122c30a1 |  | tickbox | Fridge
boolean | 25a836ba-7e3f-5ad6-8cb4-ea7dcddfc331 |  | tickbox | Waste disposal unit
boolean | 9a0964d5-467a-5fd9-8d3d-c931aa641c67 |  | tickbox | Dishwasher
checkpoint-status |  |  | checkpoint | Kitchen splash backs
boolean | 720c4186-d145-5291-b17e-b2575249938f |  | tickbox | Site measure
boolean | 85d23537-acb6-56e2-8d4f-7cbd4a10affb |  | tickbox | Install
checkpoint-group |  |  | section | Bathrooms
checkpoint-status |  |  | checkpoint | Waterproofing completed and correct
checkpoint-status |  |  | checkpoint | Under Floor Heating completed and correct
checkpoint-status |  |  | checkpoint | Floor tiles installed and acceptable
checkpoint-status |  |  | checkpoint | Grout installed and finish acceptable
checkpoint-status |  |  | checkpoint | Silicone installed and finish acceptable
checkpoint-status |  |  | checkpoint | Shower door installation completed and approved
checkpoint-status |  |  | checkpoint | Bathroom cabinetry installed checked and correct
checkpoint-status |  |  | checkpoint | Hardware second fix completed and approved
checkpoint-status |  |  | checkpoint | Shower tray QA received, reviewed and attached
checklist-sectioned |  |  | checklist | Crane Briefing Plan Template |  |  |  |  | Yes | Crane Briefing Plan Template - QA | d8a4e46b-b746-44ca-bda7-7eded1c618d7
checkpoint-group |  |  | section | Attendance
checkpoint-status |  |  | checkpoint | Attendance Information (pass once all inputted)
text | 03c12af5-828f-5863-b78a-d94234b71edb |  | textbox | Hawkins Crane Manager
text | 8794fa54-d6e0-58dd-851b-6e921e7d56a6 |  | textbox | Crane Co-ordinator
text | e9ea4029-4c51-5232-8739-94b0ec4847dc |  | textbox | Cranage Lead
text | d87f364a-ad6b-52db-81cc-95553ef6f38f |  | textbox | Crane #1 Staff
text | df7a09c9-24e3-5a64-bb49-8bbb6d5ebe2e |  | textbox | Crane #2 Staff
text | 9f3c50f4-277f-5cbc-bf3a-a38da3fa1068 |  | textbox | Crane #3 Staff
text | c0d86301-67f8-5296-8926-42db346fb763 |  | textbox | Crane #4 Staff
checkpoint-group |  |  | section | Daily Lifting Schedule
checkpoint-status |  |  | checkpoint | Daily Lifting Schedule - Crane 1
boolean | 47cd41b7-7951-5de1-a755-6fdaca43e3a0 |  | tickbox | Shutters
boolean | e5e287ab-d169-5cb0-b380-b9542c404cb2 |  | tickbox | Precast - unislab
boolean | 0cb473f3-37cf-5b02-9e77-90b4b6324080 |  | tickbox | Precast- double t
boolean | a80d3401-2028-59b6-a8db-1daaf21c3209 |  | tickbox | Precast wall
boolean | 6723e756-83ad-541b-a1d2-421444c20585 |  | tickbox | Concrete skip
boolean | 55ebc182-614f-5bbd-8507-6b1ef5053f85 |  | tickbox | Structural steel
boolean | 7ec1976b-5fc1-5d73-9c88-97ce45c915a8 |  | tickbox | Scaffold moving
boolean | 849a192b-3f99-5678-a1cb-89a9f094b7ae |  | tickbox | Structural steel delivery
boolean | df8cf755-9f26-5ca1-83e0-51351661caa9 |  | tickbox | Precast balcony
boolean | 994271e3-7d0f-57e6-9f5d-c0478dc9dc4b |  | tickbox | Waste bins
boolean | d2886383-13c6-5440-929f-03f043d25a4b |  | tickbox | Mancage
boolean | d6b83b41-f1ef-53b1-902c-888d22cda004 |  | tickbox | SWL checked
boolean | 4bc4c57b-9552-552f-8aeb-faecd1338667 |  | tickbox | Reinforcing delivery
boolean | 7a285ec5-c9d1-53a9-a905-44e639677243 |  | tickbox | Moving reinforcing
text | a51df002-4fdf-5a73-8290-08b5d05c3369 |  | textbox | If other, specify:
checkpoint-status |  |  | checkpoint | Daily Lifting Schedule - Crane 2
boolean | e11f0787-fea7-527c-a6be-bd8f85e41cdc |  | tickbox | Shutters
boolean | f3aa1e64-9f70-5ea9-af2a-6248ae90eeaf |  | tickbox | Precast - unislab
boolean | 9519fdbb-16dd-50f3-9bb0-a173a1571288 |  | tickbox | Precast- double t
boolean | 7f4166b2-168d-56cc-9889-ac6000b735f7 |  | tickbox | Precast wall
boolean | d917c77c-2585-5410-b7cd-a8f7c590a0e9 |  | tickbox | Concrete skip
boolean | 1a07178b-4bfd-52d9-aad2-4a7f866450fe |  | tickbox | Structural steel
boolean | 51d6b5c0-cedf-56d7-a190-9c931d1964b2 |  | tickbox | Scaffold moving
boolean | 5b7761da-e96f-5331-bfb5-35a4222f67a5 |  | tickbox | Structural steel delivery
boolean | 418576e6-339a-51b9-9eb5-e19504f80d5f |  | tickbox | Precast balcony
boolean | f140c8c9-d1e9-5f77-9b7a-2ef64e86ad89 |  | tickbox | Waste bins
boolean | 10d42f5f-1a7c-58aa-a754-f902452f2cec |  | tickbox | Mancage
boolean | eb1fb19d-9751-514e-98a1-5102d5869f0d |  | tickbox | SWL checked
boolean | 043a4bc4-87b4-5553-b691-6beae67736e0 |  | tickbox | Reinforcing delivery
boolean | dac1e9eb-dce6-5951-acc5-45955b7bf671 |  | tickbox | Moving reinforcing
text | 0ee316ce-452f-5890-874d-ff62b185a0a5 |  | textbox | If other, specify:
checkpoint-status |  |  | checkpoint | Daily Lifting Schedule - Crane 3
boolean | a2ed228e-b76a-54a3-960c-d1a5fe62b43e |  | tickbox | Shutters
boolean | 20e8a8dc-605d-5450-abab-5736a1b25072 |  | tickbox | Precast - unislab
boolean | d7a0c82d-fb01-5f20-8607-c65da270dce7 |  | tickbox | Precast- double t
boolean | 4cf20d59-8e45-56f1-915b-c455a54d445d |  | tickbox | Precast wall
boolean | d1501e5d-f518-590f-bcd0-1eb9605f2409 |  | tickbox | Concrete skip
boolean | 3a5c4fb8-9eec-57a6-853b-e6a1cca84a89 |  | tickbox | Structural steel
boolean | 11d4fbdd-2d45-58af-b0d5-ae8317753c03 |  | tickbox | Scaffold moving
boolean | 9e06c538-5646-5f6f-bee8-b58b5fa7c91b |  | tickbox | Structural steel delivery
boolean | fb400e4a-e2d5-5a18-a5c2-9d4e6461f6c2 |  | tickbox | Precast balcony
boolean | 26690313-91b9-536f-a15b-e65942c4cfb1 |  | tickbox | Waste bins
boolean | 4ddd05d1-7f52-50ef-ab87-500147cf52f6 |  | tickbox | Mancage
boolean | d89265b6-2d60-5f04-a295-4c3b34053580 |  | tickbox | SWL checked
boolean | 17e56970-3cc9-51a7-9b62-dfb0a60df1d4 |  | tickbox | Reinforcing delivery
boolean | 261c72ec-8a6e-56a7-a018-b420312c1dd8 |  | tickbox | Moving reinforcing
text | 99a032af-5e67-5405-8d76-59994b622890 |  | textbox | If other, specify:
checkpoint-status |  |  | checkpoint | Daily Lifting Schedule - Crane 4
boolean | e46d7d7d-ac4b-5f88-8637-9caea4f9fcdd |  | tickbox | Shutters
boolean | fc71f707-f275-590a-b516-d2fc499d743b |  | tickbox | Precast - unislab
boolean | 7d83c57f-e3fe-5803-a595-a61e696d50e9 |  | tickbox | Precast- double t
boolean | 23a60213-9e3a-5ccd-afb9-9c55b8899e44 |  | tickbox | Precast wall
boolean | 37dad073-57ff-530d-8f5f-41e78032bb4f |  | tickbox | Concrete skip
boolean | 8c56c31b-a0e7-560e-9bcc-791617b94a83 |  | tickbox | Structural steel
boolean | c5e54e3d-0e43-592f-b19a-7708ed89c15b |  | tickbox | Scaffold moving
boolean | 2d1359bf-84e6-52ad-826d-ff14b20097c8 |  | tickbox | Structural steel delivery
boolean | 5328424c-25a5-5589-9b39-c24b82a4c2a5 |  | tickbox | Precast balcony
boolean | 8f57f925-33bc-5ed6-851b-e3f9c38da610 |  | tickbox | Waste bins
boolean | 2b8163ab-9826-5932-b79b-2faf9b307872 |  | tickbox | Mancage
boolean | 1cbfe289-6516-5e93-aa40-7870cecfb626 |  | tickbox | SWL checked
boolean | 396ab2ca-e5ff-5ae5-96e1-28ef1b365101 |  | tickbox | Reinforcing delivery
boolean | 55845984-bb9a-5f52-b601-dec306ddb2db |  | tickbox | Moving reinforcing
text | 9cd379df-56dd-5c90-979e-ec2b0c0a539b |  | textbox | If other, specify:
checkpoint-status |  |  | checkpoint | Photos/additional comments
checkpoint-status |  |  | checkpoint | Radius chart or lift plan attached (pass once attached)
checkpoint-group |  |  | section | Health & Safety Controls For Lifting
checkpoint-status |  |  | checkpoint | Crane operators/dogman ticketed
checkpoint-status |  |  | checkpoint | Crane/equipment have current certificate
checkpoint-status |  |  | checkpoint | Anticlash agreement is in place
checkpoint-status |  |  | checkpoint | Plan in place to avoid lifting over people
checkpoint-status |  |  | checkpoint | Relevant SWMS signed on by workers e.g. crane ops, unloading, mancage
checkpoint-status |  |  | checkpoint | Key hazards/risks/controls discussed today
text | abe75436-e5a5-510d-8653-c3c657d38bf7 |  | textbox | Hazard One:
text | d10df7e9-f0a6-5ee1-904d-8097540bbc39 |  | textbox | Hazard Two:
text | b4049c3a-9263-5980-862c-9ceb41d7dcc1 |  | textbox | Hazard Three:
text | ab449ab3-eb02-5463-906e-f3ae89daffd3 |  | textbox | Hazard Four:
checkpoint-group |  |  | section | Weather Conditions
checkpoint-status |  |  | checkpoint | Conditions (pass once recorded)
boolean | f3c5c137-4396-570c-b0f8-7ccb60e464e0 |  | tickbox | Rain forecast
boolean | e2f43b8f-b5cd-5e72-ba3a-806c34e6c54a |  | tickbox | Wind forecast
text | 8770835b-3cc2-5758-b070-b290bbda951a |  | textbox | If other, specify (attach snip of today's forecast):
checkpoint-group |  |  | section | Lifting Gear/Hazard Check For Today
checkpoint-status |  |  | checkpoint | Lifting Gear/Hazard Check complete
boolean | 1186fdf9-1b79-55aa-be12-5c922d142f12 |  | tickbox | Taglines ok
boolean | 7ea06f9c-ca07-56c4-8a31-967675de92ae |  | tickbox | Lifting gear ok
boolean | d639f1b5-22f9-5c28-b330-b757b898d3ab |  | tickbox | Crane operation ok
boolean | 739a9be2-65a0-5f07-bd62-30a8a1d91b48 |  | tickbox | Anti-clash working ok
boolean | e2a18a47-e23f-5141-b8b2-d5dd0b18fb5a |  | tickbox | Hook camera working ok
boolean | cb8395cc-fd06-56e7-a92c-68bd6ee8d429 |  | tickbox | Rigging methodology discussed
boolean | 245f3384-f8f1-50b5-9a81-1b6b7fb982a8 |  | tickbox | Operator quick check complete
boolean | 3faa444d-9dd5-5f9d-aad5-99105d7c05a4 |  | tickbox | Radio working ok
boolean | c27b4833-f300-5d03-ae4c-9b9fc7e66392 |  | tickbox | Mancage/workbox ok
boolean | df97758d-990f-5251-a82c-5304a3b6515a |  | tickbox | Material lifting devices & attachments ok e.g. concrete skips
checkpoint-status |  |  | checkpoint | Photos/additional comments
checkpoint-group |  |  | section | Complex Lifts Today
checkpoint-status |  |  | checkpoint | Complex Lifts Today (Pass once relevant complex lifts are selected and any planning documents (e.g. lift plans, SWMS, temp work checks) completed by engineer are done - to be attached)
boolean | 2ff7a2a6-f979-5df9-a5f9-0d8345def188 |  | tickbox | Irregular loads or loads with unusual weight distribution (centre of gravity)
boolean | 6370ace2-1006-57c5-b178-b3fd813ddd23 |  | tickbox | Using one or more cranes (winches)
boolean | 35fd933a-9806-5151-b856-3203faf1b18e |  | tickbox | A lift with less than the recommended multicrane safety factors
boolean | 0764c48d-c5be-53ec-b6ab-ef4dcf8d9964 |  | tickbox | A lift out of view of the crane operator
boolean | a5c8991a-5d7c-5f39-96db-bca92fb9ae17 |  | tickbox | Technically difficult rigging e.g. liftings involving concrete panels and tilt up
boolean | 39a7eeb2-9648-5616-9d49-ed85a125b452 |  | tickbox | Lifting personnel
boolean | 93b1869f-1b29-5b52-8a8c-9d788f79f688 |  | tickbox | Lifting hazardous materials
boolean | 35f77e34-10fc-5636-b1ea-3795fc1c2644 |  | tickbox | Lifting submerged loads
boolean | cd8876c6-72da-5b49-a96e-8514cd406d70 |  | tickbox | Lift with no or partial outrigger
boolean | ef36b890-9552-54d9-b8aa-3874c35a9083 |  | tickbox | Lifting on rubber
boolean | 6ffbb94e-01bc-523c-a255-a9eda04813dc |  | tickbox | Lift weights if required
boolean | f7df975a-6cde-50e4-b241-ed8347895340 |  | tickbox | Lifts within MAD of electrical power lines
boolean | 5871c393-83e7-5158-a0c7-8f6fcb621716 |  | tickbox | Lifts on ground with geotechnical or underground service risks
boolean | b4fe5f93-52d9-5448-a051-4e4cfe44dbb5 |  | tickbox | Or any lift the crane operator feels should be classed as such
checkpoint-status |  |  | checkpoint | Project Manager signoff – attach signature
checklist-flat |  |  | checklist | Progress Update |  |  |  |  | Yes | Progress Update | d93b50b6-4538-4c33-88b6-bc7b1a150821
checkpoint-status |  |  | checkpoint | Progress report/update (add report or photos and notes as required)
checklist-flat |  |  | checklist | E-Span Cladding |  |  |  |  | Yes | Facade - E-Span Cladding Checklist | dbaa936e-4c1e-44c4-97d3-b4190be0963c
checkpoint-status |  |  | checkpoint | Product checked and correct as per specification
checkpoint-status |  |  | checkpoint | All prestart checks completed and approval given to install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint-status |  |  | checkpoint | All roofing elements completed, checked and approved as per specifications
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | All Consultant sign off completed
checklist-sectioned |  |  | checklist | Exterior Balconies & Tiling |  |  |  |  | Yes | Exterior Balconies & Tiling (long version) | dc054d4a-e557-417a-b5d1-89fac7b4911d
checkpoint-group |  |  | section | Substrate Check
checkpoint-status |  |  | checkpoint | Adequate drying time has elapsed
checkpoint-status |  |  | checkpoint | Substrate, finish/fall correct as per design and perimeter angle installed
checkpoint-status |  |  | checkpoint | General photos and observations during installation
checkpoint-status |  |  | checkpoint | Approval to install tanking - Consultant & Council inspections carried out
checkpoint-group |  |  | section | Tanking Installation
checkpoint-status |  |  | checkpoint | Product checked and correct as per specification
checkpoint-status |  |  | checkpoint | All prestart checks completed and approval given to install
checkpoint-status |  |  | checkpoint | Matt installed as per product specification
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint-status |  |  | checkpoint | Tanking to area completed, checked and approved as per specifications
checkpoint-status |  |  | checkpoint | Initial testing complete
checkpoint-status |  |  | checkpoint | Any remedials completed
checkpoint-status |  |  | checkpoint | Request Signoff from Facade engineer
holdpoint |  |  | signoff | Request Signoff from Facade engineer
checkpoint-status |  |  | checkpoint | Request signoff from architect
holdpoint |  |  | signoff | Request signoff from architect
checkpoint-status |  |  | checkpoint | Request signoff from Manufacturer
holdpoint |  |  | signoff | Request signoff from Manufacturer
checkpoint-status |  |  | checkpoint | Area protected
checkpoint-group |  |  | section | Tiling
checkpoint-status |  |  | checkpoint | Correct jacks being used as per specification
checkpoint-status |  |  | checkpoint | Correct tiles ( type/colour ) confirmed
checkpoint-status |  |  | checkpoint | All tiles have been installed and deck finished
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Architects inspection complete
checklist-flat |  |  | checklist | Painting Checklist |  |  |  |  | Yes | T1&2 Fitout (New) - Painting Checklist | dcb2a5d0-1e29-420e-9f04-d8a20cfcf2a5
checkpoint-status |  |  | checkpoint | Area / substrates acceptable
checkpoint-status |  |  | checkpoint | Paint specifications and color checked & correct to specification
checkpoint-status |  |  | checkpoint | First coat/ sealant coat completed
checkpoint-status |  |  | checkpoint | Light inspection completed and approved to continue
checkpoint-status |  |  | checkpoint | General comments and photos of additional paint application
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Final coat completed, no overpainting, finish acceptable as per specification
checklist-sectioned |  |  | checklist | Doors /Finishing Lines & Trims Checklist |  |  |  |  | Yes | TH - Doors /Finishing Lines & Trims Checklist (V2) | dd8e7a6a-d8d7-449d-a345-0e6b147034e1
checkpoint-group |  |  | section | Finishing Lines Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Finishing lines spot checks complete
boolean | 5282fe79-46db-5a83-9703-09d1778d59cb |  | tickbox | Correct product and size
boolean | ed6548aa-e286-5bd6-9234-166d85780c88 |  | tickbox | Correct fixings and jointing
checkpoint-group |  |  | section | Door Install Checklist
checkpoint-status |  |  | checkpoint | All prestart requirements completed and acceptable, approval given to commence
checkpoint-status |  |  | checkpoint | Door fitted correctly as per specification (product, size, location, level, swing, fixings etc)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Door install completed, checked, correct and approved
checklist-flat |  |  | checklist | Mechanical Services Ceiling First Fix |  |  |  |  | Yes | Mechanical Services Ceiling First Fix - QA | df21211f-1818-4451-83d0-f19e039fd5aa
checkpoint-status |  |  | checkpoint | Reference Drawings
text | f298f381-93fb-45c2-8f8e-76ad5c00df85 |  | textbox | add numbers and revisions
checkpoint-status |  |  | checkpoint | Mechanical ceiling QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First fix spot checks with subcontractor - tick when all below spot checks are complete
boolean | 1720093b-25db-4bfc-8cc2-142f02724d1e |  | tickbox | Pipes checked for damage/corrosion/Scale
boolean | 7937e2b1-1298-40e9-8cbb-07a2ecb5ed49 |  | tickbox | Ducts size correct and type
boolean | efe9f102-302d-45ab-9ae0-2e8203f1ec8c |  | tickbox | Duct supports , anchors and hangers/Clips installed correctly including seismic
boolean | 1c147387-676c-474a-9f71-e375a3633c16 |  | tickbox | Thermal ducts and pipes insulated and labelled
boolean | ea0da281-dc50-49d5-8d7e-9a30c22d0ed7 |  | tickbox | Heights of pipework checked ( above ceiling)
boolean | 62e30aea-daac-485c-95b9-a46bd84dbdb6 |  | tickbox | All labelling installed
boolean | 8118c0d9-170c-4e70-8b84-a2ec430924b9 |  | tickbox | All wiring labeled/identified
boolean | 41beb3c3-cc36-4f2e-a35d-23a514ef85b4 |  | tickbox | All ducts cleaned/and ends capped where needed
boolean | 2b472ffe-b341-45ad-a991-1521ba9ccff2 |  | tickbox | Cables are completed and with proper support
boolean | d9d63469-c926-4536-941f-551998f2715f |  | tickbox | All equipment , valves and fire dampers, air outlets louvres, grilles and dampers are in place and accessible where required
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Service Engineers Beca - Inspection requested
checkpoint-status |  |  | checkpoint | All ends covered/protected to reduce debris
checkpoint-status |  |  | checkpoint | Any onsite changes documented(add a copy)
checklist-sectioned |  |  | checklist | Structural /Framing & First Fix Checklist |  |  |  |  | Yes | TH - Structural /Framing & First Fix Checklist | df29b307-8146-48ad-b0ce-2501cfbec7d6
checkpoint-group |  |  | section | Interior Framing Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All timber framing completed correctly within tolerance in respective area ( sign off when all Complete)
boolean | f3dbf87c-8378-5efc-8be3-0968dcd636b7 |  | tickbox | Spot checks on frames for square
boolean | 6dd7d97e-fb5b-59aa-824d-92766936d792 |  | tickbox | Spot checks on frame level
boolean | 91728813-30ba-546c-8f15-f60969396fd3 |  | tickbox | Fixings are correct including seismic requirements
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Plumbing First Fix Walls & Ceilings
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Plumbing install First fix complete - checks done based on current drawings ( attach and pass once all complete)
text | ef17495e-f8d0-5f7b-a207-dd73fa0445fe |  | textbox | Confirm drawing and revision number
boolean | 2aa9faf6-d6d5-50e6-bdb7-5467186e10eb |  | tickbox | Pipes size & type
boolean | 66ff49d7-f585-5680-888f-addb8b9bb531 |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | 8c86406c-b8d2-5513-a9ab-d0ae9bbd576c |  | tickbox | Correct number of outlets
boolean | 95044678-c55b-550f-956d-7b2de5662479 |  | tickbox | Any valves/vents installed
boolean | 03097875-083c-5f1e-a2d7-2893b63f136f |  | tickbox | Pipework protected at holes and notches
boolean | 12153973-c216-5280-a980-ec3615e0ddf6 |  | tickbox | Heights & positions of pipeworks checked ( above ceiling)
boolean | fba733bf-4734-521e-ad77-f4e3e5683b1d |  | tickbox | All vents installed
boolean | 57c5a708-e355-56c8-aae0-92bdfbb83315 |  | tickbox | All lagging is inplace
boolean | 45b39986-3d6d-5f4d-8d23-8cb4f21cd782 |  | tickbox | All labelling installed for pipework
boolean | 602789ed-5864-5244-bf1c-0bc8b8a63331 |  | tickbox | All required noggs have been added
boolean | 0914d874-83b1-5763-b0fe-db826a2a7a16 |  | tickbox | all pipes cleaned/cleared before testing
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-status |  |  | checkpoint | Engineer has signed off seismic restraints
checkpoint-status |  |  | checkpoint | Protection Provided for floor wastes and ends of unfinished pipes
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Fire Protection Walls & Ceilings (sprinklers & Alarms) First Fix
checkpoint-no-status |  |  | checkpoint | Reference Drawings
text | 8154c4c0-d462-5886-a3e2-ab4332a0862d |  | textbox | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
boolean | 7b64b047-197b-55b1-8ee5-0e059d289390 |  | tickbox | Pipes checked for damage/corrosion/Scale
boolean | 902ee4f6-a287-5643-8a6c-ee4b10dd8fa6 |  | tickbox | Pipes size correct and type
boolean | b971e3f4-da9a-5b50-b7a5-c01b2a57e90f |  | tickbox | Pipe supports , anchors and hangers/Clips installed correctly including seismic
boolean | 6610a888-8fb0-5a26-acdb-894ca67a7aa9 |  | tickbox | Correct number of outlets/droppers for sprinklers
boolean | 962794e8-1a16-5386-a849-713bc1c5cb63 |  | tickbox | Heights of pipeworks checked ( above ceiling)
boolean | a9e30e92-864b-5f79-8c6c-2e277290cd4b |  | tickbox | Any lagging required is in place
boolean | 20c946c3-648d-5dc6-8105-f5c0ae165801 |  | tickbox | All labelling installed for pipework
boolean | d4e1019c-70ca-5ce6-9849-7c384857cb70 |  | tickbox | Cables are completed and with proper support
boolean | ef2a9def-2bea-5930-a9bb-21d773a805d2 |  | tickbox | All required noggs have been added
boolean | f47dfe35-3bea-5bda-ad50-ec120862e182 |  | tickbox | All wiring labelled/identified
boolean | 2bc32a13-dc3b-58af-afcf-792972a54348 |  | tickbox | All pipes cleaned/cleared before testing
boolean | 12d095a0-0f14-5e74-907f-62c2f54a12f9 |  | tickbox | Correct number of connections for dectors
boolean | 17dbe24b-507a-56a3-bc6f-f3d5ad7c2707 |  | tickbox | All MCP at correct heights & positions
checkpoint-status |  |  | checkpoint | All required 1st fix testing complete
checkpoint-status |  |  | checkpoint | FPIS inspection sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Protection Provided for floor wastes and ends of unfinished pipes
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Mechanical Services Wall & Ceilings First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
text | ed389b5c-6270-5b7e-8de9-9ebef2cac1c1 |  | textbox | Reference drawings ( add drawing numbers & revisions)
boolean | 45563d7b-d38b-52ba-9a49-e755be32932c |  | tickbox | Ducts checked for damage/corrosion etc
boolean | 9bfc955c-8237-523f-92cb-f35c3968d650 |  | tickbox | Ducts size correct and type
boolean | 69f21312-c195-5473-9a95-dfbc9b30e51a |  | tickbox | Duct supports , anchors and hangers/Clips installed correctly including seismic
boolean | 77e177df-60ef-5912-9a13-555a0c4d9397 |  | tickbox | Ducts And pipes insulated and labelled
boolean | 95f0e95f-6165-5d1e-b5a0-b59c19a82fd5 |  | tickbox | Heights of pipeworks checked ( above ceiling)
boolean | 2596e23a-7a6f-5c5c-972e-7d7225f67d09 |  | tickbox | All required labelled/identification done
boolean | 520e64ad-1526-5d9d-8407-9eea1d7acab2 |  | tickbox | all ducts cleaned/and ends capped where needed
boolean | d4846604-4eac-500a-9ef3-ad5e14f520b0 |  | tickbox | Cables are completed and with proper support
boolean | 0ac09dc0-bc27-513c-b7b0-915bc5c11ea5 |  | tickbox | All equipment , valves and fire dampers, air outlets louvres,grilles and dampers are in place and accessible where required
boolean | 7463b17d-862b-5978-92ba-d0c06c633a88 |  | tickbox | All required noggs have been added
boolean | 413461e1-b166-5169-8628-998ba74d4cf3 |  | tickbox | All required first fix testing complete
checkpoint-status |  |  | checkpoint | council signoff
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Protection of all ends & Cleanup Done
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Electrical Wall & Ceiling First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
text | 88d09a3d-72b3-575a-ba72-32cf7653e9fd |  | textbox | Add drawing numbers and revision
boolean | 2c494900-ddde-5df3-bebc-cd31a2a9dc56 |  | tickbox | cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | cc7a3348-a67f-5b38-bb71-2139c05f04c2 |  | tickbox | distribution boards in correct place
boolean | 1e3eea4d-a8ff-5a72-b783-af98e890a59d |  | tickbox | All outlets and switches at the correct position & height
boolean | 596da8dc-7b63-56e7-8851-209ce28e8b3f |  | tickbox | Wiring for ceiling lights in correct position
boolean | f9f1c023-2d5f-5b83-9fba-a601ebdfddd5 |  | tickbox | Correct number of ceiling lights installed
boolean | 09873614-8f0a-58e7-8962-bc421578d4fd |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 29d45510-57de-5734-8adf-0be9cabda9e0 |  | tickbox | Power supplies for roller doors, HWC,Sliding doors,fire ,securty etc installed in correct place
boolean | 1728323e-70dc-535d-9a86-b05cf870990d |  | tickbox | All wiring labelled/identified
boolean | d08c888b-34f1-5711-8897-b9345cba22ea |  | tickbox | all earthing and cables installed
boolean | bd96f76e-6383-51af-af38-322140768480 |  | tickbox | Cables are installed and with proper support
boolean | c6e98d8b-a196-5cdb-b6ab-293364c2a1ec |  | tickbox | All required additional noggs placed in framing
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Protection /Cleanup Done
checkpoint-status |  |  | checkpoint | any onsite changes documented
checkpoint-group |  |  | section | Data/Security Wall & Ceiling First Fix
checkpoint-status |  |  | checkpoint | Wall framing setout correct and signed off
boolean | ceb9613b-8130-52e7-bed8-c645aea39557 |  | tickbox | Setout/straightness checked
boolean | b3e80f15-707b-59cf-8463-a486851daf9e |  | tickbox | All required additional noggs placed in framing
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
boolean | 5723e144-6a9c-5093-8ef5-4e6f13099f97 |  | tickbox | cable tray and catenary wires supports located in the correct location and secured correctly including seismic restraint
boolean | 6c69600b-7e86-5dc2-bed6-6675642149b7 |  | tickbox | distribution boards in correct place
boolean | a70be1e2-513e-56f7-b137-1a1dbde71a24 |  | tickbox | All outlets and switches at the correct position & height
boolean | cd00cdac-91d3-59a9-8e6b-8e27e636f753 |  | tickbox | Wiring for ceiling lights in correct position
boolean | 23a62006-666d-5d32-884c-c2c7a0e99a79 |  | tickbox | Correct number of ceiling lights installed
boolean | f776de28-5e64-5138-b60c-5e20e530a2b9 |  | tickbox | Heights of wiring checked ( above ceiling)
boolean | 7feac31f-cd15-5ef3-b306-28bea97b0ae7 |  | tickbox | All required additional noggs placed in framing
boolean | 52f5f054-bec5-5d36-acd6-a7416279025d |  | tickbox | All wiring labelled/identified
boolean | 7cd85736-1a27-5769-9243-49a402721be9 |  | tickbox | all earthing and cables installed
boolean | c6256c31-15bd-5f47-86f6-bac74cf394fb |  | tickbox | Cables are installed and with proper support
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Beca sign off
checkpoint-status |  |  | checkpoint | Protection /Cleanup Done
checkpoint-status |  |  | checkpoint | Any onsite changes documented
checkpoint-group |  |  | section | Passive Fire- Walls & Ceilings Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached
checkpoint-status |  |  | checkpoint | All Passive fire elements completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Map for Check photos
checkpoint-status |  |  | checkpoint | Passive Fire Area 1 - hawkins check photos
checkpoint-status |  |  | checkpoint | Passive Fire Area 2 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 3 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 5 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 6 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 7 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 8 - hawkins check
checkpoint-status |  |  | checkpoint | Passive Fire Area 9 - hawkins check
checkpoint-status |  |  | checkpoint | passive Fire Area 10 - hawkins check
checkpoint-status |  |  | checkpoint | Third party review complete
checkpoint-status |  |  | checkpoint | fire consultant review
checkpoint-status |  |  | checkpoint | council have inspected
checkpoint-group |  |  | section | Insulation Checklist Prior to Lining
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Insulation pre lining works completed, checked & approved
boolean | 3c69e851-a7b6-53fc-955c-5271cbf05c7e |  | tickbox | correct product & R value as per specification
boolean | c29b58e2-b558-54d8-b435-fd300142a32d |  | tickbox | Fitting correctly/Snug
checkpoint-group |  |  | section | Preline Inspection Checklist
checkpoint-status |  |  | checkpoint | All above preline elements checked, correct & approval to line
boolean | 381c6ece-48de-526d-a0ac-7494aca62717 |  | tickbox | Council inspections carried out & attached in council folder
checkpoint-group |  |  | section | Rondo Ceiling Batten Installation
checkpoint-status |  |  | checkpoint | Service markout completed, checked and acceptable (clashes considered)
checkpoint-status |  |  | checkpoint | Ceiling Height confirmed
checkpoint-status |  |  | checkpoint | Appropriate fixings used and installed as per required specification
checkpoint-status |  |  | checkpoint | Appropriate spacings for respective grid elements
checkpoint-status |  |  | checkpoint | Battens Level
checkpoint-status |  |  | checkpoint | Perimeter channel/angle installed correctly
checkpoint-status |  |  | checkpoint | All strong backs installed where required to meet specification
checkpoint-status |  |  | checkpoint | All ceiling grid completed in respective area to required specification (Attach photograph of respective completed battens)
checklist-sectioned |  |  | checklist | Exterior Cladding(Terracotta) |  |  |  |  | Yes | Exterior Cladding(Terracotta) | e39b7b92-9945-4737-9066-8012ca303008
checkpoint-group |  |  | section | Cavity Rails & Fixings
checkpoint-status |  |  | checkpoint | Product checked and correct as per specification
boolean | bf12fbe3-cda3-5659-a70f-03b7a309a2fe |  | tickbox | All pre start checks completed and approval given to install
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Rails/Fixing installed correctly
checkpoint-status |  |  | checkpoint | Critical lines checklist completed
text | 313d7749-1216-5346-a232-39522a50d7c4 |  | textbox | Critical lines numbers, location & elevation
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
holdpoint |  |  | signoff | Request Inspection by Facade engineer/ Resonart
checkpoint-status |  |  | checkpoint | Inspections from Facade engineer /resonart
boolean | 514886f3-7903-5ce6-bc9c-b6fde905eb41 |  | tickbox | Facade engineer remedials complete and signed off
boolean | aa0b9a24-a918-54f6-90da-21785cf671fb |  | tickbox | NBK engineer remedials complete and signed off
checkpoint-group |  |  | section | Terracotta Tiles
checkpoint-status |  |  | checkpoint | Product checked and correct as per specification
checkpoint-status |  |  | checkpoint | Rails/Fixing completed and signed off for tile installation
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Critical lines checklist completed
text | 66d07b27-edcb-5bf2-9a6c-d1160046d4da |  | textbox | Critical lines numbers, location & elevation
checkpoint-status |  |  | checkpoint | Relevant Services considered, checked and approved where applicable
holdpoint |  |  | signoff | Request sign off architect/Facade engineer/ Resonart?
checkpoint-group |  |  | section | Flashings
checkpoint-status |  |  | checkpoint | Cavity battens installed and signed off
boolean | 12b0175b-57aa-5812-9bfa-430a168d9106 |  | tickbox | Correct material ordered
boolean | fe66800b-18a4-57e5-945f-0442cdbf1943 |  | tickbox | Arrived onsite and protected
checkpoint-status |  |  | checkpoint | Critical lines checklist completed
text | 02ce5edf-d3dd-56d3-8103-4c4bbc0463ad |  | textbox | Critical lines numbers, location & elevation
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Spot check with Subcontractor -Installed in correct place
holdpoint |  |  | signoff | Request Inspection by Facade engineer/ Architect
checkpoint-status |  |  | checkpoint | Inspections by Facade engineer /architect
boolean | 2e794dad-0373-5cd2-8c73-b9de25e59492 |  | tickbox | Facade engineer remedials complete and signed off
boolean | e3de996b-ffe6-5ba5-a465-d2d7ff698419 |  | tickbox | NBK engineer remedials complete and signed off
checklist-flat |  |  | checklist | Detailed Excavation - |  |  |  |  | Yes | Detailed Excavation Checklist - QA | e596d737-8b34-4423-acff-2f81dd65b779
checkpoint-status |  |  | checkpoint | Drawing details
text | 11d41c68-18b0-4c59-a9c1-91c91640c829 |  | textbox | Drawing Reference:
checkpoint-status |  |  | checkpoint | General Photos / Comments / Observations during excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
checkpoint-status |  |  | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
checkpoint-status |  |  | checkpoint | Excess Material Cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
holdpoint |  |  | signoff | Request signoff
checklist-flat |  |  | checklist | Final Tanking Sign Off |  |  |  |  | Yes | Final Tanking Sign Off | e74e69b1-7569-4c9f-9549-583d01eea96a
checkpoint-status |  |  | checkpoint | Final testing completed
checkpoint-status |  |  | checkpoint | All remedial completed
checkpoint-status |  |  | checkpoint | Final inspection completed by facade engineer
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Final inspection completed by Viking
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Final inspection completed by Architect
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Underground Services Install - Plumbing |  |  |  |  | Yes | Underground Services Install Checklist- Plumbing - QA | e94c6905-d2bd-413e-92f6-990b62be37fe
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | 19b38f63-f720-426f-b1fb-8d1e21197184 |  | textbox | Subcontractor:
text | 4946cb3a-3032-403c-b550-30878340c967 |  | textbox | Drawing Reference:
checkpoint-status |  |  | checkpoint | Plumbing Works complete
boolean | f6ed7b9a-7da7-41ef-a3b0-29f3e9bbe44a |  | tickbox | Pipes cut clean and square
boolean | 9832bc1f-d95c-4504-8f68-716549a8ae6e |  | tickbox | Located in the correct location
boolean | 3f025007-43da-43d2-8558-5729e124066c |  | tickbox | Pipework protected where required
boolean | dd4fa789-5fe5-4eee-8a13-22d677fa440b |  | tickbox | Drainage material under pipe
boolean | d6da2ac1-6502-4202-a67b-4bb4ed2e3308 |  | tickbox | Levels and inverts correct
boolean | b3a0b870-0e39-4c78-bccd-f1a36474cd85 |  | tickbox | Pipework to correct falls
checkpoint-status |  |  | checkpoint | Testing to council requirements pass (pass once inspection is completed and approved)
boolean | 47cdb491-7a42-47d1-adb6-bb2438634b37 |  | tickbox | Councils inspection booked
boolean | f3638540-dcfb-46ec-9848-0f61612242f1 |  | tickbox | Council inspection compete (attached in Council Inspection folder)
checkpoint-status |  |  | checkpoint | Consultant inspection completed & any observations closed out (Inspection attached in Consultants folder)
checklist-flat |  |  | checklist | Intumescent Painting V3 |  |  |  |  | Yes | Intumescent Painting V3 - QA | e9be4f72-d47b-4249-8a2f-23cb7dc71ffc
checkpoint-status |  |  | checkpoint | Location: Zone/Grids( add picture of mark-up)
checkpoint-status |  |  | checkpoint | Trades QA received, attached
checkpoint-status |  |  | checkpoint | Hawkins General Inspection
checkpoint-status |  |  | checkpoint | Manufacturer spot check
boolean | 80684fe3-1b21-4552-912e-de3f7a43c0ab |  | tickbox | Report received ( copy attached)
boolean | 3a6d21a7-cd73-4168-95fd-0e3861994a0e |  | tickbox | Remedials completed
holdpoint |  |  | signoff | Consultant Inspection requested
checkpoint-status |  |  | checkpoint | Consultant Signoff ( pass once below complete)
boolean | 044b284b-3b30-4d65-9f12-cc24b09f470c |  | tickbox | Consultant inspection complete
boolean | c426eec6-bbbd-4c74-843c-36e64a76d483 |  | tickbox | Report received ( copy attached)
boolean | 29d67a7d-2c92-4f0f-9118-c1effa488d87 |  | tickbox | Remedials competed and signed off
checklist-sectioned |  |  | checklist | P- Door/Finishing Line & Trims Checklist |  |  |  |  | Yes | P- Door/Finishing Line & Trims Checklist | ea7b624a-96c0-4617-8d19-f07bff6a85a4
checkpoint-group |  |  | section | Finishing Lines Checklist
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Finishing lines spot checks complete
boolean | 219b0b90-4b66-589f-b475-f8e7fba1c4c1 |  | tickbox | Correct product and size
boolean | b40dd536-a039-59ba-9e6c-dc0cb9101bc6 |  | tickbox | Correct fixings and jointing
checkpoint-group |  |  | section | Door Install Checklist
checkpoint-status |  |  | checkpoint | All prestart requirements completed and acceptable, approval given to commence
checkpoint-status |  |  | checkpoint | Door fitted correctly as per specification (product, size, location, level, swing, fixings etc.)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Door install completed, checked, correct and approved
checkpoint-status |  |  | checkpoint | Door Hardware installed
checkpoint-group |  |  | section | Painting Checklist
checkpoint-status |  |  | checkpoint | Area / substrates acceptable
checkpoint-status |  |  | checkpoint | Paint specifications and color checked & correct to specification
checkpoint-status |  |  | checkpoint | First coat/ sealant coat completed
checkpoint-status |  |  | checkpoint | Light inspection completed and approved to continue
checkpoint-status |  |  | checkpoint | General comments and photos of additional paint application
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Final coat completed, no overpainting, finish acceptable as per specification
checklist-sectioned |  |  | checklist | TRADES - |  |  |  |  | Yes | Trades Pre-Commencement Checklist (V2) | eb2a0b66-010f-40de-bf31-a91903be2018
checkpoint-group |  |  | section | Prestart Checks - Health & Safety
checkpoint-status |  |  | checkpoint | Company H&S Policy (Completed and Attached)
checkpoint-status |  |  | checkpoint | Site Specific Safety Plan (SSSP) - (Completed and Attached)
checkpoint-status |  |  | checkpoint | Worksafe NZ Notification (Completed and Attached)
checkpoint-status |  |  | checkpoint | Any Additional Prestart H&S Documents (Completed and Attached)
checkpoint-group |  |  | section | Prestart Checks - Quality Assurance
checkpoint-status |  |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Trade Setup on Conqa & Hawkins Given Review Access
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa, reviewed and Hawkins approved
checkpoint-status |  |  | checkpoint | Matrix/Insights Setup, Reviewed and Approved
checkpoint-status |  |  | checkpoint | Review Access Granted to any other Relevant Parties
checklist-sectioned |  |  | checklist | Balustrades |  |  |  |  | Yes | Balustrades | eda0dda1-f3dd-4038-be36-b8f71c5aa30b
checkpoint-group |  |  | section | Metro Glazed Balustrades
checkpoint-status |  |  | checkpoint | Waterproofing installed and signed off
checkpoint-status |  |  | checkpoint | Glazed balustrades complete
boolean | 508f810c-88a1-5417-9d53-2ce613de521e |  | tickbox | channels fixed correctly
boolean | 09471bca-a09d-555d-b0bf-0d9fe761ed15 |  | tickbox | Glass installed
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Inspected by Architect
checkpoint-group |  |  | section | Fabworx Balustrades
checkpoint-status |  |  | checkpoint | Waterproofing installed and signed off
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Spot check with Subcontractor -Installed in correct place
checkpoint-status |  |  | checkpoint | checked by Structural engineer
checklist-sectioned |  |  | checklist | Structural Remedials |  |  |  |  | Yes | Structural Remedials Checklist (V1) - QA | ee1bf803-9923-4577-887d-3d5745b8771a
checkpoint-group |  |  | section | Concrete Remedials
checkpoint-status |  |  | checkpoint | Site Inspection of Area completed with Hawkins/design team
boolean | ed42a780-5c43-4152-b925-0326c90e2b93 |  | tickbox | Defects list Confirmed ( copy attached)
boolean | 129b55e8-7669-4c24-8715-44d199fa045d |  | tickbox | Defects list Agreed with Subcontractor (copy attached)
checkpoint-status |  |  | checkpoint | Defects Complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Intumescent Paint Remedials
checkpoint-status |  |  | checkpoint | Site Inspection of Area completed with Hawkins/designer
boolean | 94215115-1c54-48fe-8a36-4be7808c566a |  | tickbox | Defects list Confirmed ( copy attached)
boolean | e7f0b1fd-6816-458b-a272-4731a6ed1ae0 |  | tickbox | Defects list Agreed with Subcontractor ( copy attached)
checkpoint-status |  |  | checkpoint | Defects Complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checklist-sectioned |  |  | checklist | Interior - Structural Remedials (V2) |  |  |  |  | Yes | QA - Interior - Structural Remedials (V2) | f0a21ac2-f69c-4ea3-bd7b-48747ea364df
checkpoint-group |  |  | section | Concrete remedials
checkpoint-status |  |  | checkpoint | Site inspection of area(structural remedials) completed with Hawkins/design team
boolean | d54de9e6-7dea-5357-8b46-35e4b5a2fec2 |  | tickbox | Defects list confirmed (copy attached)
boolean | c4de033c-ead9-5b82-8373-de6e1e497b20 |  | tickbox | Defects list agreed with subcontractor (copy attached)
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Defects complete
checkpoint-status |  |  | checkpoint | Any/all concrete remedial work completed
checkpoint-group |  |  | section | Intumescent Paint Remedials
checkpoint-status |  |  | checkpoint | Site Inspection of area completed with Hawkins/designer
boolean | 0ddab5e4-ba1e-5f85-bf3e-3705c69222fa |  | tickbox | Intumescent paint defects list confirmed ( copy attached)
boolean | 3cc0e56c-1137-532d-8e54-603239cd90ad |  | tickbox | Defects list agreed with subcontractor ( copy attached)
checkpoint-status |  |  | checkpoint | Defects complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Any/all intumescent paint remedial work completed
checklist-sectioned |  |  | checklist | Bolt Observations |  |  |  |  | Yes | Bolt Observations - QA | f15021bd-ffd5-4c40-86b0-7c2fc3316c70
checkpoint-group |  |  | section | Bolt Observations Closed Out
checkpoint-status |  |  | checkpoint | All sections completed ( handed over) before closed out
text | 3a1a610a-07b9-527a-8509-b755dc2a164c |  | textbox | Hawkins Team member to "pass " once satisfied all below items have been addressed
text | 0087fa1c-7e5d-55ce-a1f4-fcf57cb668b1 |  | textbox | Close out Required By ( add date)
checkpoint-group |  |  | section | Observation 1
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 77cff39e-5966-54b8-8aa3-495b8264603a |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 2
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 669b6cdd-c3b5-5975-b15b-3e666a6c3ad9 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 3
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | d9728877-ff9b-5837-9dbc-8a24776b07af |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 3
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | def16c99-960a-5bff-8fc0-a98cbf9b99e4 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 4
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 419a31d5-6752-5912-8bee-f28b2c699d7d |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 5
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 7bc22fc0-f863-55cb-ba63-c86be3295436 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 6
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | c5bd0e9a-342a-5fe3-885b-cd031adc3805 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 7
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | ccfd5910-a75f-50dd-a1ef-d6710a0717b9 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 8
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 9c375181-da99-5850-986f-3c36e7eef91c |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 9
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 28bf4ed2-3a70-5ac8-a13d-b0bce73d8ec7 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 10
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | b8757a90-0de2-513a-aeba-3a09f3c1c94f |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 11
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | fa87d8d1-337d-5293-9022-4daef7b8e59e |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 12
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 946a81e2-c59c-5351-91af-ed4bfbc03faa |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 13
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | a535cc73-7b01-51b2-961b-27606dd3121d |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 14
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | fde811cd-22db-5af1-abd4-e95fbec67797 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 15
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | b409b87f-22ff-575d-8467-3a9084158839 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 16
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 93a0ded4-3039-594d-8efe-82bb6344e9a8 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 17
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | e8ca971a-920b-5ae2-80ee-43c3d6286ab1 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 18
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | e3c2cc9b-0169-550d-a7b2-9a6cc344cdc7 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 19
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 21f6a69d-47f4-52ff-b789-45e139ebfd6c |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checkpoint-group |  |  | section | Observation 20
checkpoint-status |  |  | checkpoint | Current works Impacted ( Photo to be Attached of area before)
text | 787711d8-903a-5ef6-85d9-23a9bbfba927 |  | textbox | Zone /Floor Level & Location Description
checkpoint-status |  |  | checkpoint | Subcontractor works Completed including QA issued ( include photos )
checkpoint-status |  |  | checkpoint | Area Handed over to following trades
checklist-flat |  |  | checklist | Waterproofing - Tanking |  |  |  |  | Yes | Waterproofing - Tanking Checklist - QA | f2c0c4b7-a751-4907-864d-025832e0dd9c
checkpoint-status |  |  | checkpoint | Subcontractor & drawing reference details recorded
text | 3ae1e667-2a20-41c7-bb73-fd17c4170268 |  | textbox | Subcontractor:
text | 30996c58-459f-4899-9422-6656f73d3161 |  | textbox | Drawing Reference:
text | 981026d6-dfca-41c8-95d2-1dea8cb460b5 |  | textbox | Product Used:
checkpoint-status |  |  | checkpoint | Correct product delivered and checked
checkpoint-status |  |  | checkpoint | Substrate type
checkpoint-status |  |  | checkpoint | Preparation / Substrate acceptable
checkpoint-status |  |  | checkpoint | Waterproofing complete
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Any consultant inspections / observations documented, reviewed and closed out
checkpoint-status |  |  | checkpoint | Any Manufacturer inspections / observations documented, reviewed and closed out
checklist-flat |  |  | checklist | Building Consent - |  |  |  |  | Yes | Council BC Upload Checklist | f4d7f0fe-c0a2-41e7-bca3-71badde4438d
checkpoint-status |  |  | checkpoint | Latest building consent attached (superseded and attached as required)