## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 71363170-e96f-4fcc-86ce-fdcd53b9525e |  | checklist | [5 empty] | Yes | SYS - Gib Stopping | 054dac84-86e6-4911-90e2-5fd68f59c6f2
checkpoint-group | 9178e573-15fb-4fc5-b58c-340fcde534ee |  | section | Gib Stopping Checklist
checkpoint-status | 647bafff-2ae4-4cbf-b8db-1c239a560d4b |  | checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint-status | 9e431213-b0dc-4cf2-b618-282e1b3f7155 |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status | ca4722f1-b383-4225-b090-2f6abc7b54cd |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status | 1ed6a645-3f16-4618-a945-c161af1cc5e1 |  | checkpoint | Adequate drying time between applications & No visible bubbling
checkpoint-status | a761cf31-a6b2-4a8c-bbef-c17145c71200 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | c028d940-7647-4ce7-ad61-063f61be808e |  | checkpoint | All Stopping completed and specified level of finish achieved
checklist-sectioned | f6a2f5ad-55dc-4c57-9a47-ad0bcef3691e |  | checklist | Concrete Pour (Self Perform) |  |  |  |  | Yes | Concrete Pour Checklist (Self Perform) | 055d5f5c-bbae-4b73-bbaa-cbb97cd238df
checkpoint-group | 51a70fd3-8aca-4cd2-8a2a-bc101b4dabff |  | section | Pour Details
checkpoint-status | 2f1a8a6f-d358-4d50-9bfa-84a64288adea |  | checkpoint | Pour Details
text | fb021390-0e51-5030-b228-7c146b7fd325 |  | textbox | Area to be poured:
text | 20b1d42e-56c4-5554-9494-a4db49cd6b2b |  | textbox | Date of pour:
checkpoint-status | 2d988783-2466-466d-80dc-0e58dd05ae75 |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group | 026059b6-7895-4b65-8435-6d787bba06f7 |  | section | Formwork and Embedded Items
checkpoint-status | 2ef92253-aac4-4dc1-8a04-dac43e72e996 |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status | 8595338b-0a7e-4fe7-91d0-b1932c56ab88 |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status | 061f713d-e3ab-43d8-affe-5cc30153f7e1 |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status | ef42c38f-6798-491d-b714-4a4d17851601 |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group | a44dc7c4-1baf-4ad1-bdf8-8940c68ff254 |  | section | Reinforcing
checkpoint-status | 5c5d6563-238d-47f9-96ea-ffebc2629327 |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint | 9d929a52-e9e6-4645-af25-3c0cffc8443f |  | signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint-status | cde60644-0054-4f65-911e-6ab5d82b29c5 |  | checkpoint | Size and type correct to specification
checkpoint-status | 9dd8ae68-2dae-44aa-8601-eb2ebcccea9a |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status | 4aec0af2-f72e-48a1-a2a7-d2310e0e5a17 |  | checkpoint | Specified covers checked/correct
checkpoint-status | 002c1c36-e44f-4c6a-ac90-3ad7c27153f7 |  | checkpoint | Splice laps checked/correct
checkpoint-status | cf84baa8-da5a-4f0d-8523-552851e6d362 |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint-status | c6d49d3b-cd2b-41ae-9855-8e3e4e64fd4d |  | checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint-status | 5d80d7bf-873c-4523-8617-b8feba731cf9 |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status | 1ac8d9da-d0ec-477b-a1ba-969b96d365ab |  | checkpoint | Welding certificates sited and attached
checkpoint-status | 8501773c-9bca-41c7-8ef2-adaf72a65ba6 |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status | 18c125a0-6fa8-4ead-83dc-90406efa7f85 |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group | 2be4c2d5-ae32-4b46-bd38-de8e65664459 |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status | bb10925a-4d2d-49d0-83a5-ed50507882ea |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status | d06074f2-7ce6-4ec7-8a58-72fe3f679eeb |  | checkpoint | Any relevant service requirements completed (locations checked and accurate)
checkpoint-status | 4ed02f15-5359-4f1d-81e9-9f8cbbede9e7 |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status | 9af57a2f-7efc-41fb-98db-00ca55a25e26 |  | checkpoint | All relevant inspections completed and attached
checkpoint-status | eddb2a90-7ebc-4a2c-9e58-a565b98f5047 |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint-group | e29b2f3a-975f-4959-9fa9-6be6128b8979 |  | section | Concrete Supplier Specifics
checkpoint-status | 32d15521-3613-4761-a189-9f72f57f2c43 |  | checkpoint | Concrete Supplier Specifics
text | b3fdfc1e-f786-57a8-84e1-6d4ebddfdfd3 |  | textbox | Supplier Name:
text | 8bddd92f-6afd-55bf-acb5-1329f75196dc |  | textbox | Specified concrete strength:
text | 8cd3c191-61fe-50e9-9833-5259ad0d33c0 |  | textbox | Concrete strength ordered:
text | d741e67e-69bb-560c-b906-b2f1e05ec5d8 |  | textbox | Concrete quantity ordered:
checkpoint-status | acacfb9f-b2a7-4124-a6ac-c575730f9c47 |  | checkpoint | Test blocks booked
checkpoint-status | 8752cef3-6e0f-4940-adf2-6cb35c0ba44b |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status | cf93cb97-75f4-44c3-a72d-00f56495cd69 |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group | c73e39b0-589b-4e9e-a6a7-f9c242c4cf34 |  | section | Concrete Distribution
checkpoint-status | 65a0ccc4-4f7d-4711-b3d8-1f63a6feb8d6 |  | checkpoint | General distribution photos, documents and observations attached
checkpoint-status | 8eed281a-c50a-4436-8703-fd41fef80d9d |  | checkpoint | All concrete distributed correctly (area left clean and tidy)
checkpoint-group | 2c4b0569-e14f-4cee-832c-eb4b0eade63a |  | section | Placement Method
checkpoint-status | 7382a2c7-15e3-45a0-a853-49c9f03599a4 |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status | 97d924f5-b9bc-4ae3-887e-6e424ba6546e |  | checkpoint | Heights and falls checked/confirmed before placement
button | 4f79337c-f98c-5359-b118-8967d12c08e5 |  | button | Is the cover correct to specification | Yes, No
checkpoint-status | 10b51d97-b7b2-406a-97e4-ef1ebb3395dc |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status | ded9e0bd-f238-400c-bc28-7dd67354e704 |  | checkpoint | Any curing compound applied correctly
checkpoint-status | 0f1bfc4c-2b96-4249-a436-bff82dbb0384 |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status | 86ca222a-6434-43a8-990c-8283444d6227 |  | checkpoint | Area left clean and tidy
checkpoint-group | 8dd280dd-954b-4521-a70e-11c9ed014090 |  | section | Post Pour Checks/Sign Off
checkpoint-status | 45bcf761-0eb7-4a4c-ad1d-0a94998f790a |  | checkpoint | Any remedial work completed
checkpoint-status | 3e718905-5d8a-4a56-9f57-267168b350fc |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat | 92e7c082-b4c2-474c-94bb-9bd91dd310ac |  | checklist | Waterproofing Checklist |  |  |  |  | Yes | Waterproofing Checklist | 29cb1154-5055-4280-a654-4f0bc29a4a9f
checkpoint-status | 4b1bf3eb-9a33-464b-9fed-cbf9819a72e3 |  | checkpoint | Preparation / Substrate acceptable
checkpoint-status | 19ee22f4-e831-49dc-858a-3d084feaff18 |  | checkpoint | Correct product delivered and checked - approval given to install
checkpoint-status | be8ba47a-c710-4c45-bc40-5bfd2ea526e4 |  | checkpoint | General photos/comments during install
checkpoint-status | 95a539be-d714-4062-b115-87a885fe893c |  | checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint-status | 26b630ba-147c-484a-a245-2e4f4fe30cab |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | 4ce6183c-9dc6-43e4-be2f-48caeec0d703 |  | signoff | Request Subcontractor Sign Off
checklist-flat | 8c529ab8-b24a-41d9-9c60-34bab4ac4f43 |  | checklist | Council Inspection - |  |  |  |  | Yes | Add Council Inspection Checklist (V3) | 343187ae-0b95-42d2-b0d2-41d974779d8f
checkpoint-status | 74ef5da8-6d4f-4216-89e7-4008cdcdac12 |  | checkpoint | Council inspection completed, attached and any relevant observations closed out
label | 3444c651-e5e2-4a4d-87f9-f06b48de741d |  | note | PASS once all information is attached including Observations/Failed comments with evidence of closeout
text | dc83a024-74b8-4254-9ddd-e5098acc1bd8 |  | textbox | Date of Inspection:
text | 9078e12c-052d-4e8e-aaa0-bf0ee4a8e674 |  | textbox | Type of Inspection:
text | 52f91732-bf1d-45c6-bd07-b9da5bc92d07 |  | textbox | Area inspection relates to
select | b4da29de-ea63-439e-a19e-c0f75d938880 |  | dropdown | Inspection Outcome | Pass, Fail, Partial Pass,Completed, N/A
boolean | e163160e-48f6-4a1e-925a-fc9517380516 |  | tickbox | Council Inspection attached
text | 202aee45-e7db-4a11-a3cd-d58c1ed02669 |  | textbox | Failed Comment(s) & Required Action
label | 3c7bfeb2-48cc-4c75-8c53-db434c64e996 |  | note | Select N/A if there are no Observations/Failures requiring closeout
button | 5fc35eaa-61ff-4a6a-85df-bfb72c73a67d |  | button | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed) | Pass, N/A
holdpoint | 8371d317-ec31-400b-bafb-20cdce6a1315 |  | signoff | Request Signoff
checklist-flat | 80c5080c-13bd-4285-846a-274190139b3d |  | checklist | QA - Demolition Checklist (V1) |  |  |  |  | Yes | Demolition - | 363bb3bd-4f90-4e67-8f7a-036fcb8670c9
checkpoint-status | 5a2188ac-2177-4053-bddd-e8b56b7d35d0 |  | checkpoint | Appropriate services identified and appropriately isolated
checkpoint-status | a7b3f47d-1389-4e9c-9dc0-4737a17442b6 |  | checkpoint | Approval to begin demolition
label | f40df12c-532f-4de2-b5c4-a7498ae54787 |  | note | Select "PASS" once appropriate isolation and pre checks completed
checkpoint-status | 591f559e-8c5f-47f2-a8ec-80766ed474c6 |  | checkpoint | General photos during demolition
checkpoint-status | dd46db23-362e-4b13-9cc1-4f5d9cfc36bf |  | checkpoint | Demolition completed, reviewed and approved
label | 16b5c110-c73e-4d9e-8c81-0dac1483a53e |  | note | Select "Pass" once the demolition is completed & area is cleared
checklist-sectioned | ce65f06d-5962-48f4-9247-0b6795829006 |  | checklist | Services First Fix Checklist (Audit) |  |  |  |  | Yes | Services First Fix Checklist (Audit) | 4c318d98-5084-49c9-afd5-2e808843bd16
checkpoint-group | fbc5a46e-f38a-493a-886c-a843fdaa2b50 |  | section | Electrical
checkpoint-status | c552ec06-c83b-4a16-8401-fab28ac3b4ee |  | checkpoint | Shop drawing received and approved
checkpoint-status | 492029a7-c9cd-46d3-9640-40fd4bebf9b5 |  | checkpoint | Trades QA received
holdpoint | 0fa77e95-2625-42cd-8214-c701458ffdff |  | signoff | Request Subcontractor Sign Off
checkpoint-status | 03064180-ce52-4918-95a9-ab8d334e25eb |  | checkpoint | First Fix Completed
holdpoint | 90c44c4a-415c-4c82-bbe9-35cd68733bc5 |  | signoff | Request Hawkins Sign Off
checkpoint-status | ea41a524-75d0-4cc0-835a-6c4004bf0186 |  | checkpoint | Electrical Consultant inspection completed & issues closed out
checkpoint-group | 6fb297b8-c11a-4e02-b0d7-c062f2633983 |  | section | Plumbing
checkpoint-status | effbdc41-1b6a-41c3-ace3-fb3cfc10a3c9 |  | checkpoint | Shop drawing received and approved
checkpoint-status | df770c3a-224e-456a-ac35-f33a0476a101 |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | bfba5832-ab85-470c-84ff-0ea1936ea884 |  | signoff | Request Subcontractor Sign Off
checkpoint-status | 1dd40f0b-3424-414a-a006-a464f88c51c8 |  | checkpoint | First Fix Completed
holdpoint | 377a881e-bf37-4642-957f-5882357ec181 |  | signoff | Request Hawkins Sign Off
checkpoint-status | 8b19734a-e915-458d-988f-1b7c8beb142b |  | checkpoint | Hydraulic Consultant inspection completed & issues closed out
checkpoint-group | 249c34f5-018f-42a2-8688-b5f1bf4e5067 |  | section | Mechanical
checkpoint-status | f58ffedc-e602-4dee-aabe-2bf60e6e2426 |  | checkpoint | Shop drawing received and approved
checkpoint-status | 21444b57-5a33-4969-90fc-d0d16c21ee00 |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | 44647ad9-d451-4bfc-84eb-4b319dd568dc |  | signoff | Request Subcontractor Sign Off
checkpoint-status | c47268ac-7d10-41f2-bee8-d19badf84e0f |  | checkpoint | First Fix Completed
holdpoint | cd23ebbe-e88e-4e02-9aba-d6f204936a2c |  | signoff | Request Hawkins Sign Off
checkpoint-status | c9934f4b-b52d-4aa9-ac0d-b898be0e5ee7 |  | checkpoint | Mechanical Consultant inspection completed & issues closed out
checkpoint-group | 3ae556b2-b890-4439-9d18-ea21bb6f3fd7 |  | section | Fire Alarms
checkpoint-status | df22c937-9a40-4f79-892b-79bd049c2407 |  | checkpoint | Shop drawing received and approved
checkpoint-status | 93b2d591-053d-4fff-b6ff-b5031e61eda8 |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | f41ffefd-b197-4967-ad97-3c3f561d154f |  | signoff | Request Subcontractor Sign Off
checkpoint-status | cc7e424b-1fb9-48a2-9a25-897a03cd07c7 |  | checkpoint | First Fix Completed
holdpoint | 80c7a911-0c19-44ef-a79e-3e84468f39a8 |  | signoff | Request Hawkins Sign Off
checkpoint-status | a3160ed1-4b1d-4485-ac17-669a8bffbeb9 |  | checkpoint | Fire Protection Consultant inspection completed & issues closed out
checkpoint-group | d589cf88-b803-46b1-a5fc-7e53c7bb7493 |  | section | Fire Sprinklers
checkpoint-status | 13afcd3f-d4a3-4058-860f-01c7beff1664 |  | checkpoint | Shop drawing received and approved
checkpoint-status | 4e03d0bc-fe5c-4e48-bceb-e0370e9913ba |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | 8bd1a859-8cac-4871-a943-dffcb266394c |  | signoff | Request Subcontractor Sign Off
checkpoint-status | a4216126-890d-4b5c-a3a0-fece78b7b5d6 |  | checkpoint | First Fix Completed
holdpoint | e3766029-9a33-4a99-8b66-90bb61ae1f72 |  | signoff | Request Hawkins Sign Off
checkpoint-status | 7041516b-2c96-49e9-a790-d96d7751abe6 |  | checkpoint | Fire Protection Consultant inspection completed & issues closed out
checkpoint-group | 9fbb6dd0-cedc-4e50-9460-b488707ae830 |  | section | Security / Data / Comms
checkpoint-status | 955313f8-4e2f-4d39-ac6f-5189065f1a62 |  | checkpoint | Shop drawing received and approved
checkpoint-status | 48a4242f-6c98-4d31-99dd-612a53c6f316 |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | 9ba879ec-3d78-4f2d-8fa0-723a7f3bd04e |  | signoff | Request Subcontractor Sign Off
checkpoint-status | 9b85c867-1cdd-4a74-927b-f3d5424e080d |  | checkpoint | First Fix Completed
holdpoint | 0266eb33-d8ef-47b8-b114-4dd94a0c3a39 |  | signoff | Request Hawkins Sign Off
checkpoint-status | a43a329e-380d-4947-8a15-81bc6374872e |  | checkpoint | Security / Comms Consultant inspection completed & issues closed out
checkpoint-group | 6dd6bc21-1d74-47a1-8121-58839515e27a |  | section | First Fix Completion
checkpoint-status | e0d22251-053f-4448-a7b6-126330cd3170 |  | checkpoint | All First Fix Elements completed
checklist-flat | be8d1a5f-4e84-45ce-a293-0acf046a6ee2 |  | checklist | Damp Proof Membrane Checklist |  |  |  |  | Yes | Damp Proof Membrane Checklist | 4e81308c-0bf8-4f27-aa39-f0d94069ff6c
checkpoint-status | ffe0b71e-a10c-4296-b9cb-f74377fa1373 |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status | becb62f0-c6b7-44b3-ba66-961af1c4983d |  | checkpoint | Preparation / Substrate acceptable
checkpoint-status | 90a59a58-afe5-486e-b92a-102999b74eaa |  | checkpoint | Correct product delivered and checked - approval given to install
checkpoint-status | fcab6bf8-e156-4f67-a295-fa3d7d7b20ef |  | checkpoint | Sheets lapped 150mm and taped
checkpoint-status | 4ff6ece4-5210-4f3e-a36f-bad2052bee73 |  | checkpoint | PVC up-stands waterproofing details as specified
checkpoint-status | 5fdcd8f0-cf6f-4953-83ad-99df8ff61285 |  | checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint-status | 5578cdca-1b19-4b09-a781-5aac6f876fa6 |  | checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
holdpoint | ff26c1be-c291-40cf-92d1-4a9c21229430 |  | signoff | Request Subcontractor Sign Off
checklist-flat | 5426c1d5-3c0c-4b2d-9293-ad8c63327285 |  | checklist | QA - Upload - |  |  |  |  | Yes | QA - Upload Checklist (V1) | 5adc932b-147a-4379-a750-58de0636efd5
checkpoint-status | 142b7e68-adb0-46f2-94ab-572db17b50a2 |  | checkpoint | Previously completed work and QA uploaded here then "PASS"
checklist-sectioned | 88f3de3f-3601-4d51-875f-8f469e0e7365 |  | checklist | Demolition Checklist |  |  |  |  | Yes | Demolition Checklist | 7a3376e1-1ef0-4a57-a3f7-0b41a124e941
checkpoint-group | a145c29b-383b-4123-8de8-f22519fefefd |  | section | Pre Demolition QA
checkpoint-status | 85cc1e44-49ed-4c58-9cd6-3e1589f32970 |  | checkpoint | Traffic management in place (attach TMP)
checkpoint-status | 91d907f7-a278-4fe1-9068-fe75bc12d172 |  | checkpoint | NVMP completed and attached
checkpoint-status | ef1109f4-825f-47a6-82f1-06e8316bc5b7 |  | checkpoint | Attach any other relevant pre start documentation
checkpoint-status | 22e8621b-a247-4156-9ba8-3649fa92378c |  | checkpoint | All relevant services isolated
boolean | d9dc6ed5-6ea2-5df7-ad33-e356ff95f183 |  | tickbox | Power isolated
boolean | 198b8b4c-3273-5124-9b63-93cc8d934147 |  | tickbox | Waste/storm water isolated
boolean | a1f7be8d-ce05-51a5-9f7c-adf86bcc93f5 |  | tickbox | Gas isolated
boolean | c0905bd1-22ff-5d06-8478-aa94de5a4b90 |  | tickbox | Telecommunication/Fibre isolated
boolean | ec0e255c-6510-58bd-a06f-6722a044018c |  | tickbox | Any other relevant services isolated
text | 1973c2c1-6f5c-5f13-820f-69d7d533977e |  | textbox | Specify which other services were isolated
checkpoint-status | 0ba18e97-1a66-4c71-9120-3e97da9507c1 |  | checkpoint | General Photos of controls (attach and label)
checkpoint-status | 100e04cd-5eed-401d-a832-9f3fb6c1f62e |  | checkpoint | All pre demolition QA completed and approval given to commence demolition
checkpoint-group | 94b6d0e6-56db-47ce-b603-d6c49af00eaf |  | section | Demolition QA
checkpoint-status | cb67e7d9-f416-495e-b4e2-55988dd1a33f |  | checkpoint | Prior to demolition, all pre start checks have been completed
checkpoint-status | 5358b3b6-c46e-429e-89e2-08705bbe637d |  | checkpoint | General photos and observations of demo (attached and labelled)
checkpoint-group | f5e92d47-cd68-440f-b3d7-adc3c33e2cda |  | section | Demolition Complete
checkpoint-status | d97a6fad-1ebe-49d0-b1b3-7b8ed45e527d |  | checkpoint | All rubbish/debris removed and area left clean and tidy
checkpoint-status | a7a63823-ca95-4a9d-8c2b-1372b7bcbd42 |  | checkpoint | Trade Contractor QA received, attached, reviewed and approved
checkpoint-status | ab978b25-8819-4c18-9210-b0a94fcf6c9d |  | checkpoint | All demolition works completed, checked and approved
checklist-flat | 79cec70a-06d2-44c4-b020-6081b6d83623 |  | checklist | Structural Steel Checklist (Audit) |  |  |  |  | Yes | Structural Steel Checklist (Audit) | 836d1087-90f5-4bb0-926b-44b5bfd4e243
checkpoint-status | e45b426c-b863-41cd-90d0-c509ac4727fc |  | checkpoint | Steel inspected on arrival, checked and correct (photograph delivery docket)
checkpoint-status | 297d877d-aeba-4ce5-826a-c9bcd7ef7bb8 |  | checkpoint | Hold down bolts in the correct location
checkpoint-status | 1d116ca8-723f-4ec9-ae9d-fd4c270bd580 |  | checkpoint | Pre erection checks complete
checkpoint-status | 01b75a40-729d-414b-9bff-397d5fc4a772 |  | checkpoint | Steel correct size and type
checkpoint-status | 1318ad81-684d-4b1a-8d46-9c4c51a92b74 |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status | 01463ffe-42c3-4500-997d-0c65d426e00b |  | checkpoint | Correct location and orientation
checkpoint-status | 8d4617b6-3f0f-4f0e-a054-5724b16bb602 |  | checkpoint | Level, plumb, correct pitch and braced
checkpoint-status | 381bcc9b-5e52-4467-bcac-15f30cdeb450 |  | checkpoint | All bolts secure/ correctly tensioned
checkpoint-status | 71fb87ac-b70b-43bd-89e2-ad1b9afdd710 |  | checkpoint | Any additional photos, comments and observations
checkpoint-status | d6caa8f3-bfb4-4901-8872-dd3596b7e693 |  | checkpoint | All structural steel correctly installed in respective area
holdpoint | 693b8e96-9cee-407f-a23b-ef8186e0cc9b |  | signoff | Request Subcontractor Sign Off
checklist-sectioned | d0f5571c-aa72-42c9-bb2f-6781abf552a4 |  | checklist | EXAMPLE - DO NOT USE - Services First Fix Checklist |  |  |  |  | Yes | EXAMPLE - DO NOT USE - Services First Fix Checklist | 87fe8841-5ec4-49b1-87de-37a93a1c194d
checkpoint-group | 8ea61fb3-2399-4948-b61f-62e4522f9ddc |  | section | Electrical
checkpoint-status | 776f1670-45d0-4e6b-aafa-5853e6dc39f8 |  | checkpoint | Shop drawing received and approved
holdpoint | 9d1483aa-2bde-4fa1-99a5-335b4beb1e38 |  | signoff | SIGN HERE
checkpoint-status | e87f0071-7de5-4127-a986-86879cf689e7 |  | checkpoint | Trades QA received
holdpoint | d5785586-f482-4e13-8dbc-31ee002fd6be |  | signoff | SIGN HERE
checkpoint-status | f0953909-954d-46ff-817c-bed2c47330b6 |  | checkpoint | First Fix Completed
checkpoint-status | a548699b-28ca-4d46-a6c2-c732eaed8f8d |  | checkpoint | Electrical Consultant inspection completed & issues closed out
checkpoint-group | 9445efad-6b42-4426-8688-de31608befaa |  | section | Plumbing
checkpoint-status | c9312789-ed34-40b0-aefa-f28c9ee3f808 |  | checkpoint | Shop drawing received and approved
holdpoint | aa9a4a38-05c5-410f-9f36-22b21f1988ed |  | signoff | SIGN HERE
checkpoint-status | 8f9edcdc-5d8f-4fd0-ba89-795b2904d9ac |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | 1f9922f6-528a-47f3-a44d-365e26718655 |  | signoff | SIGN HERE
checkpoint-status | 119bb28a-8a89-421f-8b33-42b46e7f5fc2 |  | checkpoint | First Fix Completed
checkpoint-status | d428572a-802f-4016-9c97-faf06446d990 |  | checkpoint | Hydraulic Consultant inspection completed & issues closed out
checkpoint-group | d9d653cb-c154-4f12-b4d2-3eda6a006f84 |  | section | Mechanical
checkpoint-status | 88378377-9da3-4347-8c12-4eee3c54916d |  | checkpoint | Shop drawing received and approved
holdpoint | 0e6aec5e-18f7-4a81-923b-f5c4364f7278 |  | signoff | SIGN HERE
checkpoint-status | 9d8d30ce-2511-459e-9ae4-acbd5b8f9321 |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | d894c177-03a4-44d0-a19e-4f99884989f3 |  | signoff | SIGN HERE
checkpoint-status | eeac3fb8-8f4d-426b-ac12-9baf39a6c30f |  | checkpoint | First Fix Completed
checkpoint-status | 5078e63c-a76e-49fc-b5e3-b25cf3407bfb |  | checkpoint | Mechanical Consultant inspection completed & issues closed out
checkpoint-group | 424aaeff-bdcb-4b6a-af05-af8b5ea7efaf |  | section | Fire Alarms
checkpoint-status | 75502c13-e0b0-47eb-a744-4ab366c62c38 |  | checkpoint | Shop drawing received and approved
holdpoint | e132e624-efa7-4912-87dc-234755f92305 |  | signoff | SIGN HERE
checkpoint-status | a888a7a0-afcb-4de7-bfbf-dfcccff623d3 |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | a42ec2ab-338c-46fb-a14e-1d55d2dee0b0 |  | signoff | SIGN HERE
checkpoint-status | d0c9b200-839c-4d1b-a69e-4150ecd038c2 |  | checkpoint | First Fix Completed
checkpoint-status | 3cc10ad7-7fc1-4c10-8d85-6a97e54e979f |  | checkpoint | Fire Protection Consultant inspection completed & issues closed out
checkpoint-group | c47b7fe3-0b82-429f-8898-30184e06f84c |  | section | Fire Sprinklers
checkpoint-status | f7a3e6aa-9876-4d3f-99b7-5f9d56a08cc3 |  | checkpoint | Shop drawing received and approved
holdpoint | ba3a1f92-a6a7-4f65-87d1-40c3967692b2 |  | signoff | SIGN HERE
checkpoint-status | aafc796b-1181-45e0-80fe-f08f2cfdcd13 |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | f880f174-c93e-4f55-b6a9-e325c2c8fde0 |  | signoff | SIGN HERE
checkpoint-status | 96fef914-46e7-4799-989e-25f5a53ae900 |  | checkpoint | First Fix Completed
checkpoint-status | b25077e7-2939-4c9c-a34d-f91ea1f0ecbc |  | checkpoint | Fire Protection Consultant inspection completed & issues closed out
checkpoint-group | 004f5d7a-c686-40e9-b236-6e20cf3bf325 |  | section | Security / Data / Comms
checkpoint-status | 6fd5fbf8-a87d-4b79-ae0c-b89e73644e88 |  | checkpoint | Shop drawing received and approved
holdpoint | db04e631-1d73-4d30-81fd-1023b73b575a |  | signoff | SIGN HERE
checkpoint-status | 56f23c1f-a644-4880-9e3a-834800be355f |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | 229acb54-ccaf-4da1-83a7-b7e5471c6769 |  | signoff | SIGN HERE
checkpoint-status | bd800b7e-be29-40b0-bf29-f72c1e677f8a |  | checkpoint | First Fix Completed
checkpoint-status | 0ff1b0c5-2815-4c65-a63f-1237a4dfc223 |  | checkpoint | Security / Comms Consultant inspection completed & issues closed out
checkpoint-group | a3d5d00e-d2d9-44af-bdb5-944b2b12e099 |  | section | First Fix Completion
checkpoint-status | ddcca1a1-80ce-4e8f-9bcb-415753bc2676 |  | checkpoint | All First Fix Elements completed
checklist-sectioned | 5703662a-ec1a-440b-82a1-e6e7f8935f81 |  | checklist | Services Second Fix Checklist (Audit) |  |  |  |  | Yes | Services Second Fix Checklist (Audit) | 905c1b8b-845b-42c9-a42b-92cf098bd1e2
checkpoint-group | 0c90e365-01ec-42e2-a4fc-9290467c56ad |  | section | Electrical
checkpoint-status | f938cbcd-7d46-4e9c-a19c-d072c92ed623 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 96591270-c5a9-4098-84ce-dd83173326c5 |  | checkpoint | Second Fix Completed
holdpoint | bf9800c8-39dc-4f89-bf93-eb355e824aae |  | signoff | Request Subcontractor Sign Off
checkpoint-status | a33c485f-c3bb-4e7a-880d-03cd1de183b8 |  | checkpoint | Electrical Consultant inspection completed & issues closed out
holdpoint | dcf54dc0-c204-47dd-968b-90368412b491 |  | signoff | Request Hawkins Sign Off
checkpoint-group | 1cd9a202-f8a8-469d-8adc-5ccda25b1658 |  | section | Plumbing
checkpoint-status | ab8d572c-cde8-4f9a-939e-76135e59781f |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 5e3c7257-1273-4a8b-82be-5f5abbb44342 |  | checkpoint | Second Fix Completed
holdpoint | fd9bd92f-b605-44a2-80a9-9fd0225fd813 |  | signoff | Request Subcontractor Sign Off
checkpoint-status | 29ce6b00-5378-4f5f-8af5-58787e07840d |  | checkpoint | Hydraulic Consultant inspection completed & issues closed out
holdpoint | f00ad961-7f73-4485-9648-03adb8215bf8 |  | signoff | Request Hawkins Sign Off
checkpoint-group | 501e5290-d0a5-4705-b034-8cc8d2695698 |  | section | Mechanical
checkpoint-status | 856388b3-f856-4238-892e-af46455576cc |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 3e9eea00-4de4-4006-b4f0-07d0b9193d91 |  | checkpoint | Second Fix Completed
holdpoint | 65e7f587-8422-44c2-b6a9-ffe21180b113 |  | signoff | Request Subcontractor Sign Off
checkpoint-status | 86d9fdcd-181b-42ce-839d-7618df0bdffd |  | checkpoint | Mechanical Consultant inspection completed & issues closed out
holdpoint | fe363d60-7200-4d53-99c8-68bcacedf715 |  | signoff | Request Hawkins Sign Off
checkpoint-group | 2c1e92d9-609d-4a55-a741-ce49a0975f6e |  | section | Fire Alarms
checkpoint-status | c984beb0-9739-44dd-974e-9f70a0cd1de0 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 0e3a0e34-5616-4a8f-b9ef-dca9f3d5dec2 |  | checkpoint | Second Fix Completed
holdpoint | 99e67ace-7410-4c7a-9186-9713372cae9f |  | signoff | Request Subcontractor Sign Off
checkpoint-status | 567da7e0-7834-484e-9859-d722fa224983 |  | checkpoint | Fire Consultant inspection completed & issued closes out
holdpoint | 604ffe85-8287-4db9-a9d4-b4f61eda34e0 |  | signoff | Request Hawkins Sign Off
checkpoint-group | 274bc5f1-475f-461b-b79c-ce99c0eb06a6 |  | section | Fire Sprinklers
checkpoint-status | 03df7810-11e8-41f1-b478-47bffdc9f7ea |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 40e40be3-101f-4d72-89c6-b18be7caeef7 |  | checkpoint | Second Fix Completed
holdpoint | 5782e697-db8b-4c44-8398-0c9686c3efcc |  | signoff | Request Subcontractor Sign Off
checkpoint-status | dfaaf646-9974-481f-8c3e-e88083bf16de |  | checkpoint | Fire Consultant inspection completed & issues closed out
holdpoint | f031c1dd-4a5d-4fae-a86e-637adbb0bbb9 |  | signoff | Request Hawkins Sign Off
checkpoint-group | 6cc14e51-2557-4419-91d7-c0ecd24e39e4 |  | section | Security / Data / Comms
checkpoint-status | 2f81658d-e89a-479b-9fd2-d16cf7a472b5 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | afe26634-1b26-40a6-b492-1ce3e3dfc300 |  | checkpoint | Second Fix Completed
holdpoint | 3189fc2b-c822-4007-bd83-acd813059178 |  | signoff | Request Subcontractor Sign Off
checkpoint-status | ca4bef3e-dbb3-4feb-9aba-f9f43327d91c |  | checkpoint | Security / Comms Consultant inspection completed & issues closed out
holdpoint | 410c740c-da0d-44e6-aa76-515503424edf |  | signoff | Request Hawkins Sign Off
checkpoint-group | 33bdfa76-3cc4-448e-b89e-e339ea897d25 |  | section | Joinery
checkpoint-status | b96b23da-fd48-4287-8eb5-a14b7614a6b0 |  | checkpoint | Shop drawing received and approved
checkpoint-status | e8c8a83a-8f85-4049-bf3e-3a36263ade3a |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | 4c7ecf96-d2d5-4b9d-8089-d6670b58554e |  | signoff | Request Subcontractor Sign Off
checkpoint-status | 966e71be-433a-4e41-bbad-4ee4953faefa |  | checkpoint | Second Fix Completed
checkpoint-status | f09c5a34-8f73-45e9-8976-0080dd3a0bed |  | checkpoint | Joinery inspection completed & issues closed out
holdpoint | afdc8f24-7605-4547-bca1-f2c97621be6c |  | signoff | Request Hawkins Sign Off
checkpoint-group | 8658c128-4f4d-455b-ba68-84478668e184 |  | section | Painting
checkpoint-status | b01eba26-7d25-4c0b-9847-b0c6b4b946f0 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 3043b508-4b2f-4298-8ab7-ac0b26bc86b7 |  | checkpoint | Second Fix Completed
holdpoint | 08bb86f7-f584-4361-b6b7-6e9413e14b3f |  | signoff | Request Subcontractor Sign Off
checkpoint-status | b5e24f3a-306e-4ff1-a482-63d1d81e12cb |  | checkpoint | Painting inspection completed & issues closed out
holdpoint | 5df43c65-f0ad-407d-b0f6-91cf340f1b41 |  | signoff | Request Hawkins Sign Off
checkpoint-group | 90729344-ca17-4e21-b3d9-890ccb640399 |  | section | Flooring
checkpoint-status | 12c0093c-3e4a-47f6-9da4-921594bec85b |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | e22c742b-c437-4d6e-95c0-32fff8ac87c3 |  | checkpoint | Second Fix Completed
holdpoint | 991de28a-2fb1-49a0-be70-b9daa70d5beb |  | signoff | Request Subcontractor Sign Off
checkpoint-status | 29d95d2f-7841-4e1e-952b-451ed780108a |  | checkpoint | Flooring inspection completed & issues closed out
holdpoint | b458c46f-e9b4-4567-b00e-22f602936552 |  | signoff | Request Hawkins Sign Off
checkpoint-group | c422f4fe-fdad-4c94-9dd5-fe1914bc4eee |  | section | Ceiling Grid Checklist
checkpoint-status | 7da6ab9a-99fe-4e44-bee4-f1c617358d0b |  | checkpoint | Service markout completed, checked and acceptable (clashes considered)
checkpoint-status | 1631a964-527e-4e1f-8ed6-95bf8a56ad1b |  | checkpoint | Ceiling Height confirmed
checkpoint-status | 6262135c-76d6-4c1c-8a75-df780098b0e0 |  | checkpoint | Appropriate fixings used and installed as per required specification
checkpoint-status | 76ba5567-8518-488a-8107-730ebb557412 |  | checkpoint | Appropriate spacings for respective grid elements
checkpoint-status | 6b042bd6-2aee-43bb-aa75-a183bdbcbc44 |  | checkpoint | All ceiling grid completed in respective area to required specification (Attach photograph of respective completed grid)
checkpoint-status | 8704d5b5-fa78-4c74-af01-aef0fffb0c5e |  | checkpoint | Trades QA received, reviewed, attached and approved - Subcontractor
checkpoint-status | 06cee4f1-f179-475a-9e91-42087d1f307f |  | checkpoint | Request Subcontractor Sign Off
holdpoint | b013a4a2-43c0-465d-a6a7-e6b3e1269f86 |  | signoff | Request Sign Off
checkpoint-status | ea5de07f-d031-403e-8221-0b46ec93ea17 |  | checkpoint | Request Hawkins Sign Off
holdpoint | 81d92f20-0d6d-42ce-a053-7279ec38de09 |  | signoff | Request Sign Off
checkpoint-group | c7035d6f-cd41-42d2-81ca-ab4cc86d517c |  | section | Ceiling Tile Checklist
checkpoint-status | d2983732-b1b6-4a99-88bf-b9355be76b9e |  | checkpoint | Correct tiles installed as per design
checkpoint-status | bbd6ae76-7d10-4cdd-acf9-38d47dd0a327 |  | checkpoint | Services tiles installed, clean & tidy
checkpoint-status | ce05d393-702d-4f47-8469-77f38804bcd4 |  | checkpoint | All other tiles installed, clean & tidy
checkpoint-status | b53448a4-4cbb-4fbc-9bc8-83800d411829 |  | checkpoint | All tiles installed, mark/damage free and area completed to required specification (attach relevant photos)
checkpoint-status | c1cfbe62-7832-4fa1-b6da-bb7dffe7ee84 |  | checkpoint | All tiles installed and area left clean and tidy (attach relevant photos)
checkpoint-status | 669db590-9472-441e-bb44-9da5c849edbb |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 80c536bd-49c5-4c86-b9c4-a898074fc6d4 |  | checkpoint | Request Subcontractor Sign Off
holdpoint | e46ed493-21f8-4b31-9181-b4e73a3f585a |  | signoff | Request Sign Off
checkpoint-status | a714caa3-6e6d-41fe-996a-2253d38dbef9 |  | checkpoint | Request Hawkins Sign Off
holdpoint | 1b8d36d5-37fe-46c6-a39f-a8b5f33e9250 |  | signoff | Request Sign Off
checkpoint-group | 7f397e7d-9f8b-437f-8258-553b4086e52e |  | section | Second Fix Completion
checkpoint-status | 3b543bf6-896f-431c-aef7-b1884c7b4d55 |  | checkpoint | All Second Elements completed
checklist-sectioned | b2e8db29-a77c-4fae-9039-db5c56b1ec65 |  | checklist | [5 empty] | Yes | SYS - Gib Lining | 95624349-a472-470a-b295-c504c808e2ae
checkpoint-group | b93d8efa-4e1e-458b-bdbd-ec5414d6c174 |  | section | Gib Lining Checklist
checkpoint-status | 315fb4df-ddc8-457b-ab04-b542feb07cea |  | checkpoint | All preline services completed and approval given to line
boolean | 44f8df5b-cb4d-50af-a2eb-6cbb21106822 |  | tickbox | moisture content checked, recorded and acceptable
checkpoint-status | 26f7e3b5-8628-4123-94e7-90e999c24fcf |  | checkpoint | Correct lining (Checked and approved)
checkpoint-status | ee9ddad9-55bb-4149-8d28-c8f0a6349e0b |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | c8922bed-3f1f-42a3-a259-6a64b153799c |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | 47a74e86-6396-48c2-ac27-d118115e2831 |  | checkpoint | check if service are required in this location
checkpoint-status | a795eaf3-78ec-408a-9208-00aceb8ebb06 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 456d8205-62d9-4148-b8d9-82a7294f0742 |  | checkpoint | All lining completed, checked and approved
checkpoint-group | 414967b6-dd3d-4dfc-b993-2ea3677a4db2 |  | section | Passive Fire Checklist
checkpoint-status | 6a69ee07-74f4-47a8-b94c-9877a1fb5d28 |  | checkpoint | Trades QA received
checkpoint-status | 34604f5d-7587-4dfd-b53b-4dde22c9c9d1 |  | checkpoint | All Passive fire elements completed, reviewed and approved
boolean | 0af48d62-cda0-590b-a68d-f83104801b08 |  | tickbox | Fire Protection Consultant inspection completed & issued closed out
boolean | 9c1b8280-b882-5e88-9491-5e131df57f56 |  | tickbox | Council inspections carried out & attached in council folder
checklist-sectioned | 0ff12a1c-2ad8-4970-8f5f-22c8c3098629 |  | checklist | Services First Fix Checklist |  |  |  |  | Yes | SYS Services First Fix Checklist | 95a038bd-7464-4fc1-bc10-a7ac3b7c1102
checkpoint-group | 2e8244f8-3cab-4df9-b34d-994e2da3a77b |  | section | Electrical
checkpoint-status | 600ba832-cb09-46c8-85e0-6ca9aeeece79 |  | checkpoint | Shop drawing received and approved
checkpoint-status | fd9d6ee8-6b56-4dc2-96ea-aee2897ee98c |  | checkpoint | Trades QA received
checkpoint-status | 866d365d-3e16-4160-ac33-5ec51cee68ed |  | checkpoint | First Fix Completed
checkpoint-status | c933aeed-c388-454f-887c-8657332ba033 |  | checkpoint | Electrical Consultant inspection completed & issues closed out
checkpoint-group | dea4ab6e-8d46-4211-bf43-8ee52f53dc0c |  | section | Plumbing
checkpoint-status | 40611b49-e373-4bb0-bcd5-b0c72013c288 |  | checkpoint | Shop drawing received and approved
checkpoint-status | 4424b9f0-9253-4506-9f8c-6d189a0736eb |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | de5a1dd5-9606-42f7-88da-1c94adefdc7e |  | checkpoint | First Fix Completed
checkpoint-status | 51a79250-59a0-435b-a420-6b55acd2b0f3 |  | checkpoint | Hydraulic Consultant inspection completed & issues closed out
checkpoint-group | 1b78bd0f-7641-4029-b16d-3e32681fe0c6 |  | section | Mechanical
checkpoint-status | e5fab4e7-4ee4-4b12-a355-0fb2d09ce3eb |  | checkpoint | Shop drawing received and approved
checkpoint-status | 5095a02d-b8e1-42b2-95e2-0f5c99bd35db |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 1e839b83-ad72-40ec-812a-15d9120b4e33 |  | checkpoint | First Fix Completed
checkpoint-status | a68b0dbf-a617-499d-ae67-d85e18386c69 |  | checkpoint | Mechanical Consultant inspection completed & issues closed out
checkpoint-group | d4aacf24-c0b9-4b5c-b207-a5be20e1be38 |  | section | Fire Alarms
checkpoint-status | 8fcbb1f8-948e-4a74-bac5-27479193d5ca |  | checkpoint | Shop drawing received and approved
checkpoint-status | 52b59897-fbf1-4b8b-a317-462deacfff60 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 87100b2d-3ada-48d3-8751-a01766840126 |  | checkpoint | First Fix Completed
checkpoint-status | ca87f510-e630-4150-aa9e-b975392bc2d3 |  | checkpoint | Fire Protection Consultant inspection completed & issues closed out
checkpoint-group | b853123a-fa80-493a-b71b-b708008b7dc2 |  | section | Fire Sprinklers
checkpoint-status | b39bd4ff-3787-4d11-9ade-c9dd4a6a9cd8 |  | checkpoint | Shop drawing received and approved
checkpoint-status | 22270ecf-556d-4577-8fba-912d234568aa |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 1583c33d-58e0-4d3c-b44f-cc8c2b0c4374 |  | checkpoint | First Fix Completed
checkpoint-status | dbabefc5-1b5c-4424-8382-31b2ad093f67 |  | checkpoint | Fire Protection Consultant inspection completed & issues closed out
checkpoint-group | 99cd3396-94ad-4ce7-bb02-395f3b517af4 |  | section | Security / Data / Comms
checkpoint-status | f274feeb-53de-458e-a901-5f33c33e28dc |  | checkpoint | Shop drawing received and approved
checkpoint-status | e4c566ae-5fbc-4599-a943-2de74afa9329 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | dbc450dc-976d-4084-afa6-5282dce8dd38 |  | checkpoint | First Fix Completed
checkpoint-status | 88b07411-1e4b-4a72-be70-3d5af3d74cf6 |  | checkpoint | Security / Comms Consultant inspection completed & issues closed out
checkpoint-group | f5efb42d-02af-48b1-a404-08f1d18bc2c0 |  | section | First Fix Completion
checkpoint-status | cd8e7ebf-0547-404e-928d-ef0f49727db9 |  | checkpoint | All First Fix Elements completed
checklist-sectioned | 71a5253d-067a-4835-953a-bde6a0b6f005 |  | checklist | [5 empty] | Yes | SYS - Timber Framing | a32da9b3-e49b-4f97-a392-23110b8f6f57
checkpoint-group | 8559e0c5-2ceb-4e13-8cae-466a2a83a9de |  | section | Framing
checkpoint-status | fefa87dc-c180-4d51-9ab6-3953f9481c28 |  | checkpoint | Room set outs and wall locations consistent with approved plans
checkpoint-status | 8bdbb163-1f2a-41b0-b7e3-f68c2179df66 |  | checkpoint | Check framing for straigthness
checkpoint-status | d7b5a3b1-ef9c-4971-9328-1364bd3fe7bf |  | checkpoint | bracing installed
checkpoint-status | 98aefbe9-e3d6-474b-8b98-ba8a4b007d87 |  | checkpoint | Nogs installed correctly
checkpoint-status | 3c004724-0893-4e5f-a492-1bc836d2ac64 |  | checkpoint | General photos during installion
checkpoint-status | 973996fd-560e-4a0b-8a5b-859f0f4e4fff |  | checkpoint | Trades QA received, reviewed, attached and approved
checklist-sectioned | 7f168a28-604f-43b2-b72c-543298f3a894 |  | checklist | Services Second Fix Checklist (Audit) |  |  |  |  | Yes | SYS Services Second Fix Checklist | a8e78839-19a3-4cbb-9c09-29db4c099bbd
checkpoint-group | 0a8be351-2018-48de-9152-3a663a3f6222 |  | section | Electrical
checkpoint-status | c141c35a-5b08-496f-8c4e-65d4e15549ff |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 56376ada-a054-4f88-abee-16e5f52240d4 |  | checkpoint | Second Fix Completed
checkpoint-status | 8b796936-31d3-4155-8b3b-e014ad8486af |  | checkpoint | Electrical Consultant inspection completed & issues closed out
checkpoint-group | f4248046-22ae-4918-b979-1505a7ed0935 |  | section | Plumbing
checkpoint-status | 36a074e6-af96-4b46-84b2-513796d8534f |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 30d37061-bdf7-4d67-aa0e-3c2407cf3722 |  | checkpoint | Second Fix Completed
checkpoint-status | d74c042c-3632-466e-a13f-50a392d7b17d |  | checkpoint | Hydraulic Consultant inspection completed & issues closed out
checkpoint-group | 20f0bef6-03c3-489a-a971-d9a691612777 |  | section | Mechanical
checkpoint-status | 567b58bd-3461-4653-9308-79467c3e4259 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 5b5b251b-d4e7-42d5-b7ba-b2ea8eb41baf |  | checkpoint | Second Fix Completed
checkpoint-status | a83400b2-b4a5-447f-93e1-35a2b18934b1 |  | checkpoint | Mechanical Consultant inspection completed & issues closed out
checkpoint-group | 0f42d530-5295-4477-8888-69e8411cb358 |  | section | Fire Alarms
checkpoint-status | 81c5d6d7-30c2-448d-aff8-33796a3e2f2e |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | affdc08f-eb83-4131-88e6-a5c536e7cb3f |  | checkpoint | Second Fix Completed
checkpoint-status | fcb8e6a3-9267-4688-af7a-99c97513fc04 |  | checkpoint | Fire Consultant inspection completed & issued closes out
checkpoint-group | 4b588eac-1557-4941-89b2-47677c3c2d85 |  | section | Fire Sprinklers
checkpoint-status | e0301eae-cd2b-46c0-91be-b06137393cbb |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 88e581f4-add0-4cf6-925d-5e238fb0fffd |  | checkpoint | Second Fix Completed
checkpoint-status | 75638d7c-dba6-416b-808b-e1e93b1ea636 |  | checkpoint | Fire Consultant inspection completed & issues closed out
checkpoint-group | ea9c55eb-0a04-4cb9-a542-fe694f821640 |  | section | Security / Data / Comms
checkpoint-status | 3ab13996-76a0-4f05-9537-7aa121571a14 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 7c2b3a8d-5813-4525-a1ee-daa01758aae5 |  | checkpoint | Second Fix Completed
checkpoint-status | fec8fc8f-50d2-4374-b146-0337ee1440c9 |  | checkpoint | Security / Comms Consultant inspection completed & issues closed out
checkpoint-group | 0bcaf03b-3071-4b35-8ca6-323c71133460 |  | section | Joinery
checkpoint-status | bdf7a4c4-8c1d-49ee-8d5b-c9a1c3b76ec0 |  | checkpoint | Shop drawing received and approved
checkpoint-status | 653785cc-7347-4d21-9eb4-41c8bb163026 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | b19e69cb-5e4e-4525-a638-3248e643a6b6 |  | checkpoint | Second Fix Completed
checkpoint-status | 5fa4d5d1-2c69-47da-a612-f49ed99ce280 |  | checkpoint | Joinery inspection completed & issues closed out
checkpoint-group | 26a7f5af-452b-4626-b03a-328db4db422d |  | section | Painting
checkpoint-status | bfc2708c-86fa-4e7a-a973-5349134560c4 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 744dc32d-31b6-4037-ac80-899da94cc4bf |  | checkpoint | Second Fix Completed
checkpoint-status | e2489ff1-3f3d-4607-9cd0-5175d571dd2b |  | checkpoint | Painting inspection completed & issues closed out
checkpoint-group | 0b74ffb6-3ac6-467c-b3f2-c14aaa53ba94 |  | section | Flooring
checkpoint-status | 9316f2c6-71a1-43eb-a6ed-01bf8eb86add |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 47c23b61-ba6e-4692-8b23-9cf83810f9c4 |  | checkpoint | Second Fix Completed
checkpoint-status | 7573b449-0875-49fd-b63f-9d11ba7e2123 |  | checkpoint | Flooring inspection completed & issues closed out
checkpoint-group | deef86cb-65db-4808-9293-bb7d04579cae |  | section | Ceiling Grid Checklist
checkpoint-status | 1f32fb89-f683-4b92-b762-0b588f766c66 |  | checkpoint | Service markout completed, checked and acceptable (clashes considered)
checkpoint-status | 2bd46fa6-199a-4abb-9d00-8795396b71ca |  | checkpoint | Ceiling Height confirmed
checkpoint-status | c7ac63c9-696b-4e2c-9723-349b9ae27ca4 |  | checkpoint | Appropriate fixings used and installed as per required specification
checkpoint-status | 35497703-1294-423f-9a4f-76c7b3ad1272 |  | checkpoint | Appropriate spacings for respective grid elements
checkpoint-status | df92db98-9385-47e5-a5fe-1fe43aa0e234 |  | checkpoint | All ceiling grid completed in respective area to required specification (Attach photograph of respective completed grid)
checkpoint-status | 7db36723-206a-43ed-a501-5ce046d676b4 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group | 53c22b92-a313-4087-8ba8-6079e416b64a |  | section | Ceiling Tile Checklist
checkpoint-status | 818be84c-beab-49f7-9f64-ae74c2bc5723 |  | checkpoint | Correct tiles installed as per design
checkpoint-status | a6c7034c-e134-4621-8b42-540571959c8d |  | checkpoint | Services tiles installed, clean & tidy
checkpoint-status | e7bb5b64-5207-40b9-9c54-c5ebf1bb254f |  | checkpoint | All other tiles installed, clean & tidy
checkpoint-status | 97733a87-8ca0-405d-9cf3-54c403234279 |  | checkpoint | All tiles installed, mark/damage free and area completed to required specification (attach relevant photos)
checkpoint-status | 416f4b7c-49dd-4175-9f84-8219bec0fd1e |  | checkpoint | All tiles installed and area left clean and tidy (attach relevant photos)
checkpoint-status | b9292b5f-07b3-428a-90b7-1ec032c6b3c7 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group | 55f5f019-1f03-4327-af1e-9e7f8b46f34c |  | section | Second Fix Completion
checkpoint-status | cbdfc3fb-fa5d-4905-b8df-8c11ecd847f8 |  | checkpoint | All Second Elements completed
checklist-flat | 962d481a-7587-42ff-ae23-a9c1947aae24 |  | checklist | Consultant Inspection - |  |  |  |  | Yes | Add Consultant Inspection Checklist (V3) | c66e680a-ead9-4eae-a6ea-7894d70404ab
checkpoint-status | 3604c82c-1a09-4913-a688-1069e86dc7f5 |  | checkpoint | Consultant inspection completed, attached and any relevant observations closed out
text | 7b7a025d-81fa-4409-9ef9-3281b2d64523 |  | textbox | Date of Inspection
text | dd36bd0b-3ee0-4704-912f-3f8f961a2cb6 |  | textbox | Type of Inspection
text | da74bdd5-b086-41a1-94ef-12814f41c3f5 |  | textbox | Area inspection relates to
boolean | e495e118-490c-453e-af9d-13b99904e2dc |  | tickbox | Consultant Inspection attached
button | 0f8e78cc-ac2e-4458-b897-ef644c2cb994 |  | button | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed) | PASS, N/A
label | 1f26a12b-97a7-4354-afab-298bf48ac079 |  | note | "PASS" once corrective closeout evidence has been attached
label | 5b90254d-0b5f-40ab-b626-60f2f7e09379 |  | note | If there are no corrective action requirements select "N/A"
text | 3d06351b-6af4-431a-909b-5a78ef041b49 |  | textbox | Corrective Actions (listed here if required)
holdpoint | 4fa66bbd-2478-44a5-b5e5-6f6d88c66db2 |  | signoff | Request Signoff
checklist-flat | e4ee226c-3085-4005-aef3-8b9111e368b6 |  | checklist | Insulation Checklist prior to lining |  |  |  |  | Yes | Insulation Checklist | cabb08cc-75a3-4da7-9367-f0cf66bdde36
checkpoint-status | 386c2fc3-4e64-4b98-a6a3-f68d2e25eafe |  | checkpoint | Area accessible, substrate acceptable and approval to start works (If not comment below)
checkpoint-status | 762efc24-a886-4858-8e98-ccffa1243aec |  | checkpoint | All delivered materials checked & aligning with consented design and specifications prior to install
checkpoint-status | 25e727ea-8f12-4cfd-a3d7-5ef979b31897 |  | checkpoint | General photos, comments and observations during insulation install (Add below)
checkpoint-status | 17d74435-5fd1-46ea-a020-08e35e783654 |  | checkpoint | Double check product once installed & attach relevant evidence
label | 4ab13c4d-f07f-5143-9697-0314dab6fe2c |  | note | Correct product & R value as per specification (R-Value label attached to wall)
label | 08098abd-6948-5ca0-a3f5-9e3facc33379 |  | note | Fitting Snug
label | dc63fa94-5b55-554d-bc2a-de599675b116 |  | note | Correct orientation (if applicable)
checkpoint-status | 26778936-6905-45d9-be7e-33a7a500547b |  | checkpoint | All Insulation completed correctly to specification & within tolerance in respective area(s) (Photographic evidence provided)
label | 78d13afb-4751-57b0-9a4e-18bc4ac2587f |  | note | FINAL - Pass when work(s) are completed (Any issues please comment below) Then SEND report to Main Contractor
checklist-sectioned | ce346fba-31ce-4087-aad1-2621d21dd875 |  | checklist | Steel Erection Checklist (Trade's QA) |  |  |  |  | Yes | Steel Erection Checklist (Trade's QA) | d6bde0bf-fd69-4d60-be19-73d86cd10266
checkpoint-group | 29ad6f7b-4e29-4981-8b74-92004e6196f1 |  | section | Pre-Erection Checks
checkpoint-status | 43ae3130-dca5-4bd0-be26-7bc878d8233f |  | checkpoint | Latest drawings available, checked and referenced
text | 4f325bda-2a89-5271-b8b5-c9e5cf93bf38 |  | textbox | Input drawing/revision number
checkpoint-status | 09106c43-d1fe-4f99-b11c-51fda4a42c93 |  | checkpoint | Relevant steel delivered, checked and correct
boolean | 060ec966-ea3f-513e-9e0c-980fe6eab359 |  | tickbox | Correct elements received
boolean | 9a0db890-e0fb-5904-85fe-4e7932b3f5be |  | tickbox | Coating condition acceptable
boolean | 3a205a06-4a5d-5fca-a604-ea1b3beb5787 |  | tickbox | Dispatch docket correct and photographed
checkpoint-status | b36f0c23-82bb-4c61-8178-259517202cdf |  | checkpoint | Work area acceptable
checkpoint-status | 951dde63-aab3-44ec-85b9-c84fa2e9b0b3 |  | checkpoint | Checked for set out and alignment
checkpoint-status | 55e213d2-e8e4-434b-bfc9-89669e14f594 |  | checkpoint | Checked for Level and RL
checkpoint-status | 05a30465-a553-4cd0-8a2b-df2a4fa67f8b |  | checkpoint | Hold down bolts / cast-in items checked and approved (location and size)
checkpoint-status | 64da22ec-24b5-4918-8e6e-990200c2f80f |  | checkpoint | Pre-erection checks
boolean | d770f8cd-96cc-5e05-8d20-79cbf4eed1c5 |  | tickbox | All steel tags match drawings marks numbers
boolean | 13859e7c-f666-55cb-b679-39cbf27c3fe5 |  | tickbox | Sufficient steel on site for erection to proceed
checkpoint-status | 98be9f1c-fb7b-4ebb-8aad-930fef0a699a |  | checkpoint | Steel hoisted as per agreed lifting procedure
checkpoint-status | 5125cda8-aa7a-475f-bb3f-ede4411e43c1 |  | checkpoint | Steel secured before taking off hook
checkpoint-status | 609dd578-6f1c-41d0-895f-4f03c5dc2425 |  | checkpoint | Soft slings used instead of chains, if required
checkpoint-status | 02d2aa9d-6f36-4189-81ff-00249d95f8d2 |  | checkpoint | Crane operated within rating chart capacity
checkpoint-group | e3de4d93-adee-4607-be8a-6269a0af2de7 |  | section | Steel Erection Checks
checkpoint-status | d1ef064d-dff0-42a7-82e0-6e28fa153ba6 |  | checkpoint | Correct location and orientation
checkpoint-status | 633bb527-e509-4481-af83-5f4cfe3e442f |  | checkpoint | Steel erected level, plumb and correct pitch
checkpoint-status | 97900103-615f-48d7-866b-831d370d31a0 |  | checkpoint | Temporary props, turfers, bracing etc. installed/removed
checkpoint-status | e047c2fd-f2b1-49a8-b9e1-d30eb9df61f3 |  | checkpoint | All fixings appropriately installed
checkpoint-status | 0a6fe108-4034-419c-9a9d-c9b22c47a658 |  | checkpoint | Epoxy and mechanical anchors drilled to correct depths
checkpoint-status | f2e5843d-a8b4-4f56-bdc1-f02b00b20fdb |  | checkpoint | Epoxy and mechanical anchors tightened
checkpoint-status | 97bfb39e-fca9-4f3d-bfa9-1de7197293d7 |  | checkpoint | Taper washers installed, if required
checkpoint-status | d0735b5b-a0d6-44ba-99f1-27e57d33cd72 |  | checkpoint | All bolts secure / correctly tensioned
checkpoint-status | cd7b399b-47b3-41fc-a4a1-53b6c3483995 |  | checkpoint | All on-site welding completed correctly
checkpoint-status | 4845ab07-f969-4cb6-ad45-4247cbbd7984 |  | checkpoint | Damaged coatings repaired / touched-up
checkpoint-status | c8373fcd-9ff3-40b3-a484-5a56ed68c58f |  | checkpoint | Request Subcontractor Sign Off
holdpoint | c246fd15-8af1-40b4-8b76-44a416c0eb07 |  | signoff | Request Sign Off
checkpoint-status | e6fcab65-bf4f-43c2-b2d9-7f9ecf92d48e |  | checkpoint | Request Hawkins Sign Off
holdpoint | 37a24b9a-b7f9-4fd0-a90e-0e4ef9886e5d |  | signoff | Request Sign Off
checkpoint-group | f666b722-3354-40bf-b8b6-6db4ad43c4ca |  | section | Intumescent Painting Checklist
checkpoint-status | d5210e04-6a3a-41c3-9938-dccf032f7996 |  | checkpoint | Steel Erection completed and approval given to apply Intumescent Paint
checkpoint-status | 125f68ce-20a2-4014-97f5-f54a90d3ad08 |  | checkpoint | Paint specifications and product checked
checkpoint-status | 58bda4a9-17c9-41c4-86f7-7e56493fa385 |  | checkpoint | Paint applied using correct methodology
checkpoint-status | 0b1d0cb1-9c71-4cd6-887c-3965db3a0547 |  | checkpoint | General photos, comments and observations during paint application
holdpoint | 56a75023-ef35-41d9-9fca-d770a5085d56 |  | signoff | Request Subcontractor Sign Off
checklist-sectioned | f09600d0-a4e2-4670-bce5-aab8897a1b2f |  | checklist | Steel Erection |  |  |  |  | Yes | SYS Steel Erection Checklist (Trade's QA) | e0c5d025-89dd-4586-8702-03b412695faf
checkpoint-group | 21957e03-696c-4799-90d5-be7150c8fc60 |  | section | Pre-Erection Checks
checkpoint-status | 44fe3a17-cc0e-4e7b-a855-fa999ebf5386 |  | checkpoint | Latest drawings available, checked and referenced
text | 68fd7947-256f-57d5-9529-455376223910 |  | textbox | Input drawing/revision number
checkpoint-status | 8464e773-b977-430f-b0fc-e41fcdc1ba02 |  | checkpoint | Relevant steel delivered, checked and correct
boolean | 5123599a-8d3a-5ccb-a36e-69a06a3a2d7f |  | tickbox | Correct elements received
boolean | 15a96b6b-4bba-5fc8-b213-33f174d6eb89 |  | tickbox | Coating condition acceptable
boolean | f5bd407c-3a1b-563f-9ee9-22be3b06dc8b |  | tickbox | Dispatch docket correct and photographed
checkpoint-status | 70d74b1f-3096-44f5-81ac-b1a87baa32d8 |  | checkpoint | Work area acceptable
checkpoint-status | e0dc8ed4-0c6f-4be7-ace0-3711bf03c468 |  | checkpoint | Checked for set out and alignment
checkpoint-status | 08882163-1145-4498-8371-77a9ef282d85 |  | checkpoint | Checked for Level and RL
checkpoint-status | 9c40a9ee-09b8-4d92-adde-d47ec974702b |  | checkpoint | Hold down bolts / cast-in items checked and approved (location and size)
checkpoint-status | de2b198f-32a0-4f91-a787-d0d617ca4039 |  | checkpoint | Pre-erection checks
boolean | 793b818d-bdc0-5345-b304-abcfd4908263 |  | tickbox | All steel tags match drawings marks numbers
boolean | fc08532b-8473-53a6-8870-d4ec9e7fcf92 |  | tickbox | Sufficient steel on site for erection to proceed
checkpoint-status | 51dd7d74-a5d9-4bde-a67f-b235643cee27 |  | checkpoint | Steel hoisted as per agreed lifting procedure
checkpoint-status | fe0e6362-44dc-4df0-881c-224cfc83e2b6 |  | checkpoint | Steel secured before taking off hook
checkpoint-status | 9f6cb367-c871-47d2-949f-d7f408b572b5 |  | checkpoint | Soft slings used instead of chains, if required
checkpoint-status | 4093e974-ef9e-4b82-95e7-4a56ba067159 |  | checkpoint | Crane operated within rating chart capacity
checkpoint-group | 23a9a0a0-c043-45bf-afc7-2ebfd718d3b7 |  | section | Steel Erection Checks
checkpoint-status | fd5836fa-9281-4be0-bb0c-67dd3fa6909f |  | checkpoint | Correct location and orientation
checkpoint-status | 79a2d5fa-89a2-42df-bc9c-88818bb5b496 |  | checkpoint | Steel erected level, plumb and correct pitch
checkpoint-status | ca13184d-89ff-4f71-8816-6ebb68815f4f |  | checkpoint | Temporary props, turfers, bracing etc. installed/removed
checkpoint-status | 1606fd1f-3ecf-4ed0-9f74-49073103e13b |  | checkpoint | All fixings appropriately installed
checkpoint-status | 33606973-2fb6-4cef-907d-071074af22fe |  | checkpoint | Epoxy and mechanical anchors drilled to correct depths
checkpoint-status | 8e084f82-3b13-4b6d-ac34-534a1956fc89 |  | checkpoint | Epoxy and mechanical anchors tightened
checkpoint-status | 84951983-a70d-4840-873d-246b3eb21ceb |  | checkpoint | Taper washers installed, if required
checkpoint-status | 091b3767-8a59-4f4b-ad6a-4b68b776312d |  | checkpoint | All bolts secure / correctly tensioned
checkpoint-status | cc94353d-8458-4e00-b47d-09106015ed34 |  | checkpoint | All on-site welding completed correctly
checkpoint-status | aba10e97-2af6-46d2-bbaa-98ed4e66944c |  | checkpoint | Damaged coatings repaired / touched-up
checkpoint-group | e820ca53-09ad-41a9-9d0c-3dc44b0b0f0a |  | section | Intumescent Painting Checklist
checkpoint-status | 277e88f4-e1bd-456b-af80-86d41adfa025 |  | checkpoint | Steel Erection completed and approval given to apply Intumescent Paint
checkpoint-status | 16681a38-ba8d-4406-91c6-bce3f6a3e2ad |  | checkpoint | Paint specifications and product checked
checkpoint-status | af64669b-906f-4b34-abf8-a8d4a2729461 |  | checkpoint | Paint applied using correct methodology
checkpoint-status | 2e3a932d-87cd-4052-a4b0-d12e592830c6 |  | checkpoint | General photos, comments and observations during paint application
checklist-flat | 684c6b96-3c4d-46ac-b4b2-55d5824de8ea |  | checklist | Name: |  |  |  |  | Yes | Add document | e6c3748b-4cca-4719-8ff4-fb4c03c199e4
checkpoint-no-status | 6706b94d-6335-41e5-a01f-09b70eb8b201 |  | checkpoint | Attach document here
checklist-flat | c92ec4d9-9c6f-4980-9c09-47cdcbc08905 |  | checklist | Intumescent Painting Checklist |  |  |  |  | Yes | Intumescent Painting Checklist | e7d12873-f940-41de-a02d-ae22345da6c4
checkpoint-status | 97fe0878-a6e0-4b68-a4c1-96d5eac9dd12 |  | checkpoint | Steel Erection completed and approval given to apply Intumescent Paint
checkpoint-status | 38467d07-0b96-48de-a48f-c575d309ae0b |  | checkpoint | Paint specifications and product checked
checkpoint-status | 592164ea-8b02-487d-82a3-8eec67e4de26 |  | checkpoint | Paint applied using correct methodology
checkpoint-status | f2958dcb-f38c-47ed-bae4-2b8f3b0d1534 |  | checkpoint | General photos, comments and observations during paint application
checklist-sectioned | 67789340-3bdb-47a1-8184-e2325232d314 |  | checklist | GIB Lining, Stopping, Passive fire (Audit) |  |  |  |  | Yes | GIB Lining, Stopping, Passive fire (Audit) | f09b15f5-cf8b-47e0-8445-9d82bf39eb09
checkpoint-group | faa0dc95-b50e-4b2e-80da-9a3a5766fcb3 |  | section | Gib Lining Checklist
checkpoint-status | 54e941a5-e5b2-46a0-b44c-88f305672e11 |  | checkpoint | All preline services completed and approval given to line
boolean | a068d252-049a-5d27-b07e-9b97f35a2fc7 |  | tickbox | moisture content checked, recorded and acceptable
checkpoint-status | 11c6df23-319b-4d6a-8a59-6c49c030e509 |  | checkpoint | Correct lining (Checked and approved)
checkpoint-status | ce811034-a285-4df8-8992-648b978b9177 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 2b10c3f1-005f-4353-8363-fe84e117cd77 |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | eb88c1ea-be2e-4f80-a8fd-e07795bc0a62 |  | checkpoint | check if service are required in this location
checkpoint-status | 47375701-c1a4-443e-a36a-4d4d655a1cac |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | aff7b322-5bdb-48f3-b906-5154db542257 |  | checkpoint | All lining completed, checked and approved
holdpoint | 1e634be3-4afc-4af0-9cda-45c222afc278 |  | signoff | Request Subcontractor Sign Off
checkpoint-group | 98e5b818-fc34-4353-b060-990ac9a06638 |  | section | Gib Stopping Checklist
checkpoint-status | 45a9ffa0-a79a-4c04-a2d9-5d6ee216a5da |  | checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint-status | 2745dd1b-8caf-419f-9dfa-2ba0b796db3e |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status | 68d6d9a5-4edf-4418-b391-bc07012b2d51 |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status | f30585f0-ee4c-4569-886e-d1f50e620c3e |  | checkpoint | Adequate drying time between applications & No visible bubbling
checkpoint-status | 890e7dc9-5ecd-4fcf-ac61-e319c9b67a4b |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 5975d043-8d65-4e74-b932-fb8c991e68f0 |  | checkpoint | All Stopping completed and specified level of finish achieved
holdpoint | 1c275ec1-bad5-4a3b-8999-af19783f6bd7 |  | signoff | Request Subcontractor Sign Off
checkpoint-group | b653cf20-6b35-4fd1-926b-8107d130daa7 |  | section | Passive Fire Checklist
checkpoint-status | b789d35e-87e2-4a11-a655-a16d1f4ffe4a |  | checkpoint | Trades QA received
checkpoint-status | ca794129-b557-47e6-b0bb-47d5bed22450 |  | checkpoint | All Passive fire elements completed, reviewed and approved
boolean | 3d6852e2-faa6-58e9-8cde-0f57f374b890 |  | tickbox | Fire Protection Consultant inspection completed & issued closed out
boolean | c164f575-df1d-50d9-ba7d-1c0a7e8a3226 |  | tickbox | Council inspections carried out & attached in council folder
checklist-sectioned | e85a7c62-8f0a-4c4e-8bf0-bf546d884968 |  | checklist | Timber Framing |  |  |  |  | Yes | SYS Timber Framing Checklist | f1837e69-c7da-414f-aa12-8b39c2e92f89
checkpoint-group | adfe6ea5-55f8-4f33-988e-a1f75bfdb6f2 |  | section | Framing
checkpoint-status | 05fe3627-60f9-4a4c-90fd-f04ae0c08d67 |  | checkpoint | Room set outs and wall locations consistent with approved plans
checkpoint-status | 960142e3-833e-4e53-af39-bf522fa0aa15 |  | checkpoint | Check framing for straigthness
checkpoint-status | 779ee2a0-5ee7-4f83-b359-da8e11fa80db |  | checkpoint | bracing installed
checkpoint-status | 66abc54f-be58-48b9-bfa5-6406b59df553 |  | checkpoint | Nogs installed correctly
checkpoint-status | 5a0ad51a-71a8-46a6-8f18-553b8212856d |  | checkpoint | General photos during installion
checkpoint-status | b62b7829-56b2-4ff7-8494-11daae23e7d3 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group | e57059e7-e3fc-41b9-a575-1ff54d344d20 |  | section | COMPACT - Insulation Checklist prior to lining
checkpoint-status | 36edd3f7-956e-4775-b313-3977abe878b3 |  | checkpoint | Area accessible, substrate acceptable and approval to start works (If not comment below)
checkpoint-status | f744f21b-26bf-4a3e-a5cb-88c0facd5a88 |  | checkpoint | All delivered materials checked & aligning with consented design and specifications prior to install
checkpoint-status | 693e9ed4-1a08-45a1-b66c-7a873e2ac179 |  | checkpoint | General photos, comments and observations during insulation install (Add below)
checkpoint-status | 62185d6f-7174-444d-b9e8-46aff3f86ba2 |  | checkpoint | Double check product once installed & attach relevant evidence
label | bcd7fba3-c7c3-52b8-8831-ef9de8241acf |  | note | Correct product & R value as per specification (R-Value label attached to wall)
label | b4eb0fe4-eadf-5373-9148-ed32a0229f74 |  | note | Fitting Snug
label | be315ace-9448-5a98-8c56-5067b4a8cfa4 |  | note | Correct orientation (if applicable)
checkpoint-status | 91f7e113-cc74-4b8c-94f8-7d7af6d01666 |  | checkpoint | All Insulation completed correctly to specification & within tolerance in respective area(s) (Photographic evidence provided)
checklist-sectioned | ab39052a-eec5-451e-98e3-c296a47e8961 |  | checklist | GIB Lining, Stopping, Passive fire (Audit) |  |  |  |  | Yes | SYS GIB Lining, Stopping, Passive Fire Checklist | f514712c-b2e0-447b-a329-031d2d2fa7bb
checkpoint-group | 37db8b4a-fa0c-4f6f-b284-867dadff0573 |  | section | Gib Lining Checklist
checkpoint-status | 447121c4-a965-4f77-a680-06becfa39c47 |  | checkpoint | All preline services completed and approval given to line
boolean | 44f8df5b-cb4d-50af-a2eb-6cbb21106822 |  | tickbox | moisture content checked, recorded and acceptable
checkpoint-status | 5d43d9cb-d8bb-4e15-a838-eda4d9775b4c |  | checkpoint | Correct lining (Checked and approved)
checkpoint-status | 2059fbec-d1fb-42ca-ba3f-17694418d99d |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | a8865230-8f78-442e-960a-1b48bd51a0d2 |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | f0d086d0-c3c9-4c29-a364-5ce4c411a4fd |  | checkpoint | check if service are required in this location
checkpoint-status | a5ccc9f9-e418-41cb-93fe-332561d2d2aa |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | e1c59606-7650-45cd-bf09-ee5df0ecf7d8 |  | checkpoint | All lining completed, checked and approved
checkpoint-group | 832b7446-0879-4a9c-a28f-7b7917bab334 |  | section | Gib Stopping Checklist
checkpoint-status | 7960d622-17a2-4ed0-a6c3-a9cd3dc0211e |  | checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint-status | 7facc4cd-0742-4ff7-81d8-5f904111564c |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status | ebd5dc3d-6381-4034-813b-dd0399d50bf0 |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status | 628574ec-9574-4be7-a3fb-2bafc1c961f3 |  | checkpoint | Adequate drying time between applications & No visible bubbling
checkpoint-status | 339a9a6d-75e1-4a56-bfb7-5ec744a51295 |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status | 14f53847-42ce-4557-bee0-72e01e17b185 |  | checkpoint | All Stopping completed and specified level of finish achieved
checkpoint-group | bc1d7d1d-6f1d-4211-bdef-6c1f0525ee74 |  | section | Passive Fire Checklist
checkpoint-status | 6ff386b7-7f42-486b-8c2d-adb99b4f284c |  | checkpoint | Trades QA received
checkpoint-status | 9eaaef6e-f5c0-480f-972c-70365f77cc88 |  | checkpoint | All Passive fire elements completed, reviewed and approved
boolean | 0af48d62-cda0-590b-a68d-f83104801b08 |  | tickbox | Fire Protection Consultant inspection completed & issued closed out
boolean | 9c1b8280-b882-5e88-9491-5e131df57f56 |  | tickbox | Council inspections carried out & attached in council folder
checklist-sectioned | 682c2934-abc6-44d7-b723-ae68b5b659d4 |  | checklist | Timber Framing |  |  |  |  | Yes | Timber Framing | f7da6d34-94d4-4e25-b0f6-326555da9133
checkpoint-group | ca6ecf0b-388f-472a-927f-e0853781431b |  | section | Framing
checkpoint-status | 28d7a954-fc28-495b-b7b0-31ea3fd043ca |  | checkpoint | Room set outs and wall locations consistent with approved plans
checkpoint-status | 795b09f6-e117-4470-9f01-94dfa0188c42 |  | checkpoint | Check framing for straightness
checkpoint-status | 501345b1-1cd5-4834-ab8d-b851ef79d4c4 |  | checkpoint | bracing installed
checkpoint-status | 9efd188c-be1b-4c5a-9022-29f6e6d187dd |  | checkpoint | Nogs installed correctly
checkpoint-status | 01466eeb-0250-4dcc-8f82-736836f49748 |  | checkpoint | General photos during installation
checkpoint-status | aa74b971-11d8-4729-8a0b-e6c3a7ffc95a |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint | 2f75f1f1-fce9-4d74-9136-2156ff87f5ff |  | signoff | Request Subcontractor Sign Off
checkpoint-group | 0f192e8f-f94a-41a2-aef8-ea2e14f9b6df |  | section | COMPACT - Insulation Checklist prior to lining
checkpoint-status | db5ac88e-d0d2-4403-8aa8-dfb4f2a06582 |  | checkpoint | Area accessible, substrate acceptable and approval to start works (If not comment below)
checkpoint-status | a563d4fe-0dfe-41c3-bac4-a58a49b4a4e4 |  | checkpoint | All delivered materials checked & aligning with consented design and specifications prior to install
checkpoint-status | 09775d3b-0ae5-4004-a51a-7dd8c7817c7b |  | checkpoint | General photos, comments and observations during insulation install (Add below)
checkpoint-status | b07d0774-64d5-4528-9f12-5dc3bad806e7 |  | checkpoint | Double check product once installed & attach relevant evidence
label | 49d2dc6e-1198-5757-a826-f51f7e770722 |  | note | Correct product & R value as per specification (R-Value label attached to wall)
label | 7afc30e1-2947-5ae3-ac30-a6b634e5628a |  | note | Fitting Snug
label | ba843fe3-eac1-515c-9d80-fc89f1d983eb |  | note | Correct orientation (if applicable)
checkpoint-status | 8c2a00c2-b58e-4936-96c0-0eba386ab103 |  | checkpoint | All Insulation completed correctly to specification & within tolerance in respective area(s) (Photographic evidence provided)
label | c5ad79c8-5d74-505b-8711-fe1fa2e65423 |  | note | FINAL - Pass when work(s) are completed (Any issues please comment below) Then SEND report to Main Contractor
holdpoint | 0a9fb4db-dc51-46ae-a66c-92b3f23f06ae |  | signoff | Request Subcontractor Sign Off