## Table 1
Attention: Lockwood Flooring 1/8 Vella Drive Sunshine West VIC 3012
Project Name: Footscray Commercial Building D
Builder: Multiplex
Installer: Lockwood Flooring Australia Pty Ltd
CARPET - INSPECTION TEST PLAN
Task Complete Pass Date Sign
Working to latest plan revisions and check latest correspondence 2 Prior works checks Area free of building debris and trade tools Walls plastered and first coat of paint All adjacent finishes completed and ready to be finishes. Area to be flagged if LF cannot finish 100% 3 Specification checks - Correct materials as per finishes schedule and sample approvals 4 Installation procedure as per manufactures recommendations and AUS standards - Barridcaded areas Vacuum area and minor patch as required Apply Intertact Pressure Sensitive adhesive Installation pattern and direction followed Installation complete and rubbish placed in bins provided 5 Protection - woven plastic 6 Confirm material warranty applies 7 Confirm installation warranty 12 months applies 8 Care and maintenance as per O&Ms
Level Area Complete Pass Date Sign Notes
1