## Table 1
Attention: Lockwood Flooring 1/8 Vella Drive, Sunshine West VIC 3012
Project Name: Victoria University Building E
Builder: Multiplex
Installer: Lockwood Flooring Australia Pty Ltd
Timber - INSPECTION TEST PLAN
Task Complete Pass Date
Working to latest plan revisions and check latest correspondence 2 Prior works checks Area free of building debris and trade tools Walls plastered and first coat of paint All adjacent finishes completed and ready to be finishes. Area to be flagged if LF cannot finish 100% Specification checks - Correct materials as per finishes schedule and sample approvals 4 Installation procedure as per manufactures recommendations and AUS standards - Barridcaded areas Vac and clean area Floor prep (grind, MB, 3mm) as required Ensure joinery kickers, skirting boards etc removed where possible Set out Rezil sleeper system as per manufacturer recommendations Set out solid timber to sleepers Install timber with recommended adhesive and secret nails Allow for expansion gaps at perimeter and to fixtures Sand and seal timber as per manufacturer recommendations 5 Protection - corflute plastic 6 Confirm material warranty applies 7 Confirm installation warranty 12 months applies
Lockwood Flooring ¦ 1/8 Vella Drive, Sunshine West VIC 3020 ¦ lockwoodflooring.com.au
Level Area Complete Pass Date Sign Notes
Lockwood Flooring ¦ 1/8 Vella Drive, Sunshine West VIC 3020 ¦ lockwoodflooring.com.au
8
Care and maintenance as per O&Ms
1
3