## Table 1
Attention: Lockwood Flooring 1/8 Vella Drive Sunshine West VIC 3012
Project Name: Victoria University Building E
Builder: Multiplex
Installer: Lockwood Flooring Australia Pty Ltd
VINYL - INSPECTION TEST PLAN
Task Complete Pass Date Sign
Working to latest plan revisions and check latest correspondence 2 Prior works checks Area free of building debris and trade tools Walls plastered and first coat of paint All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100% 3 Specification checks - Correct materials as per finishes schedule and sample approvals 4 Installation procedure as per manufactures recommendations and AUS standards - Barridcaded areas Grind, vac and clean Apply moisture barrier as required Prime and self level as quoted (3mm) Set out vinyl to minimise waste and cross joins Apply cove fillet to perimeter as required Install vinyl and cove with recommended adhesive Heavy roll finished floor 6 Protection - corflute plastic 7 Confirm material warranty applies 8 Confirm installation warranty 12 months applies 9 Care and maintenance as per O&Ms
Level Area Complete Pass Date Sign Notes
1