## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building A & B)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
checkpoint | Area free of building debris and trade tools
checkpoint | Walls plastered and first coat of paint
checkpoint | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100%
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
checkpoint | Barricaded areas
checkpoint | Vacuum area and minor patch as required
checkpoint | Apply Intertact Pressure Sensitive adhesive
checkpoint | Installation pattern and direction followed
checkpoint | Installation complete and rubbish placed in bins provided
checkpoint | Install 150mm feather edge skirting
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Vinyl ITP | [5 empty] | Vinyl ITP (Building C)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
checkpoint | Area free of building debris and trade tools
checkpoint | Walls plastered and first coat of paint
checkpoint | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100%
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
checkpoint | Barricaded areas
checkpoint | Grind, vac and clean
checkpoint | Apply moisture barrier as required
checkpoint | Prime and self level as quoted (3mm)
checkpoint | Set out vinyl to minimise waste and cross joins
checkpoint | Apply cove fillet to perimeter as required
checkpoint | Install vinyl and cove with recommended adhesive
checkpoint | Heavy roll finished floor
checkpoint | Protection - corflute plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building C)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
checkpoint | Area free of building debris and trade tools
checkpoint | Walls plastered and first coat of paint
checkpoint | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100%
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
checkpoint | Barricaded areas
checkpoint | Vacuum area and minor patch as required
checkpoint | Apply Intertact Pressure Sensitive adhesive
checkpoint | Installation pattern and direction followed
checkpoint | Installation complete and rubbish placed in bins provided
checkpoint | Install 150mm feather edge skirting
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building D)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
checkpoint | Area free of building debris and trade tools
checkpoint | Walls plastered and first coat of paint
checkpoint | All adjacent finishes completed and ready to be finishes. Area to be flagged if LF cannot finish 100%
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
checkpoint | Barricaded areas
checkpoint | Vacuum area and minor patch as required
checkpoint | Apply Intertact Pressure Sensitive adhesive
checkpoint | Installation pattern and direction followed
checkpoint | Installation complete and rubbish placed in bins provided
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Vinyl ITP | [5 empty] | Vinyl ITP (Building D)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
checkpoint | Area free of building debris and trade tools
checkpoint | Walls plastered and first coat of paint
checkpoint | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100%
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
checkpoint | Barricaded areas
checkpoint | Grind, vac and clean
checkpoint | Apply moisture barrier as required
checkpoint | Prime and self level as quoted (3mm)
checkpoint | Set out vinyl to minimise waste and cross joins
checkpoint | Apply cove fillet to perimeter as required
checkpoint | Install vinyl and cove with recommended adhesive
checkpoint | Heavy roll finished floor
checkpoint | Protection - corflute plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building E)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
checkpoint | Area free of building debris and trade tools
checkpoint | Walls plastered and first coat of paint
checkpoint | All adjacent finishes completed and ready to be finishes. Area to be flagged if LF cannot finish 100%
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
checkpoint | Barricaded areas
checkpoint | Vacuum area and minor patch as required
checkpoint | Apply Intertact Pressure Sensitive adhesive
checkpoint | Installation pattern and direction followed
checkpoint | Installation complete and rubbish placed in bins provided
checkpoint | Install 150mm feather edge skirting
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Timber ITP | [5 empty] | Timber ITP (Building E)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
checkpoint | Area free of building debris and trade tools
checkpoint | Walls plastered and first coat of paint
checkpoint | All adjacent finishes completed and ready to be finishes. Area to be flagged if LF cannot finish 100%
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
checkpoint | Barricaded areas
checkpoint | Vac and clean area
checkpoint | Floor prep (grind, MB, 3mm) as required
checkpoint | Ensure joinery kickers, skirting boards etc removed where possible
checkpoint | Set out Rezil sleeper system as per manufacturer recommendations
checkpoint | Set out solid timber to sleepers
checkpoint | Install timber with recommended adhesive and secret nails
checkpoint | Allow for expansion gaps at perimeter and to fixtures
checkpoint | Sand and seal timber as per manufacturer recommendations
checkpoint | Protection - corflute plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Vinyl ITP | [5 empty] | Vinyl ITP (Building E)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
checkpoint | Area free of building debris and trade tools
checkpoint | Walls plastered and first coat of paint
checkpoint | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100%
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
checkpoint | Barricaded areas
checkpoint | Grind, vac and clean
checkpoint | Apply moisture barrier as required
checkpoint | Prime and self level as quoted (3mm)
checkpoint | Set out vinyl to minimise waste and cross joins
checkpoint | Apply cove fillet to perimeter as required
checkpoint | Install vinyl and cove with recommended adhesive
checkpoint | Heavy roll finished floor
checkpoint | Protection - corflute plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms