## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-139-RAIL-BRUNT-Track Construction
ITP Description: |  | Track Construction
Project: |  | Brunt Rd
Discipline (e.g. CIV/STR/RAIL: |  | RAIL
Revision Number: |  | 0
Revision Date: |  | 2024-03-14
ITP created by: |  | Mac Cameron
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP to be used at Brunt Rd Project Only
Inspection & Test Plan - Track Construction
|  |  | Document Title: ITP-139-RAIL-BRUNT-Track Construction | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-03-14
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Drawing Pack - Rail Track and Civil | GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Railway Track Materials – Part 1: Steel Rails | AS 1085.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Welding Rail Steels | AS 1085.2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Concrete Sleepers Specification | A1504 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.5 | Track Geometry Tolerances | A1303 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.6 | Ballast Supply Specification | A1341 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.7 | Transit Space Clearances | A1536 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.8 | Track Design And Construction | A1545 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.9 | Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure | A4598 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.10 | Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure | A4597 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.11 | Aluminothermic Weld and Stressing - Inspection and Test Plan Template | A7949 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.12 | PTC Heavy Rail Track Construction Standards | N/A - no document reference number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.13 | PTC Heavy Rail Track Construction Standards Drawing | F598 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.14 | Earthworks & Formation Specification | L1-CHE-SPE-178 (VERSION 3) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.15 | Earthworks & Formation Standard | L1-CHE-STD-029 (VERSION 4) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Supply of 60mm Ballast | A1341 Ballast Supply Specification Section 4.2.2 | The Ballast supplied must be tested and meet requirements in MTM standard Ballast Supply Specification (A1341) Table 3 | Visual Measure Document Review | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
2.2 | Supply of FDCS Sleepers | A1303 Track Geometry Tolerances Section 8.1.13 A1504 Concrete Sleepers Specification Table 2 | Sleepers supplied must be type approved by MTM and in accordance with the relevant standard. | Visual Measure Document Review | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
2.3 | Supply of 53kg/m Rail | One Steel Certificate Flashbutt Weld Reports | AS 1085.1 Railway Track Materials – Part 1: Steel Rails AS 1085.20 Welding Rail Steels Section 2 | Visual Measure Document Review | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: One Steel Certificate Flashbutt Weld Reports Delivery Dockets
2.4 | Supply of: -Track Jewellery -Geofabric |  | To be type approved by MTM. To be inspected upon delivery to have no damage or rust. | Visual Measure | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
3 | Preliminaries - Procedures & Documentation
3.1 | Primary Documentations | A4263 PTDT Form B - Track Certifier Booking Form A1606 Hot Works Procedure | Approved PTDT | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Approved PTDT
3.2 | Pre-Commencement of Work | ITP, Quality Checklist, SWMS | All approved by relevant representative. | Document review and approval | Once (Prior to Works) | HP | SE/PE | This ITP Signed Off Attach: Approved Templates
4 | Pre-Construction Activities
4.1 | Approval of IFC drawings | GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Approved IFC Drawings | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off
5 | Construction Activities
5.1 | Survey Track Alignment | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Correct line and level established for placement of Sleepers and Ballast as per IFC. | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Track Supervisor Track Surveyor | This ITP Signed Off Attach: Survey Records & Photos on site
5.2 | Lay Bottom Ballast | PTC Heavy Rail Track Construction Standards Drawing F598 | Ballast to be placed in 150mm max layers. Bottom Ballast to be left 20-40mm below final design level – Tolerance (under sleeper) -0mm, +25mm | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Track Supervisor Track Surveyor | This ITP Signed Off Attach: Survey Records & Photos on site
5.3 | Place Sleepers | A1303 Track Geometry Tolerances Table 1 A4597 Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure Section 4.8 | Sleepers Square at nominal 685mm ±25mm. 2 concrete sleepers either side of welds Up to 50mm variation in spacing to allow for clearance around a thermit weld (only over two sleepers) | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Track Supervisor Track Surveyor | This ITP Signed Off Attach: Survey Records & Photos on site
5.4 | Rail Installation | A4598 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure Section 4.1.1, 4.1.2 and Table 7 Aluminothermic Weld and Stressing - Inspection and Test Plan | Plain line Aluminothermic welds square and centrally located in beds. Alignment inspection shall be carried out on each weld and record results. Horizontal Alignment ± 0.5mm Vertical Alignment + 0.5mm, - 0.0mm Rail ends identified & clearly marked for visibility of joint. All fastenings must be fully applied. Minimum Closure Length taken as 13. 7meters if not Detailed in A4598 table 7. Complete Aluminothermic Weld and Stressing - Refer to Aluminothermic Weld and Stressing ITP | Visual Inspection Measure | As Task Progresses | HP | SE/PE Track Supervisor | This ITP Signed Off Attach: Photos on site
5.5 | Sleeper Alignment and Rail Jewellery | PTC Heavy Rail Track Construction Standards Drawing F598 | Sleeper alignment complies to square with centreline for tangent track. Rail jewellery secure and installed correctly | Visual Inspection | As Task Progresses | HP | SE/PE Track Supervisor | This ITP Signed Off Attach: Photos on site
5.6 | Tamp New Track | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 A1536 Transit Space Clearances Figure 1 and section 9.2 | Tamp track as per IFC design and within below tolerances: Gauge +3 / -3 Gauge Variation in 2m 4 Line (10m Chord) +4 / -4 Twist (3.5m Chord) +2 / -2 Top (10m Chord) +5 / -5 Cant +5 / -5 General Alignment +15/ -15 A minimum horizontal clearance of 3.0m from track centreline to structure. Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached | Visual Inspection Tamping Geometry Recording Measure / Survey Pickup | Once (Post Tamping) | HP | Tamping Operator Track Surveyor Overhead Engineer Track Supervisor SE/PE | This ITP Signed Off Attach: Photos on site Tamping Geometry Report Survey Records
5.7 | Regulate and Check Ballast profile | A1537 Earthworks And Formation Standard Section 9 PTC Heavy Rail Track Construction Standards Drawing F598 | As per IFC drawings; 405mm from sleeper end tangent track 1 in 1.5 steepest shoulder slope. | Visual Inspection Measure | Once | HP | SE/PE Track Supervisor | This ITP Signed Off Attach: Photos on site
6 | Post-Construction Activities
6.1 | As-Built Survey | As-Built Drawing Management Procedure (A8197) | Track survey to be carried out at completion of works. Track levels compared to IFC and ensure tolerances are met | Survey and Review | Once | HP | Track Surveyor SE/PE | This ITP Signed Off Attach: As-Built survey report
6.2 | Track Certification | MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE | - Track Geometry Conformance Certificate - Track System and Component | Visual Measure Document Review | Once (upon completion of occupation works) | HP | Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure | This ITP Signed Off Attach: Relevant Conformance Certs as per acceptance criteria
6.3 | As-Built Drawings | As-Built Drawing Management Procedure (A8197) | IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM. | Document review and approval | Once | HP | SE/PE | This ITP Signed Off Attach: Redline mark-up drawings
6.4 | Non-conformance Report (NCR) Closure | MTM Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP | SE/PE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /