## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-143-RAIL-BRUNT-Track Formation - Subgrade
ITP Description: |  | Track Formation - Subgrade
Project |  | Brunt Rd
Discipline (e.g. CIV/STR/RAIL: |  | RAIL
Revision Number: |  | 0
Revision Date: |  | 2024-03-25
ITP created by: |  | Mac Cameron
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP to be used at Brunt Rd Project Only
Inspection & Test Plan - Track Formation - Subgrade
|  |  | Document Title: ITP-143-RAIL-BRUNT-Track Formation - Subgrade | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-03-25
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Drawing Pack - Rail Track and Civil | GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Metro Engineering Specifications - Earthworks & Formation Specification | L1-CHE-SPE-178 (VERSION 3) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Metro Engineering Specifications - Earthworks & Formation Standard | L1-CHE-STD-029 (VERSION 4) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Australian Standard - Methods of testing soils for engineering purposes | AS 1289 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Subgrade Description | L1-CHE-SPE-178 - Clause 5.5.1. Table 1 AS1289 Tests 5.1.1 & 5.3.1 | Subgrade shall comply with the following criteria: • Soaked CBR - 3% min nominal • Plasticity Index 9-20% • Dispersion (pin hole dispersity) - ND1/ND2 • Dispersion (Emerson class number of soil) - not to be class 1 or 2 • Collapse strain - to be agreed by MTM geotechnical engineer • Free swell index - 2.5% max. • Soil soluble salt content - 3% • Organic content (dry weight) - 2% max. Refer to AS 1289 for Tests | Document Review | Once, for each material type - prior to works commencement | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate
3 | Preliminaries - Procedures & Documentation
3.1 | Pre-Commencement of Fill Works | L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer. | Visual Inspection | Prior to commencement of fill works | HP | SE/PE | This ITP Signed Off MTM representative signoff Attach: Site Photos
4 | Pre-Construction Activities
4.1 | Approval of IFC drawings | GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Approved IFC Drawings | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off
4.2 | Survey Set Out | IFC Drawings | Set out pegs in place and clearly mark out limits of works. | Visual Inspection | Prior to commencement of fill works | HP* | SE/PE/SPE | This ITP Signed Off
5 | Construction Activities
5.1 | Subgrade Preparation and Installation - For track constructed on embankment (1 of 3) | L1-CHE-SPE-178 - Clause 5.4. | If min CBR < 3%: - Install min 1m structural fill If general fill is to be placed directly over subgrade: - Subgrade to be compacted to 98% If structural fill is to be placed directly over subgrade: - Subgrade shall be scarified to 200mm and re-compacted to 100% • One test per 1000m³ • Volume < 1000m³ atleast one set of tests shall be carried out | Standard Compaction Test | Each Lot | HP | SE/PE | This ITP Signed Off Attach: Compaction Test Report
5.2 | Subgrade Preparation and Installation - For track constructed on embankment (2 of 3) | L1-CHE-SPE-178 - Clause 5.4. | If min 3%< CBR < 8%: If general fill is to be placed directly over subgrade - Subgrade to be compacted to 98% (Standard Compaction Test) If structural fill is to be placed directly over subgrade - Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test) • One test per 1000m³ • Volume < 1000m³ atleast one set of tests shall be carried out | Standard Compaction Test | Each Lot | HP | SE/PE | This ITP Signed Off Attach: Compaction Test Report
5.3 | Subgrade Preparation and Installation - For track constructed on embankment (3 of 3) | L1-CHE-SPE-178 - Clause 5.4. | If min CBR > 8% - Excavation can be stopped to suit capping layer or at top of section with CBR > 8% - Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test) • One test per 1000m³ • Volume < 1000m³ atleast one set of tests shall be carried out | Standard Compaction Test | Each Lot | HP | SE/PE | This ITP Signed Off Attach: Compaction Test Report
5.4 | Proof rolling | L1-CHE-SPE-178 - Clause 4.6. and 5.4.1. | Proof roll as per L1-CHE-SPE-178 - Clause 4.6. | Proof roll | Each Lot | HP | SE | This ITP Signed Off MTM representative Signoff
6 | Subgrade Finishing and Tolerances
6.1 | Subgrade Finishing and Tolerances - For track constructed on embankment / Survey Conformance | L1-CHE-SPE-178 - Clause 5.7. | Subgrade on embankments shall be installed within +/- 40mm of approved design surface level | Document Review | Each Lot | IP | SE/Surveyor | This ITP Signed Off Attach: Survey Conformance Report
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /