## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-138-RAIL-BRUNT-Aluminothermic Welding and Stressing Rev.0 | itp |  |  |  |  | ITP-138-RAIL-BRUNT-Aluminothermic Welding and Stressing Rev.0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-138-RAIL-BRUNT-Aluminothermic Welding and Stressing
label | ITP Description: Aluminothermic Welding and Stressing
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 0
label | Revision Date: 14/03/2024
label | ITP created by: Mac Cameron
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
checkpoint | 1.2 - Railway Track Materials – Part 1: Steel Rails
label | Reference - AS 1085.1
checkpoint | 1.3 - Welding Rail Steels
label | Reference - AS 1085.2
checkpoint | 1.4 - Flash Butt Welding Specification
label | Reference - A1340
checkpoint | 1.5 - Hot Works Procedure
label | Reference - A1606
checkpoint | 1.6 - Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure
label | Reference - A4597
checkpoint | 1.7 - Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure
label | Reference - A4589
checkpoint | 1.8 - Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure
label | Reference - A4598
checkpoint | 1.9 - PTDT Form B - Track Certifier Booking Form
label | Reference - A4263a
checkpoint | 1.10 - Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
label | Reference - A4588
checkpoint | 1.11 - Non-Destructive Hand Testing Of Rail - Track Procedure
label | Reference - A4550
checkpoint | 1.12 - Track Construction - ITP
label | Reference - ITP-139-RAIL-BRUNT-Track Construction
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Supply of Weld Kits
label | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
label | Acceptance Criteria - Weld kits supplied are within expiry period and conform to the requirements of applicable standards.
label | Method - Visual Measure, Document Review
label | Frequency - Upon Delivery
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Delivery Dockets/Site Photos
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Primary Documentations
label | Reference - A4263 PTDT Form B - Track Certifier Booking Form A1606 Hot Works Procedure
label | Acceptance Criteria - Approved PTDT Works to be completed in accordance with Hot Work Procedure.
label | Method - Document review and approval
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Approved PTDT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Pre-Commencement of Work
label | Reference - ITP, Quality Checklist, SWMS,
label | Acceptance Criteria - All approved by relevant representative.
label | Method - Document review and approval
label | Frequency - Once (Prior to Works)
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Approved templates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Welding Procedures & Quality Documentation
label | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
label | Acceptance Criteria - WPS (Welding Procedure Specifications), WPQR (Welding Procedure Qualification Records), WQR (Welder Qualification Register)
label | Method - Document review and approval
label | Frequency - Once (Prior to Works)
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Approval of IFC drawings
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Approved IFC Drawings
label | Method - Document review and approval
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
section | 5. Construction Activities
checkpoint | 5.1 - Aluminothermic Welding
label | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails
label | Acceptance Criteria - Verify Aluminothermic welding carried out in accordance with AS1085.20
label | Method - Visual Inspection
label | Frequency - As Task Progresses
label | Category - IP
label | Responsibility - SE/PE, Track Supervisor, Welder
label | Verifying Documents - This ITP Signed Off
label | Attach: Site Photos
checkpoint | 5.2 - Alignment of Welds
label | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails L2-TRK-PRO-014 Welded Track Management Manual Chapter 11 – Rail Welding Process Section 4.9
label | Acceptance Criteria - Alignment inspection shall be carried out on each weld and record results.
label | ○ Horizontal Alignment ± 0.5mm
label | ○ Vertical Alignment + 0.5mm, - 0.0mm
label | Method - Visual Inspection, Test & Measure
label | Frequency - Each Weld
label | Category - IP
label | Responsibility - SE/PE, Track Supervisor, Welder
label | Verifying Documents - This ITP Signed Off
label | Attach: Inspection Records & site photos
checkpoint | 5.3 - Welder's Identification Marks
label | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails A1340 Flash Butt Welding Specification Section 4.3.5
label | Acceptance Criteria - Stamp ID on the field side of the rail head adjacent to the weld.
label | Method - Visual Inspection
label | Frequency - Each Weld
label | Category - IP
label | Responsibility - SE/PE, Track Supervisor, Welder
label | Verifying Documents - This ITP Signed Off
label | Attach: Site Photos
checkpoint | 5.4 - Stressing Track Lengths
label | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails A4200 Metro Track - Management Chapter 11 Welding Process Procedure Section 5 A4598 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure Table 7.
label | Acceptance Criteria - Ensure track lengths area stressing accordance with Metro Track - Management Chapter 11 Welding Process Procedure (A4200), Minimum Closure Length taken as 13. 7 meters if not Detailed in Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure (A4598) table 7.
label | Method - Survey and Visual Inspection
label | Frequency - As Task Progresses
label | Category - IP
label | Responsibility - SE/PE, Track Supervisor, Track Surveyor
label | Verifying Documents - This ITP Signed Off
label | Attach: Inspection Records & site photos
checkpoint | 5.5 - Stress Free Temperature
label | Reference - A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 5.1.2
label | Acceptance Criteria - The design SFT is 38°C and all stressing is to be carried out to this design SFT.
label | Method - Test and Measure
label | Frequency - Each Weld
label | Category - IP
label | Responsibility - SE/PE, Track Supervisor, Welder
label | Verifying Documents - This ITP Signed Off
label | Attach: Inspection Records & site photos
checkpoint | 5.6 - Weld Ultrasonic Testing
label | Reference - A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2. A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 6.20
label | Acceptance Criteria - Ultrasonic testing to be carried out within 14 days and in accordance with A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
label | ○ The cross section of the area of the head and web shall be completely scanned;
label | – The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
label | – Welds shall be scanned to both directions.
label | Method - Inspection / Test
label | Frequency - Each Weld within 14 days
label | Category - IP
label | Responsibility - SE/PE, Track Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: Ultrasonic Weld Test Results
section | 6. Post-Construction Activities
checkpoint | 6.1 - Rail Stressing Records
label | Reference - A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 6.21
label | Acceptance Criteria - Complete Stressing Recorded documentation
label | Method - Measure and Document Review
label | Frequency - Each Weld
label | Category - IP
label | Responsibility - SE/PE, Track Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: Rail Stressing Documentation
checkpoint | 6.2 - Track Certification
label | Reference - MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE
label | Acceptance Criteria - - Track Geometry Conformance Certificate - Track System and Component
label | Method - Visual Measure, Document Review
label | Frequency - Once (upon completion of occupation works)
label | Category - HP
label | Responsibility - Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure
label | Verifying Documents - This ITP Signed Off
label | Attach: Relevant Conformance Certs as per acceptance criteria
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - As-Built Drawings
label | Reference - As-Built Drawing Management Procedure (A8197)
label | Acceptance Criteria - IFC drawings (including cables, patches and labels) are marked up with redlines and supplied the Project and MTM.
label | Method - Document review and approval
label | Frequency - Once
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Redline mark-up drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MTM Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP