## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-139-RAIL-BRUNT-Track Construction Rev.0 | itp |  |  |  |  | ITP-139-RAIL-BRUNT-Track Construction Rev.0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-139-RAIL-BRUNT-Track Construction
label | ITP Description: Track Construction
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 0
label | Revision Date: 14/03/2024
label | ITP created by: Mac Cameron
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
checkpoint | 1.2 - Railway Track Materials – Part 1: Steel Rails
label | Reference - AS 1085.1
checkpoint | 1.3 - Welding Rail Steels
label | Reference - AS 1085.2
checkpoint | 1.4 - Concrete Sleepers Specification
label | Reference - A1504
checkpoint | 1.5 - Track Geometry Tolerances
label | Reference - A1303
checkpoint | 1.6 - Ballast Supply Specification
label | Reference - A1341
checkpoint | 1.7 - Transit Space Clearances
label | Reference - A1536
checkpoint | 1.8 - Track Design And Construction
label | Reference - A1545
checkpoint | 1.9 - Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure
label | Reference - A4598
checkpoint | 1.10 - Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure
label | Reference - A4597
checkpoint | 1.11 - Aluminothermic Weld and Stressing - Inspection and Test Plan Template
label | Reference - A7949
checkpoint | 1.12 - PTC Heavy Rail Track Construction Standards
label | Reference - N/A - no document reference number
checkpoint | 1.13 - PTC Heavy Rail Track Construction Standards Drawing
label | Reference - F598
checkpoint | 1.14 - Earthworks & Formation Specification
label | Reference - L1-CHE-SPE-178 (VERSION 3)
checkpoint | 1.15 - Earthworks & Formation Standard
label | Reference - L1-CHE-STD-029 (VERSION 4)
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Supply of 60mm Ballast
label | Reference - A1341 Ballast Supply Specification Section 4.2.2
label | Acceptance Criteria - The Ballast supplied must be tested and meet requirements in MTM standard Ballast Supply Specification (A1341) Table 3
label | Method - Visual Measure, Document Review
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Supply of FDCS Sleepers
label | Reference - A1303 Track Geometry Tolerances Section 8.1.13 A1504 Concrete Sleepers Specification Table 2
label | Acceptance Criteria - Sleepers supplied must be type approved by MTM and in accordance with the relevant standard.
label | Method - Visual Measure, Document Review
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Supply of 53kg/m Rail
label | Reference - One Steel Certificate, Flashbutt Weld Reports
label | Acceptance Criteria - AS 1085.1 Railway Track Materials – Part 1: Steel Rails AS 1085.20 Welding Rail Steels Section 2
label | Method - Visual Measure Document Review
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: One Steel Certificate, Flashbutt Weld Reports, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Supply of: Track Jewellery, Geofabric
label | Acceptance Criteria - To be type approved by MTM.
label | ○ To be inspected upon delivery to have no damage or rust.
label | Method - Visual Measure
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Primary Documentations
label | Reference - A4263 PTDT Form B - Track Certifier Booking Form A1606 Hot Works Procedure
label | Acceptance Criteria - Approved PTDT
label | Method - Document review and approval
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Approved PTDT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Pre-Commencement of Work
label | Reference - ITP, Quality Checklist, SWMS
label | Acceptance Criteria - All approved by relevant representative.
label | Method - Document review and approval
label | Frequency - Once (Prior to Works)
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Approved Templates
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Approval of IFC drawings
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Approved IFC Drawings
label | Method - Document review and approval
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
section | 5. Construction Activities
checkpoint | 5.1 - Survey Track Alignment
label | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Correct line and level established for placement of Sleepers and Ballast as per IFC.
label | Method - Visual Inspection, Survey / Measure
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE, Track Supervisor, Track Surveyor
label | Verifying Documents - This ITP Signed Off
label | Attach: Survey Records & Photos on site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Lay Bottom Ballast
label | Reference - PTC Heavy Rail Track Construction Standards Drawing F598
label | Acceptance Criteria - Ballast to be placed in 150mm max layers. Bottom Ballast to be left 20-40mm below final design level – Tolerance (under sleeper) -0mm, +25mm
label | Method - Visual Inspection Survey / Measure
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE, Track Supervisor, Track Surveyor
label | Verifying Documents - This ITP Signed Off
label | Attach: Survey Records & Photos on site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Place Sleepers
label | Reference - A1303 Track Geometry Tolerances Table 1 A4597 Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure Section 4.8
label | Acceptance Criteria - Sleepers Square at nominal 685mm ±25mm.
label | ○ 2 concrete sleepers either side of welds
label | ○ Up to 50mm variation in spacing to allow for clearance around a thermit weld (only over two sleepers)
label | Method - Visual Inspection, Survey / Measure
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE, Track Supervisor, Track Surveyor
label | Verifying Documents - This ITP Signed Off
label | Attach: Survey Records & Photos on site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Rail Installation
label | Reference - A4598 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure Section 4.1.1, 4.1.2 and Table 7 Aluminothermic Weld and Stressing - Inspection and Test Plan
label | Acceptance Criteria - Plain line Aluminothermic welds square and centrally located in beds.
label | ○ Alignment inspection shall be carried out on each weld and record results.
label | ○ Horizontal Alignment ± 0.5mm
label | ○ Vertical Alignment + 0.5mm, - 0.0mm
label | ○ Rail ends identified & clearly marked for visibility of joint.
label | ○ All fastenings must be fully applied.
label | ○ Minimum Closure Length taken as 13. 7meters if not Detailed in A4598 table 7.
label | ○ Complete Aluminothermic Weld and Stressing - Refer to Aluminothermic Weld and Stressing ITP
label | Method - Visual Inspection, Measure
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE, Track Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: Photos on site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Sleeper Alignment and Rail Jewellery
label | Reference - PTC Heavy Rail Track Construction Standards Drawing F598
label | Acceptance Criteria - Sleeper alignment complies to square with centreline for tangent track.
label | ○ Rail jewellery secure and installed correctly
label | Method - Visual Inspection
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE, Track Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: Photos on site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Tamp New Track
label | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 A1536 Transit Space Clearances Figure 1 and section 9.2
label | Acceptance Criteria - Tamp track as per IFC design and within below tolerances:
label | ○ Gauge +3 / -3
label | ○ Gauge Variation in 2m 4
label | ○ Line (10m Chord) +4 / -4
label | ○ Twist (3.5m Chord) +2 / -2
label | ○ Top (10m Chord) +5 / -5
label | ○ Cant +5 / -5
label | ○ General Alignment +15/ -15
label | – A minimum horizontal clearance of 3.0m from track centreline to structure.
label | – Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached
label | Method - Visual Inspection, Tamping Geometry Recording, Measure / Survey Pickup
label | Frequency - Once (Post Tamping)
label | Category - HP
label | Responsibility - Tamping Operator, Track Surveyor, Overhead Engineer, Track Supervisor, SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Photos on site, Tamping Geometry Report, Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Regulate and Check Ballast profile
label | Reference - A1537 Earthworks And Formation Standard Section 9 PTC Heavy Rail Track Construction Standards Drawing F598
label | Acceptance Criteria - As per IFC drawings; 405mm from sleeper end tangent track
label | ○ 1 in 1.5 steepest shoulder slope.
label | Method - Visual Inspection, Measure
label | Frequency - Once
label | Category - HP
label | Responsibility - SE/PE, Track Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: Photos on site
holdpoint | AUTHORITY HOLDPOINT
section | 6. Post-Construction Activities
checkpoint | 6.1 - As-Built Survey
label | Reference - As-Built Drawing Management Procedure (A8197)
label | Acceptance Criteria - Track survey to be carried out at completion of works. Track levels compared to IFC and ensure tolerances are met
label | Method - Survey and Review
label | Frequency - Once
label | Category - HP
label | Responsibility - Track Surveyor, SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: As-Built survey report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Track Certification
label | Reference - MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE
label | Acceptance Criteria - - Track Geometry Conformance Certificate - Track System and Component
label | Method - Visual Measure, Document Review
label | Frequency - Once (upon completion of occupation works)
label | Category - HP
label | Responsibility - Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure
label | Verifying Documents - This ITP Signed Off
label | Attach: Relevant Conformance Certs as per acceptance criteria
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - As-Built Drawings
label | Reference - As-Built Drawing Management Procedure (A8197)
label | Acceptance Criteria - IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM.
label | Method - Document review and approval
label | Frequency - Once
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Redline mark-up drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MTM Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP